## user stories
project ID | story ID | status | status icon | sprint | size | points | development champion | suitable for external demo | percentage complete | comment
Collision Awareness | 001 – Perforce Server Setup | accepted | 3 | 1309 | S | 2 | Christopher Lum
Collision Awareness | 002 – Perforce Visual Client | accepted | 3 | 1309 | S | 2 | Christopher Lum
Collision Awareness | 003 – Forward State Estimator Feature Level Design | accepted | 3 | 1309 | L | 5 | Kevin Ueunten
Collision Awareness | 004 – Literature Review (Collision Avoidance) | accepted | 3 | 1310 | M | 3 | Al Creigh
Collision Awareness | 005 – ICOMC2 Partners Program | in backlog | 0 | - | M | 3 | Christopher Lum | no |  | waiting on Insitu
Collision Awareness | 006 – Software Developer Background Training (Algorithm and Back End) | accepted | 3 | 1311 | L | 5 | Matthew Davis | no |  | 90%
Collision Awareness | 007 – Software Developer Infrastructure Setup | in backlog | 0 | - | L | 5 | Christopher Lum | no |  | waiting on Insitu
General AFSL Lab | 008 – Software Developer Background Training (UI and Front End) | in backlog | 0 | - | - | #N/A | -
Unfiled | 009 – ICOMC2 Operator Familiarization | in backlog | 0 | - | L | 5 | -
Collision Awareness | 010 – Plugin Prototype Development | in backlog | 0 | - | XL | 8 | Christopher Lum
Collision Awareness | 011 – Forward State Estimator Implementation (Free Flight) | accepted | 3 | 1403 | L | 5 | Kevin Ueunten |  |  | 50%
Collision Awareness | 012 – Air Traffic Controller Interaction | accepted | 3 | 1309 | M | 3 | Al Creigh
Collision Awareness | 013 – Perforce Visual Client (copy) | accepted | 3 | 1309 | S | 2 | Al Creigh
Collision Awareness | 014 – Perforce Visual Client (copy) | accepted | 3 | 1309 | S | 2 | Kevin Ueunten
Collision Awareness | 015 – Perforce Visual Client (copy) | accepted | 3 | 1309 | S | 2 | Bao Le
Collision Awareness | 016 – Perforce Visual Client (copy) | accepted | 3 | 1309 | S | 2 | Madison Peck
Collision Awareness | 017 – Perforce Visual Client (copy) | accepted | 3 | 1309 | S | 2 | Matthew Davis
Collision Awareness | 018 – Perforce Visual Client (copy) | accepted | 3 | 1309 | S | 2 | Taras Eremenko
Collision Awareness | 019 – Perforce Visual Client (copy) | accepted | 3 | 1309 | S | 2 | Daniel Ablog
Collision Awareness | 020 – Perforce Visual Client (copy) | accepted | 3 | 1311 | S | 2 | Henry Qin | no |  | 100%
Collision Awareness | 021 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1312 | L | 5 | Kevin Ueunten | no |  | 50%
Collision Awareness | 022 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1312 | L | 5 | Bao Le | no
Collision Awareness | 023 – Search and Rescue Movie Capture | accepted | 3 | 1310 | XS | 1 | Al Creigh | no
Collision Awareness | 024 – UW Project Infrastructure Step 1 | accepted | 3 | 1309 | M | 3 | Christopher Lum
Collision Awareness | 025 – Perforce Depot Backup | accepted | 3 | 1310 | L | 5 | Federico Alvarez | no
Collision Awareness | 026 – Matlab Simulation Framework | accepted | 3 | 1310 | L | 5 | Kevin Ueunten | demoable |  | Discussion needed about Conflict entity, isinairspace function, other than that 3 scenarios were created and documented via a simulation movie. Also need to present simulator to group.
Collision Awareness | 027 – Forward State Estimator R&D Prototype | accepted | 3 | 1310 | L | 5 | Kevin Ueunten | no
Collision Awareness | 028 – Image Insitu Development Machines | accepted | 3 | 1310 | M | 3 | Bao Le | no
Collision Awareness | 029 – Literature Review (Separation Management) | accepted | 3 | 1310 | M | 3 | Al Creigh | demoable
Collision Awareness | 030 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1313 | L | 5 | Federico Alvarez
Collision Awareness | 031 – Vehicle Class for R&D Matlab Prototype | accepted | 3 | 1310 | M | 3 | Madison Peck | demoable
Unfiled | 032 – Search and Rescue Plugin Familiarization | in backlog | 0 | - | - | #N/A | -
Collision Awareness | 033 – Unit Testing Background Training | accepted | 3 | 1311 | L | 5 | Madison Peck | no |  | 100%
Collision Awareness | 034 – Review Journal of Aircraft Article | accepted | 3 | 1310 | S | 2 | Noel Kimber | no
Collision Awareness | 035 – Conflict Entity Class for R&D Matlab Prototype | accepted | 3 | 1310 | M | 3 | Al Creigh | demoable
Collision Awareness | 036 – AFSL Website Update | accepted | 3 | 1310 | M | 3 | Bao Le | no
Collision Awareness | 037 – Team Contact Information Document | accepted | 3 | 1310 | XS | 1 | Noel Kimber | no
Collision Awareness | 038 – Insitu Project Plan Document | dropped | #N/A | 1410 | M | 3 | Christopher Lum |  |  | waiting on Insitu
Collision Awareness | 039 – Simulation Test Plan Design and Documentation | accepted | 3 | 1310 | M | 3 | Taras Eremenko | demoable
Collision Awareness | 040 – Separation Management Feature Level Design | accepted | 3 | 1310 | L | 5 | Matthew Davis | demoable
Collision Awareness | 041 – Perforce Visual Client (copy) | accepted | 3 | 1310 | S | 2 | Noel Kimber | no
Collision Awareness | 042 – Prepare for Sprint 1310 External Demo | accepted | 3 | 1310 | S | 2 | Christopher Lum | no
Collision Awareness | 043 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1312 | L | 5 | Noel Kimber | no
Collision Awareness | 044 – FlexRotor Movie Capture | accepted | 3 | 1311 | XS | 1 | Seunghyun Ko | no |  | 100%
Collision Awareness | 045 - Image Insitu Development Machines (part 2) | accepted | 3 | 1411 | M | 3 | Christopher Lum |  | 100%
Collision Awareness | 046 – AFSL Website Update (part 2) | dropped | #N/A | 1410 | S | 2 | Bao Le |  |  | 75%. In Kim's hands
Collision Awareness | 047 - JCATI Marketing Video Production | accepted | 3 | 1312 | M | 3 | Daniel Ablog | yes |  | 75%
Collision Awareness | 048 - Conflict Entity Iteration 2 | accepted | 3 | 1312 | XS | 1 | Matthew Davis | no
Collision Awareness | 049 - Literature Review (part 2) | accepted | 3 | 1311 | M | 3 | Al Creigh | no |  | 80%
Collision Awareness | 050 – Matlab Simulator Presentation | accepted | 3 | 1311 | S | 2 | Kevin Ueunten | no
Collision Awareness | 051 – Separation Notifier Feature Level Design (Part 2) | accepted | 3 | 1311 | M | 3 | Matthew Davis | no |  | 90%
Collision Awareness | 052 – Perforce Change List Code Review Verbiage | dropped | #N/A | 1312 | S | 2 | Noel Kimber |  |  | consider dropping
Collision Awareness | 053 – Forward State Estimator Feature Level Design Update | accepted | 3 | 1311 | M | 3 | Kevin Ueunten | no |  | 50%
General AFSL Lab | 054 – Windows Presentation Foundation Controls Familiarization | in backlog | 0 | - | L | 5 | -
Collision Awareness | 055 – Perforce Visual Client (copy) | accepted | 3 | 1312 | S | 2 | John Marshall | no
Collision Awareness | 056 – Perforce Visual Client (copy) | accepted | 3 | 1311 | S | 2 | Keisuke Tsujita | no |  | 100%
Collision Awareness | 057 – Perforce Visual Client (copy) | accepted | 3 | 1311 | S | 2 | Dai Tsukada | no |  | 100%
Collision Awareness | 058 – Visual Studio Via DreamSpark | dropped | #N/A | 1410 | S | 2 | Noel Kimber |  |  | waiting for Insitu to decide what to do
Collision Awareness | 059 – C# Vehicle Class | accepted | 3 | 1311 | L | 5 | Madison Peck | yes |  | 50%
Collision Awareness | 060 – C# ConflictEntity Class | accepted | 3 | 1312 | L | 5 | Federico Alvarez | yes |  | 95% | Need Code and Power Point to be peer review
Collision Awareness | 061 – JCATI Quarterly Progress Report | accepted | 3 | 1311 | S | 2 | Christopher Lum | yes |  | 50%
Collision Awareness | 062 – Prepare for Sprint 1311 External Demo | accepted | 3 | 1311 | S | 2 | Christopher Lum | no |  | 0%
Collision Awareness | 063 – Continuous Time, Dynamic Vehicle Model | accepted | 3 | 1311 | XS | 1 | Kevin Ueunten | no |  | 40%
Collision Awareness | 064 – Forward State Estimator C# Implementation | accepted | 3 | 1406 | S | 2 | Kevin Ueunten
Collision Awareness | 065 – Separation Notifier Matlab R&D Prototype | accepted | 3 | 1312 | M | 3 | Matthew Davis | no |  | Matt will be moving tasks around
Collision Awareness | 066 – New Team Member Orientation | accepted | 3 | 1311 | XS | 1 | Federico Alvarez | no
Collision Awareness | 067 – Perforce Visual Client (copy) | accepted | 3 | 1311 | S | 2 | Seunghyun Ko | no |  | 100%
Collision Awareness | 068 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1312 | L | 5 | Daniel Ablog | no |  | 75%
Collision Awareness | 069 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1311 | L | 5 | Madison Peck | no |  | 100%
Collision Awareness | 070 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1312 | L | 5 | Al Creigh | no |  | 25%
General AFSL Lab | 071 – Software Developer Background Training (Algorithm and Back End) (copy) | dropped | #N/A | - | L | 5 | Zach Caratao |  | 10%
Collision Awareness | 072 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1313 | L | 5 | Henry Qin
Collision Awareness | 073 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1312 | L | 5 | Keisuke Tsujita | no |  | 95%
Collision Awareness | 074 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1312 | L | 5 | Seunghyun Ko | no |  | 90%
Collision Awareness | 075 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1312 | L | 5 | Dai Tsukada | no
Collision Awareness | 076 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1311 | L | 5 | Richard Fukutome | no
Collision Awareness | 077 – Perforce Visual Client (copy) | accepted | 3 | 1311 | S | 2 | Richard Fukutome | no |  | 100%
Unfiled | 078 – ICOMC2 Operator Familiarization (copy) | in backlog | 0 | - | L | 5 | -
Collision Awareness | 079 – WebEx Account Investigation | accepted | 3 | 1311 | XS | 1 | Dai Tsukada | no |  | 50%
Collision Awareness | 080 – Successive Separation Notification | in backlog | 0 | - | - | #N/A | -
Collision Awareness | 081 – Windows Presentation Foundation Controls Familiarization (copy) | dropped | #N/A | 1404 | L | 5 | Dai Tsukada |  |  | look at this again
Collision Awareness | 082 – Perforce Visual Client (copy) | accepted | 3 | 1311 | S | 2 | Brian Chang | no |  | 50%
Collision Awareness | 083 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1312 | L | 5 | Brian Chang | no |  | 75%
Collision Awareness | 084 – Unit Testing for Sprint 1311 | accepted | 3 | 1312 | S | 2 | Christopher Lum | no |  | 75%
Collision Awareness | 085 – FAA National Airspace Integration Research and Literature Review | accepted | 3 | 1401 | M | 3 | Federico Alvarez | yes |  | this is a short 30 second demo | Need to present results to group and incorporate feedback
Collision Awareness | 086 – UW Solution Unit Testing Spreadsheet Backlog (Group 1) | accepted | 3 | 1402 | S | 2 | Richard Fukutome
Collision Awareness | 087 – UW Solution Missing Unit Testing Creation (Group 1) | in backlog | 0 | - | S | 2 | -
Collision Awareness | 088 - JCATI Marketing Video Production (part 2) | accepted | 3 | 1312 | M | 3 | Henry Qin | yes |  | 75%
Collision Awareness | 089 – UW Solution Unit Testing Spreadsheet Backlog (Group 2) | accepted | 3 | 1312 | S | 2 | Bao Le | yes |  |  |  | 0
Collision Awareness | 090 – UW Solution Unit Testing Spreadsheet Backlog (Group 3) | accepted | 3 | 1401 | S | 2 | Brian Chang
Collision Awareness | 091 – UW Solution Unit Testing Spreadsheet Backlog (Group 4) | accepted | 3 | 1403 | S | 2 | Dai Tsukada |  |  | 50%
Collision Awareness | 092 – UW Solution Unit Testing Spreadsheet Backlog (Group 5) | accepted | 3 | 1313 | S | 2 | Daniel Ablog
Collision Awareness | 093 – UW Solution Unit Testing Spreadsheet Backlog (Group 6) | accepted | 3 | 1313 | S | 2 | Federico Alvarez
Collision Awareness | 094 – UW Solution Unit Testing Spreadsheet Backlog (Group 7) | accepted | 3 | 1313 | S | 2 | Henry Qin
Collision Awareness | 095 – UW Solution Unit Testing Spreadsheet Backlog (Group 8) | accepted | 3 | 1401 | S | 2 | Keisuke Tsujita
Collision Awareness | 096 – UW Solution Unit Testing Spreadsheet Backlog (Group 9) | accepted | 3 | 1312 | S | 2 | Kevin Ueunten | yes |  | block from CL
Collision Awareness | 097 – UW Solution Unit Testing Spreadsheet Backlog (Group 10) | accepted | 3 | 1313 | S | 2 | Matthew Davis
Collision Awareness | 098 – UW Solution Unit Testing Spreadsheet Backlog (Group 11) | accepted | 3 | 1313 | S | 2 | Noel Kimber
Collision Awareness | 099 – UW Solution Unit Testing Spreadsheet Backlog (Group 12) | accepted | 3 | 1401 | S | 2 | Seunghyun Ko
Collision Awareness | 100 – UW Solution Unit Testing Spreadsheet Backlog (Group 13) | accepted | 3 | 1402 | S | 2 | Richard Fukutome
CERES | 1000 - Meadowbrook Flight Test | accepted | 3 | 1605 | M | 3 | Alec Bueing
CERES | 1001 - Meadowbrook Flight Test | accepted | 3 | 1605 | M | 3 | Mia Lee
CERES | 1002 - Meadowbrook Flight Test | accepted | 3 | 1605 | M | 3 | Tyler Leis
CERES | 1003 - Meadowbrook Flight Test | accepted | 3 | 1605 | M | 3 | Navdeep Sandhu
CERES | 1004 - Meadowbrook Data Reduction | accepted | 3 | 1605 | L | 5 | Alec Bueing
CERES | 1005 - CERES Airframe Repair | accepted | 3 | 1605 | M | 3 | Tyler Leis
CERES | 1006 - CERES Airframe Repair - Helper | accepted | 3 | 1605 | M | 3 | Navdeep Sandhu
CERES | 1007 – Magnuson Flight test preparation | accepted | 3 | 1605 | M | 3 | Harrison Stankey
CERES | 1008 – Magnuson Flight test preparation - Helper | accepted | 3 | 1605 | M | 3 | Brian Carpenter
CERES | 1009 - Magnuson Flight test preparation and modication | accepted | 3 | 1605 | M | 3 | Mia Lee
Collision Awareness | 101 – UW Solution Unit Testing Spreadsheet Check | accepted | 3 | 1402 | S | 2 | Noel Kimber |  |  | 25%
CERES | 1010 - Final Poster Creation | accepted | 3 | 1606 | M | 3 | Brian Carpenter
CERES | 1011 - Final Poster Creation - Helper | accepted | 3 | 1606 | M | 3 | Harrison Stankey
CERES | 1012 – CERES Final Design Review Presenter – Position 1 | accepted | 3 | 1606 | L | 5 | Brian Carpenter
CERES | 1013 – CERES Final Design Review Presenter – Position 2 | accepted | 3 | 1606 | L | 5 | Harrison Stankey
CERES | 1014 – CERES Final Design Review Presenter – Position 3 | accepted | 3 | 1606 | L | 5 | Mia Lee
CERES | 1015 – CERES Final Design Review Presenter – Position 4 | accepted | 3 | 1606 | L | 5 | Tyler Leis
CERES | 1016 – CERES Final Design Review Presenter – Position 5 | accepted | 3 | 1606 | L | 5 | Navdeep Sandhu
CERES | 1017 – CERES Final Design Review Presenter – Position 6 | accepted | 3 | 1606 | L | 5 | Alec Bueing
CERES | 1018 - CERES Budget Manager | accepted | 3 | 1606 | L | 5 | Mia Lee
Visual Anchoring | 1019 - Visual Anchoring Journal Article | in backlog | 0 | 1908 | XL | 8 | Tadej Kosel |  | 0%
Collision Awareness | 102 – UW Solution Missing Unit Testing Creation (Group 2) | accepted | 3 | 1402 | M | 3 | Brian Chang |  |  | 75%
CERES | 1020 - CERES Journal Article | dropped | #N/A | 1705 | XL | 8 | Chris Nee
Mapping | 1021 - Mapping Journal Article | dropped | #N/A | 1705 | XL | 8 | Vitor Vasconcelos
General AFSL Lab | 1022 – Arduino with Matlab and Simulink | accepted | 3 | 1702 | XL | 8 | Daniel Arzouman |  | 30%
General AFSL Lab | 1023 – Arduino with Matlab and Simulink (Update Documentation) | accepted | 3 | 1702 | XL | 8 | Daniel Arzouman |  | 10%
General AFSL Lab | 1024 – Arduino with Matlab and Simulink (Position 2) | accepted | 3 | 1702 | XL | 8 | Nathan Isaman |  | 30% | Performing intial set-up and testing; stuck at a debugging stage prior to deploying to the Due
General AFSL Lab | 1025 – Arduino with Matlab and Simulink (Update Documentation) (Position 2) | accepted | 3 | 1702 | XL | 8 | Nathan Isaman |  | 10%
General AFSL Lab | 1026 – Custom Mission Planner and ArduPlane Builds | accepted | 3 | 1607 | L | 5 | Yifu Wang |  | 30%
General AFSL Lab | 1027 – Custom Flight Mode Build | accepted | 3 | 1607 | L | 5 | Yifu Wang |  | 10%
JCATI 2016 | 1028 – AFSL Large Multi-Rotor Build | accepted | 3 | 1611 | XL | 8 | Zachary Williams |  | 30%
JCATI 2016 | 1029 – ArduCopter Testing and Implementation | dropped | #N/A | 1608 | XL | 8 | Zachary Williams |  | 50%
Collision Awareness | 103 – UW Solution Missing Unit Testing Creation (Group 3) | accepted | 3 | 1402 | M | 3 | Daniel Ablog
CERES | 1030 - CERES High Start System (Position 1) | accepted | 3 | 1607 | M | 3 | Scott An |  | 100%
CERES | 1031 - CERES High Start System (Position 2) | accepted | 3 | 1607 | M | 3 | Aaron Goldfogel |  | 100%
CERES | 1032 - CERES High Start System (Position 3) | accepted | 3 | 1607 | S | 2 | Zach Caratao |  | 100%
Mapping | 1033 - PAM ICPA Preparation | accepted | 3 | 1607 | L | 5 | Madison Mackenzie
Visual Anchoring | 1034 – Visual Anchoring Conference Paper | descoped | 6 | 1608 | XL | 8 | Tadej Kosel |  | 50%
GROVER | 1035 - GROVER Operational Checklists And Notes | accepted | 3 | 1611 | M | 3 | Zach Caratao |  | 80%
JCATI 2015 | 1036 - JCATI Flight Test TRAPIS Operator Training | in backlog | 0 | 1608 | M | 3 | Zach Caratao
JCATI 2015 | 1037 - JCATI Flight Test Payload Technician Training | descoped | 6 | 1608 | M | 3 | Selina Lui
JCATI 2015 | 1038 - JCATI Flight Test Clarity Receiver Technician Training | descoped | 6 | 1608 | S | 2 | Zhenzhen Su
JCATI 2016 | 1039 - JCATI Using Mission Planner to execute Python scripts and output distance to home data to an external computer | dropped | #N/A | 1608 | M | 3 | Zachary Williams
Flight Operations | 1039 - Using Mission Planner to Execute Python Scripts | accepted | 3 | 1611 | M | 3 | Zachary Williams
Collision Awareness | 104 – UW Solution Missing Unit Testing Creation (Group 4) | accepted | 3 | 1401 | M | 3 | Dai Tsukada
JCATI 2016 | 1040 - JCATI Drone Procurement and SDR board testing | dropped | #N/A | 1608 | M | 3 | Zachary Williams |  | 15%
Flight Operations | 1041 - 3D Printing Parts | accepted | 3 | 1608 | M | 3 | Selina Lui
Mapping | 1042 - Vulcan SLA-1500 Configuration | accepted | 3 | 1608 | XL | 8 | Scott An |  | 100%
Mapping | 1043 - Vulcan SLA-1500 Documentation | accepted | 3 | 1609 | M | 3 | Scott An |  | 90%
Flight Operations | 1044 - Flight Operations Work Items | dropped | #N/A | 1608 | XL | 8 | Hannah Rotta
JCATI 2015 | 1045 - JCATI 2015 KalmanFuser Code Updates | accepted | 3 | 1608 | M | 3 | Robert Larson
JCATI 2015 | 1046 - ADS-B Transponder Integration on Leia Aircraft | accepted | 3 | 1608 | M | 3 | Robert Larson
JCATI 2015 | 1047 - ADS-B Transponder Payload Flight Test | accepted | 3 | 1608 | S | 2 | Robert Larson
General AFSL Lab | 1048 – Perforce Visual Client (copy) | accepted | 3 | 1608 | S | 2 | Hannah Rotta
JCATI 2015 | 1049 - Luke ADS-B Transponder Payload Construction | accepted | 3 | 1609 | M | 3 | Robert Larson |  | 60%
Collision Awareness | 105 – UW Solution Missing Unit Testing Creation (Group 5) | accepted | 3 | 1402 | M | 3 | Daniel Ablog |  |  | 100%
Flight Operations | 1050 - Soldering LiPo Batteries | accepted | 3 | 1609 | S | 2 | Selina Lui |  | 90%
Flight Operations | 1051 - Skywalker 1900 Repairs and Construction | accepted | 3 | 1609 | S | 2 | Selina Lui |  | 75%
Flight Operations | 1052 - CERES and High Start Modification (Position 1) | accepted | 3 | 1609 | XS | 1 | Aaron Goldfogel
Flight Operations | 1053 - CERES and High Start Modification (Position 2) | accepted | 3 | 1609 | XS | 1 | Zach Caratao
General AFSL Lab | 1054 - Decals and Lab Information | accepted | 3 | 1609 | S | 2 | Aaron Goldfogel |  | 100%
General AFSL Lab | 1055 - Part 107 Test Preparation | accepted | 3 | 1610 | M | 3 | Aaron Goldfogel |  | 85%
Flight Operations | 1056 – Fat Shark Dominator V3 Head Tracking Configuration | accepted | 3 | 1609 | M | 3 | Scott An |  | 100%
Flight Operations | 1057 - Flight Operations Work items (Position 1) | accepted | 3 | 1609 | M | 3 | Scott An |  | 75%
Flight Operations | 1058 - Flight Operations Work Items (Position 2) | accepted | 3 | 1609 | XS | 1 | Zhenzhen Su |  | 50%
General AFSL Lab | 1059 - AFSL Battery Charging Station | accepted | 3 | 1610 | M | 3 | Chris Nee |  | 95%
Collision Awareness | 106 – UW Solution Missing Unit Testing Creation (Group 6) | accepted | 3 | 1403 | S | 2 | Seunghyun Ko
Flight Operations | 1060 - EDF jet Research | accepted | 3 | 1609 | S | 2 | Scott An |  | 100%
Flight Operations | 1061 - Talon UAS | dropped | #N/A | 1701 | L | 5 | Hannah Rotta |  | 20%
General AFSL Lab | 1062 - Camera Research for Lab | accepted | 3 | 1610 | S | 2 | Chris Nee |  | 90%
Flight Operations | 1063 - Arduplane Parameter Standardization | accepted | 3 | 1610 | S | 2 | Hannah Rotta |  | 100%
Flight Operations | 1064 - Rebuilding CONDOR | accepted | 3 | 1703 | XL | 8 | Michael Brady | yes
Flight Operations | 1065 - Skywalker 1900 Flight Characteristics | dropped | #N/A | 1812 | M | 3 | -
Flight Operations | 1066 - Checklists Software Research | accepted | 3 | 1701 | S | 2 | Karine Chen |  | 100%
General AFSL Lab | 1067 - Pre-Quarter Lab Cleanup | accepted | 3 | 1610 | S | 2 | Hannah Rotta |  | 100%
General AFSL Lab | 1068 - Create a TRAPIS Promo Video | accepted | 3 | 1706 | S | 2 | Sicong Huang
Flight Operations | 1069 - Build Falco | accepted | 3 | 1610 | S | 2 | Scott An |  | 90%
Collision Awareness | 107 – UW Solution Missing Unit Testing Creation (Group 7) | accepted | 3 | 1401 | M | 3 | Henry Qin
Flight Operations | 1070 - Create Landing Platform | accepted | 3 | 1610 | S | 2 | Max McDonald |  | 80%
General AFSL Lab | 1071 - Ensure Safety Survey Compliance | accepted | 3 | 1610 | S | 2 | Hannah Rotta |  | 100%
Visual Anchoring | 1072 - Review Visual Anchoring Conference Paper | accepted | 3 | 1610 | S | 2 | Ryan Grimes
Flight Operations | 1073 – Set Up Simulator | accepted | 3 | 1609 | XS | 1 | Hannah Rotta
General AFSL Lab | 1074 – Update Inventory Doc | accepted | 3 | 1701 | M | 3 | Karine Chen |  | 100%
General AFSL Lab | 1075 – Add Parts into Component Tracker | accepted | 3 | 1610 | L | 5 | Truc Hoa |  | 40%
Flight Operations | 1076 – Find New Flight Test Locations | accepted | 3 | 1611 | L | 5 | Karine Chen |  | 100%
General AFSL Lab | 1077 – Perforce Visual Client (copy) | accepted | 3 | 1611 | S | 2 | Aaron Su
General AFSL Lab | 1078 – Wind Tunnel Deep Storage | accepted | 3 | 1610 | XS | 1 | Hannah Rotta |  | 100%
Flight Operations | 1079 – Aircraft Part Familiarization | accepted | 3 | 1611 | S | 2 | Tommy Zhou
Flight Operations | 1079 – Aircraft Part Familiarization (copy) | accepted | 3 | 1710 | S | 2 | Sai Ranganathan
Flight Operations | 1079 – Aircraft Part Familiarization (copy) | accepted | 3 | 1702 | S | 2 | Taehan Kook |  | 100%
Collision Awareness | 108 – UW Solution Missing Unit Testing Creation (Group 8) | accepted | 3 | 1402 | M | 3 | Keisuke Tsujita |  |  | 30%
Flight Operations | 1080 – Equipment Testing | dropped | #N/A | 1703 | L | 5 | Kibaek Jeong
Flight Operations | 1081 – Battery Charging | accepted | 3 | 1610 | M | 3 | Selina Lui |  | 100%
General AFSL Lab | 1082 – Social Media Updates | in backlog | 0 | - | S | 2
General AFSL Lab | 1083 – Mission Planner Familiarization | in backlog | 0 | - | L | 5 | -
Flight Operations | 1083 – Mission Planner Familiarization (copy) | accepted | 3 | 1702 | M | 3 | Selina Lui |  | 50%
Flight Operations | 1083 – Mission Planner Familiarization (copy) | accepted | 3 | 1702 | L | 5 | Taehan Kook |  | 100%
Flight Operations | 1083 – Mission Planner Familiarization (copy) | accepted | 3 | 1702 | L | 5 | Truc Hoa |  | 100%
Flight Operations | 1084 - Part 107 Test Preparation (copy) | accepted | 3 | 1805 | M | 3 | Zachary Williams
Flight Operations | 1084 - Part 107 Test Preparation (copy) | accepted | 3 | 1706 | S | 2 | Connor Kafka
General AFSL Lab | 1084 - Part 107 Test Preparation (copy) | accepted | 3 | 1710 | M | 3 | Nicholas Price
Flight Operations | 1084 – Part 107 Test Preparation (copy) | in backlog | 0 | 1803 | M | 3
General AFSL Lab | 1085 – Unit Background Testing (copy) | dropped | #N/A | 1902 | L | 5 | -
Flight Operations | 1086 - Falco Pixhawk Assembly | accepted | 3 | 1611 | XS | 1 | Hannah Rotta |  | 80%
Flight Operations | 1087 – Falco Aircraft Manual (part 1) | accepted | 3 | 1612 | M | 3 | Tommy Zhou |  | 10%
Flight Operations | 1088 - Skywalker 1900 UAS Cradle | accepted | 3 | 1612 | M | 3 | Arwa Sait
General AFSL Lab | 1089 - New AFSL Printer | accepted | 3 | 1610 | S | 2 | Shumin Lin
Collision Awareness | 109 – UW Solution Missing Unit Testing Creation (Group 9) | accepted | 3 | 1403 | S | 2 | Dai Tsukada
JCATI 2015 | 1090 - JCATI 2015 KDLS Flight Demonstration | accepted | 3 | 1609 | XL | 8 | Robert Larson
JCATI 2015 | 1091 - JCATI 2015 KDLS Flight Demonstration (Copy 1) | accepted | 3 | 1609 | XL | 8 | Zach Caratao
JCATI 2015 | 1092 - JCATI 2015 KDLS Flight Demonstration (Copy 2) | accepted | 3 | 1609 | XL | 8 | Selina Lui
JCATI 2015 | 1093 - JCATI 2015 KDLS Flight Demonstration (Copy 3) | accepted | 3 | 1609 | XL | 8 | Zhenzhen Su
Flight Operations | 1094 – Set Up Radio Communication | accepted | 3 | 1609 | M | 3 | Hannah Rotta
General AFSL Lab | 1095 – Create a System to Track Parts | accepted | 3 | 1609 | S | 2 | Hannah Rotta
General AFSL Lab | 1096 – Create a System to Track Member Certifications | accepted | 3 | 1609 | XS | 1 | Hannah Rotta
General AFSL Lab | 1097 – Lab Cleaning and Reorganization | accepted | 3 | 1609 | S | 2 | Hannah Rotta
Flight Operations | 1098 – Create a Training Program for Simulator | accepted | 3 | 1610 | S | 2 | Hannah Rotta |  | 95%
General AFSL Lab | 1099 – Start a Maintenance Manager Spreadsheet | dropped | #N/A | 1610 | XS | 1 | Hannah Rotta
Collision Awareness | 110 – UW Solution Missing Unit Testing Creation (Group 10) | accepted | 3 | 1402 | M | 3 | Richard Fukutome |  |  | Need code review to be done
Flight Operations | 1100 – Register Argo | accepted | 3 | 1705 | XS | 1 | Hannah Rotta |  | 80%
Flight Operations | 1101 – Establish Emergency Procedures for Lost-Link, etc | dropped | #N/A | 1708 | M | 3 | -
Flight Operations | 1102 - Add Python Interpreter on AFSLPrecision02 | dropped | #N/A | 1610 | XS | 1 | Zachary Williams
General AFSL Lab | 1102 – Add Python Interpreter on AFSLPrecision02 | accepted | 3 | 1610 | XS | 1 | Zachary Williams
General AFSL Lab | 1103 – Wind Tunnel Deep Storage (Copy 1) | accepted | 3 | 1610 | XS | 1 | Selina Lui
General AFSL Lab | 1104 – Wind Tunnel Deep Storage (Copy 2) | accepted | 3 | 1610 | XS | 1 | Scott An
General AFSL Lab | 1105 - October Flight Operations | accepted | 3 | 1610 | M | 3 | Hannah Rotta
Mapping | 1106 – 3D Printing TEDD’s Camera Housing | accepted | 3 | 1611 | S | 2 | Selina Lui |  | 95% | Need to flight test
Mapping | 1107 - Mapping Administration | accepted | 3 | 1701 | L | 5 | Scott An
Mapping | 1107 - Mapping Administration | accepted | 3 | 1610 | L | 5 | Scott An |  | 10%
Mapping | 1107 - Mapping Administration | accepted | 3 | 1611 | L | 5 | Scott An
Mapping | 1107 - Mapping Administration | accepted | 3 | 1612 | L | 5 | Scott An
JCATI 2015 | 1108 - AIAA Conference Paper Draft Writing | accepted | 3 | 1610 | XL | 8 | Robert Larson
Flight Operations | 1109 - JCATI To-Do Items | accepted | 3 | 1611 | M | 3 | Connor Kafka
Collision Awareness | 111 – UW Solution Missing Unit Testing Creation (Group 11) | accepted | 3 | 1313 | M | 3 | Noel Kimber
Flight Operations | 1110 - JCATI To-Do Items (copy) | accepted | 3 | 1611 | M | 3 | Zachary Williams
Flight Operations | 1111 - ARGO Repair | accepted | 3 | 1610 | M | 3 | Connor Kafka
Flight Operations | 1112 - ARGO Repair (copy) | accepted | 3 | 1610 | M | 3 | Zachary Williams
JCATI 2016 | 1113 - Piksi RTK Flight Test (Abbreviated) | accepted | 3 | 1711 | L | 5 | Connor Kafka |  | 90%
Flight Operations | 1114 – MFOC Maintenance (part 1) | accepted | 3 | 1612 | M | 3 | Karine Chen |  | 100%
Flight Operations | 1115 - CERES Hand Launch | dropped | #N/A | 1704 | M | 3 | -
Mapping | 1116 - Canon EOS and Canon Vixia Optical Settings | accepted | 3 | 1611 | S | 2 | Daniel Matthew
Mapping | 1117 - Mapping Software Research | accepted | 3 | 1610 | M | 3 | Anupam Gupta
Mapping | 1118 - Poaching Operations Research | dropped | #N/A | 1703 | M | 3 | -
Mapping | 1119 - SLA-1500 Wireless Connection | dropped | #N/A | 1703 | L | 5 | - |  |  | investigate micro hard radio
Collision Awareness | 112 – Separation Notifier C# Implementation | accepted | 3 | 1403 | L | 5 | Matthew Davis |  |  | needs unit testing.
Flight Operations | 1120 – Falco Pixhawk Assembly (copy 1) | accepted | 3 | 1611 | M | 3 | Riley Turk
Flight Operations | 1121 – Falco Pixhawk Assembly (copy 2) | accepted | 3 | 1611 | M | 3 | James Kurniawan |  | 80%
Flight Operations | 1122 – Falco Pixhawk Assembly (copy 3) | accepted | 3 | 1611 | M | 3 | Jason Borgida
General AFSL Lab | 1123 – Trailer Tidying and Poster Hanging | accepted | 3 | 1610 | XS | 1 | Aaron Goldfogel
Flight Operations | 1124 - Register Falco with FAA | accepted | 3 | 1610 | XS | 1 | Christopher Lum
Flight Operations | 1125 - Request a Waiver for sUAS – Increase in Altitude | accepted | 3 | 1612 | M | 3 | Truc Hoa |  | 100%
Flight Operations | 1126 - Request a Waiver for sUAS – Increase in Altitude (Copy) | accepted | 3 | 1612 | M | 3 | Yifu Wang |  | 80% | waiting on lights
Flight Operations | 1127 - Flight Training Program – Fixed Wing | accepted | 3 | 1611 | XL | 8 | Aaron Goldfogel
Flight Operations | 1128 – MFOC Maintenance (copy) | dropped | #N/A | 1611 | M | 3 | Truc Hoa
General AFSL Lab | 1129 – Perforce Visual Client (copy) | accepted | 3 | 1610 | S | 2 | Karine Chen |  | 100%
Collision Awareness | 113 – Unit Testing for Sprint 1312 | accepted | 3 | 1312 | S | 2 | Christopher Lum | no
Mapping | 1130 - FPV Camera for TEDD | accepted | 3 | 1704 | M | 3 | Kibaek Jeong |  | 50% | waiting on camera
Flight Operations | 1131 – MOFC 3D Printing | accepted | 3 | 1610 | S | 2 | Selina Lui |  | 80%
Mapping | 1132 - SLA-1500 Gimbal Research | dropped | #N/A | 1702 | L | 5 | - |  |  | waiting for aircraft
Mapping | 1132 - SLA-1500 Gimbal Research (copy) | dropped | #N/A | 1703 | L | 5 | -
General AFSL Lab | 1133 – Perforce Visual Client (copy) | dropped | #N/A | 1612 | S | 2 | Daniel Matthew
General AFSL Lab | 1134 - Part 107 Test Preparation (copy) | accepted | 3 | 1610 | S | 2 | Zach Caratao
GROVER | 1135 - GROVER Maintenance | dropped | #N/A | 1801 | S | 2 | -
General AFSL Lab | 1136 - Perforce Visual Client (copy) | accepted | 3 | 1612 | S | 2 | Kibaek Jeong
General AFSL Lab | 1137 – Perforce Visual Client (copy) | accepted | 3 | 1704 | S | 2 | Riley Harris
General AFSL Lab | 1138 – Perforce Visual Client (copy) | accepted | 3 | 1611 | S | 2 | Chris Nee
General AFSL Lab | 1139 – Perforce Visual Client (copy) | accepted | 3 | 1611 | S | 2 | Shumin Lin
Collision Awareness | 114 – Developer WebEx Account Setup (Group 1) | accepted | 3 | 1312 | XS | 1 | Al Creigh | no
General AFSL Lab | 1140 – Perforce Visual Client (copy) | accepted | 3 | 1610 | S | 2 | Daniel Arzouman
General AFSL Lab | 1141 – Perforce Visual Client (copy) | accepted | 3 | 1610 | S | 2 | Michael Brady
General AFSL Lab | 1142 – Perforce Visual Client (copy) | accepted | 3 | 1612 | S | 2 | Max McDonald
General AFSL Lab | 1143 – Perforce Visual Client (copy) | accepted | 3 | 1611 | S | 2 | Truc Hoa
General AFSL Lab | 1144 – Perforce Visual Client (copy) | accepted | 3 | 1611 | S | 2 | Tommy Zhou
General AFSL Lab | 1145 – Perforce Visual Client (copy) | accepted | 3 | 1611 | S | 2 | Riley Turk
General AFSL Lab | 1146 – Perforce Visual Client (copy) | accepted | 3 | 1611 | S | 2 | James Kurniawan
General AFSL Lab | 1147 – Perforce Visual Client (copy) | accepted | 3 | 1611 | S | 2 | Jason Borgida
General AFSL Lab | 1148 – Perforce Visual Client (copy) | accepted | 3 | 1703 | S | 2 | Helen Kuni
Mapping | 1149 – Creating an Angled Platform for Object Detection | accepted | 3 | 1611 | M | 3 | Chris Nee
Collision Awareness | 115 – Developer WebEx Account Setup (Group 2) | accepted | 3 | 1312 | XS | 1 | Bao Le | no
Mapping | 1150 – Volumetric Analysis | accepted | 3 | 1710 | L | 5 | Carter Kraus
JCATI 2016 | 1151 – Investigation of Mission Planner's Swarm Capabilities | accepted | 3 | 1702 | L | 5 | Zach Caratao
Flight Operations | 1152 – Write SAM Aircraft Flight Manual | accepted | 3 | 1703 | M | 3 | Truc Hoa |  | 100%
Flight Operations | 1153 – Airworthiness for SAM | accepted | 3 | 1612 | L | 5 | Selina Lui |  | 50%
JCATI 2015 | 1154 - AIAA Conference Paper Draft Writing (copy) | accepted | 3 | 1610 | XL | 8 | Robert Larson
JCATI 2015 | 1155 - AIAA Conference Paper Draft Writing (copy) | accepted | 3 | 1610 | XL | 8 | Robert Larson
Flight Operations | 1156 - ARGO Gimbal Construction | accepted | 3 | 1701 | M | 3 | Max McDonald
Mapping | 1157 - Investigate LIDAR Feasibility | accepted | 3 | 1701 | S | 2 | Karine Chen |  | 100%
Flight Operations | 1158 - ARGO Interchangeable Payload Mounts | accepted | 3 | 1703 | M | 3 | Selina Lui
Flight Operations | 1159 - Additional Multi-rotor research | accepted | 3 | 1610 | S | 2 | Yifu Wang
Collision Awareness | 116 – Developer WebEx Account Setup (Group 3) | accepted | 3 | 1312 | XS | 1 | Brian Chang | no
Flight Operations | 1160 – Props for Flight Tests | dropped | #N/A | 1701 | M | 3 | -
Flight Operations | 1161 – Vulcan Test Matrix | dropped | #N/A | 1611 | M | 3 | Hannah Rotta
Flight Operations | 1162 – Airworthiness for SAM (copy) | accepted | 3 | 1612 | L | 5 | Hannah Rotta |  | 100%
Flight Operations | 1163 – Flight Ops Administration (11/2016) | accepted | 3 | 1611 | M | 3 | Hannah Rotta
General AFSL Lab | 1164 – Arduino with Matlab and Simulink (Position 3) | accepted | 3 | 1702 | XL | 8 | Eze Klarnet |  | 30% | Performing intial set-up and testing; stuck at a debugging stage prior to deploying to the Due
General AFSL Lab | 1165 – Arduino with Matlab and Simulink (Update Documentation) (Position 3) | accepted | 3 | 1702 | XL | 8 | Eze Klarnet |  | 10%
Flight Operations | 1166 - Luke Post-Mortem Analysis | accepted | 3 | 1611 | M | 3 | Ryan Grimes
Visual Anchoring | 1167 - Arduplane SITL Validation | accepted | 3 | 1610 | M | 3 | Ryan Grimes |  | 50% | please tweak the documentation
Flight Operations | 1168 – CONDOR Post-Mortem Analysis | accepted | 3 | 1705 | M | 3 | Ryan Grimes
Visual Anchoring | 1169 - Understand Image Processing Matlab Code | accepted | 3 | 1702 | M | 3 | Ryan Grimes |  | 100%
Collision Awareness | 117 – Developer WebEx Account Setup (Group 4) | accepted | 3 | 1312 | XS | 1 | Christopher Lum | no
General AFSL Lab | 1170 - FPV Camera Research for Skywalker X8 | accepted | 3 | 1610 | M | 3 | James Kurniawan |  | 90%
General AFSL Lab | 1171 – New AFSL Printer (copy) | accepted | 3 | 1610 | S | 2 | Aaron Goldfogel
JCATI 2015 | 1172 - AIAA Conference Paper Draft Writing (copy) | accepted | 3 | 1610 | XL | 8 | Selina Lui
JCATI 2015 | 1173 - AIAA Conference Paper Draft Writing (copy) | accepted | 3 | 1610 | XL | 8 | Zach Caratao
JCATI 2015 | 1174 - AIAA Conference Paper Draft Writing (copy) | accepted | 3 | 1610 | XL | 8 | Zhenzhen Su
JCATI 2015 | 1175 - AIAA SciTech Conference Paper Draft Writing | accepted | 3 | 1612 | XL | 8 | Robert Larson
Flight Operations | 1176 - Flight Training Program – Fixed Wing(copy) | accepted | 3 | 1611 | XL | 8 | Zach Caratao
Visual Anchoring | 1177 – Image Processing 1: slant range algorithm | dropped | #N/A | 1703 | XL | 8 | Simeng Zhu
Visual Anchoring | 1178 – Image Processing 2: fit slant range algorithm to tracking algorithm | accepted | 3 | 1703 | XS | 1 | Simeng Zhu
Visual Anchoring | 1179 – Image Processing 3: automate the algorithm | accepted | 3 | 1703 | M | 3 | Simeng Zhu
Collision Awareness | 118 – Developer WebEx Account Setup (Group 5) | accepted | 3 | 1312 | XS | 1 | Dai Tsukada | no
Visual Anchoring | 1180 – Image Processing 4: field test & finalize | accepted | 3 | 1703 | M | 3 | Simeng Zhu
Flight Operations | 1181 - Flight Training Program – Fixed Wing (copy) | dropped | #N/A | 1902 | L | 5 | -
Flight Operations | 1182 - Maintenance of Training Planes (Position 1) | accepted | 3 | 1611 | XS | 1 | Hannah Rotta
Flight Operations | 1183 - Maintenance of Training Planes (Position 2) | accepted | 3 | 1611 | S | 2 | Selina Lui
Flight Operations | 1184 - Turnigy Talon Tricopter (T3) Build (part 1) | accepted | 3 | 1701 | S | 2 | Yifu Wang |  | 30%
Flight Operations | 1185 - Request a Waiver for sUAS – Increase in Altitude (copy) | accepted | 3 | 1612 | M | 3 | Karine Chen |  | 100%
Flight Operations | 1186 – HiLPixhawk Maintenance | accepted | 3 | 1611 | S | 2 | Selina Lui
Visual Anchoring | 1187 - Visual Anchoring White Paper | accepted | 3 | 1612 | M | 3 | Ryan Grimes |  | 40%
Visual Anchoring | 1188 – Understand Original Image Processing Algorithm | accepted | 3 | 1612 | M | 3 | Simeng Zhu
Visual Anchoring | 1189 - Integrate Tracking and Image Processing Algorithms | accepted | 3 | 1703 | XL | 8 | Ryan Grimes
Collision Awareness | 119 – Developer WebEx Account Setup (Group 6) | accepted | 3 | 1312 | XS | 1 | Daniel Ablog | no
Visual Anchoring | 1190 - Custom Arduplane build with UW modes | accepted | 3 | 1705 | XL | 8 | Ryan Grimes
Visual Anchoring | 1191 - Prepare Rebuilt CONDOR for ground testing | accepted | 3 | 1702 | L | 5 | Ryan Grimes |  | 90%
Flight Operations | 1192 – Mission Planner Familiarization (copy) | dropped | #N/A | 1902 | L | 5
Flight Operations | 1193 – ARGO “Training Wheels” | accepted | 3 | 1612 | S | 2 | Zachary Williams
Flight Operations | 1194 – Soldering | accepted | 3 | 1611 | S | 2 | Tommy Zhou |  | 20%
General AFSL Lab | 1195 – LinkedIn Page Setup and Facebook Link | accepted | 3 | 1706 | S | 2 | Aaron Su
GROVER | 1196 – GROVER Research - Mission Planner and Python Scripts | dropped | #N/A | 1801 | L | 5 | -
JCATI 2015 | 1197 - Master's Thesis Rough Draft (Larson) | accepted | 3 | 1701 | XL | 8 | Robert Larson
JCATI 2015 | 1198 - Master's Thesis Revisions (Larson) | accepted | 3 | 1703 | XL | 8 | Robert Larson
JCATI 2015 | 1199 - Master's Thesis Presentation (Larson) | accepted | 3 | 1702 | XL | 8 | Robert Larson
Collision Awareness | 120 – Developer WebEx Account Setup (Group 7) | accepted | 3 | 1312 | XS | 1 | Federico Alvarez | no
JCATI 2015 | 1200 - Master's Thesis Polishing (Larson) | accepted | 3 | 1703 | XL | 8 | Robert Larson
Flight Operations | 1201 - Flight Training Program – Fixed Wing (copy) | accepted | 3 | 1611 | XL | 8 | Hannah Rotta
Flight Operations | 1202 – Flight Instruction | accepted | 3 | 1611 | M | 3 | Robert Larson
Flight Operations | 1203 – MFOC Maintenance (part 2) | dropped | #N/A | 1902 | M | 3 | -
Flight Operations | 1204 – Student Technology Fee Proposal (copy) – LIDAR | accepted | 3 | 1701 | L | 5 | Karine Chen |  | 100%
General AFSL Lab | 1205 – Perforce Visual Client (copy) | accepted | 3 | 1612 | S | 2 | Taehan Kook
Flight Operations | 1206 – Flight Ops Administration (12/2016) | accepted | 3 | 1612 | M | 3 | Hannah Rotta |  | 100%
General AFSL Lab | 1207 – AFSL Website Updates (People Section) (copy) | accepted | 3 | 1612 | M | 3 | Karine Chen |  | 100%
General AFSL Lab | 1208 – AFSL Website Updates (People Section) (copy) | accepted | 3 | 1802 | XS | 1 | Karine Chen |  | 100%
General AFSL Lab | 1209 – AFSL Website Updates (Research Section) (copy) | accepted | 3 | 1802 | M | 3 | Karine Chen |  | 100%
Collision Awareness | 121 – Developer WebEx Account Setup (Group 8) | accepted | 3 | 1312 | XS | 1 | Keisuke Tsujita | no
General AFSL Lab | 1210 – AFSL Website Updates (Publications Section) (copy) | accepted | 3 | 1802 | M | 3 | Karine Chen |  | 100% | 2012+
Flight Operations | 1211 – Investigate Pixhawk 2 | accepted | 3 | 1701 | S | 2 | Riley Turk |  | 75% | talk with CONDOR team
General AFSL Lab | 1212 – Flight Test Videos Excel Data | accepted | 3 | 1710 | S | 2 | Karine Chen |  | 100%
General AFSL Lab | 1213 – AFSL Website (Research) – JCATI 2015 | accepted | 3 | 1707 | XS | 1 | Karine Chen |  | 100%
General AFSL Lab | 1214 – Social Media Updates (copy) – AUT ‘16 | accepted | 3 | 1612 | S | 2 | Karine Chen |  | 100%
General AFSL Lab | 1215 – Social Media Updates (copy) – WIN '17 | accepted | 3 | 1703 | S | 2 | Karine Chen |  | 100%
Flight Operations | 1216 – Falco Aircraft Manual (part 2) | dropped | #N/A | 1902 | M | 3 | -
Flight Operations | 1217 – White Paper | accepted | 3 | 1612 | S | 2 | Nathan Isaman
General AFSL Lab | 1218 - Perforce Visual Client (copy) | accepted | 3 | 1612 | S | 2 | BJ Arun
General AFSL Lab | 1219 - Perforce Visual Client (copy) | accepted | 3 | 1612 | S | 2 | Kelsey Gabel
Collision Awareness | 122 – Developer WebEx Account Setup (Group 9) | accepted | 3 | 1312 | XS | 1 | Kevin Ueunten | no
General AFSL Lab | 1220 - Perforce Visual Client (copy) | accepted | 3 | 1612 | S | 2 | Brett Myers
Flight Operations | 1221 – SAM Post-Mortem Analysis | accepted | 3 | 1704 | M | 3 | Tommy Zhou
Flight Operations | 1222 – MFOC Maintenance Post 12/16 flight tests | accepted | 3 | 1704 | S | 2 | Ge Bao
Flight Operations | 1223 – Troubleshoot CERES | accepted | 3 | 1703 | S | 2 | Scott An
Flight Operations | 1223 – Troubleshoot CERES (part 1) | accepted | 3 | 1703 | M | 3 | Aaron Goldfogel
Flight Operations | 1224 – Troubleshoot TEDD | dropped | #N/A | 1703 | S | 2 | - |  |  | battery issue
Flight Operations | 1225 – Falco Rebuild | accepted | 3 | 1702 | S | 2 | Jason Borgida
Flight Operations | 1226 – SAM Rebuild | accepted | 3 | 1704 | L | 5 | Karine Chen |  | 100%
Mapping | 1227 – MicaSense RedEdge Documentation | accepted | 3 | 1701 | S | 2 | Scott An
JCATI 2015 | 1228 - AIAA SciTech Conference Paper Draft Writing (copy) | accepted | 3 | 1701 | XL | 8 | Robert Larson
JCATI 2015 | 1229 - AIAA SciTech Conference Paper Draft Writing (copy) | accepted | 3 | 1703 | XL | 8 | Robert Larson
Collision Awareness | 123 – Developer WebEx Account Setup (Group 10) | accepted | 3 | 1312 | XS | 1 | Matthew Davis | no |  | 90%
MAPSS | 1230 - MAPSS Initial Gimbal System Trade Study | accepted | 3 | 1701 | M | 3 | Zach Caratao
MAPSS | 1231 - MAPSS Project Plan Deliverables | accepted | 3 | 1701 | L | 5 | Zach Caratao
MAPSS | 1232 - MAPSS Project Plan Deliverables (copy) | accepted | 3 | 1701 | L | 5 | BJ Arun
MAPSS | 1233 - MAPSS Project Plan Deliverables (copy) | accepted | 3 | 1701 | L | 5 | Kelsey Gabel
MAPSS | 1234 - MAPSS Project Plan Delivarables (copy) | accepted | 3 | 1701 | L | 5 | Brett Myers
MAPSS | 1235 - MAPSS Equipment Acquisition Sprint 1702 | accepted | 3 | 1704 | S | 2 | BJ Arun
MAPSS | 1236 - MAPSS Initial Red Edge Data Acquisition | accepted | 3 | 1704 | S | 2 | BJ Arun
MAPSS | 1237 - MAPSS Accessory Sensor Specs and CAD work | accepted | 3 | 1703 | S | 2 | Kelsey Gabel |  |  | Mount location
MAPSS | 1238 - MAPSS Accessory Sensor Dummy Model | accepted | 3 | 1701 | L | 5 | Kelsey Gabel
MAPSS | 1239 - MAPSS Matrice 100 Integration | accepted | 3 | 1705 | XS | 1 | Brett Myers
Collision Awareness | 124 – Developer WebEx Account Setup (Group 11) | accepted | 3 | 1312 | XS | 1 | Madison Peck | no
MAPSS | 1240 - MAPSS Sprint 1701 Administation | accepted | 3 | 1701 | L | 5 | BJ Arun
MAPSS | 1240 - MAPSS Sprint 1702 Administation | accepted | 3 | 1702 | L | 5 | BJ Arun
MAPSS | 1241 - MAPSS Sprint 1701 Budgeting | accepted | 3 | 1702 | M | 3 | Zach Caratao
MAPSS | 1241 - MAPSS Sprint 1702 Budgeting | accepted | 3 | 1702 | XS | 1 | Zach Caratao
MAPSS | 1242 - MAPSS Pixhawk/MissionPlanner Integration | dropped | #N/A | 1702 | M | 3 | Zach Caratao
MAPSS | 1243 - MAPSS Axis Camera Gimbal Trade Study | accepted | 3 | 1701 | S | 2 | Kelsey Gabel
MAPSS | 1244 - MAPSS Axis Camera Gimbal Trade Study (copy) | accepted | 3 | 1701 | S | 2 | Zach Caratao
General AFSL Lab | 1245 – AFSL Website Updates (People Section) (copy) | accepted | 3 | 1707 | XS | 1 | Karine Chen |  | 100%
Flight Operations | 1246 – MARV JCATI Flight Test | accepted | 3 | 1701 | M | 3 | Connor Kafka |  | 100%
Flight Operations | 1247 – Plan a Snow Excursion | dropped | #N/A | 1808 | M | 3 | Hannah Rotta
General AFSL Lab | 1248 – SciTech Paper | accepted | 3 | 1701 | M | 3 | Selina Lui
General AFSL Lab | 1249 – Amazon Catalyst Proposal | dropped | #N/A | 1711 | M | 3 | -
Collision Awareness | 125 – Developer WebEx Account Setup (Group 12) | accepted | 3 | 1312 | XS | 1 | Noel Kimber | no
General AFSL Lab | 1250 – JCATI Proposal | accepted | 3 | 1703 | XL | 8 | Hannah Rotta
Flight Operations | 1251 – Flight Ops Administration (1701) | accepted | 3 | 1701 | M | 3 | Hannah Rotta
Flight Operations | 1252 – Cera Build (copy) | accepted | 3 | 1705 | S | 2 | Max McDonald
General AFSL Lab | 1253 – Perforce Visual Client (copy) | accepted | 3 | 1701 | S | 2 | Maius Wong
Flight Operations | 1254 – Purchase New Skywalker 1900 | dropped | #N/A | 1705 | XS | 1 | Tommy Zhou
General AFSL Lab | 1255 – Perforce Visual Client (copy) | accepted | 3 | 1703 | S | 2 | Sicong Huang
General AFSL Lab | 1256 – Perforce Visual Client (copy) | accepted | 3 | 1703 | S | 2 | Ge Bao
General AFSL Lab | 1257 – Create a TRAPIS Promo Video (copy) | accepted | 3 | 1707 | M | 3 | Ge Bao
General AFSL Lab | 1258 – Weather Station & Equipment Functionality | accepted | 3 | 1701 | S | 2 | Maius Wong
Flight Operations | 1259 – MFOC Maintenance Post 12/16 flight tests (copy) | accepted | 3 | 1704 | S | 2 | Sicong Huang
Collision Awareness | 126 – Developer WebEx Account Setup (Group 13) | accepted | 3 | 1312 | XS | 1 | Henry Qin | no |  | 90%
Flight Operations | 1260 – Falco Rebuild (copy) | accepted | 3 | 1702 | M | 3 | Riley Turk |  | 80%
General AFSL Lab | 1261 – Camera Cases | accepted | 3 | 1701 | XS | 1 | Aaron Goldfogel
General AFSL Lab | 1262 – Undergrad Research Symposium | accepted | 3 | 1705 | XS | 1 | Zachary Williams
Flight Operations | 1263 – Flight Training Program – Multi-Rotor | accepted | 3 | 1705 | L | 5 | Connor Kafka |  | 80% | waiting for outdoor test w/ marv
MAPSS | 1264 – MAPSS Analyze Previous Flight Data | accepted | 3 | 1701 | XS | 1 | Brett Myers
General AFSL Lab | 1265 – Research Parameter Loading Order in Checklists | accepted | 3 | 1701 | S | 2 | Selina Lui
MAPSS | 1266 – MAPSS Passive Damping Designs Research | accepted | 3 | 1702 | S | 2 | Brett Myers
MAPSS | 1267 – MAPSS Sprint 1701 Communication Focal Duties | accepted | 3 | 1701 | S | 2 | Kelsey Gabel
MAPSS | 1267 – MAPSS Sprint 1702 Communication Focal Duties | accepted | 3 | 1702 | S | 2 | Kelsey Gabel
MAPSS | 1268 – MAPSS Senior Capstone Grant Application | accepted | 3 | 1701 | S | 2 | Zach Caratao |  | 85%
JCATI 2016 | 1269 - Argo Repairs | accepted | 3 | 1701 | S | 2 | Zachary Williams |  | 100%
Collision Awareness | 127 – Developer WebEx Account Setup (Group 14) | accepted | 3 | 1312 | XS | 1 | Seunghyun Ko | no
JCATI 2016 | 1270 - Argo Test Flights | accepted | 3 | 1701 | L | 5 | Zachary Williams |  | 100%
Flight Operations | 1271 – Piksi Ground Test | accepted | 3 | 1701 | S | 2 | Connor Kafka |  | 100%
JCATI 2016 | 1272 – Piksi 3D Printed Mount | accepted | 3 | 1702 | L | 5 | Connor Kafka |  | 75%
Flight Operations | 1273 – Archival and Data Analysis for Mission 1/21/17 | accepted | 3 | 1701 | S | 2 | Selina Lui
MAPSS | 1273 – MAPSS MicaSense Rededge CAD Work | accepted | 3 | 1702 | M | 3 | Kelsey Gabel
MAPSS | 1273 – MAPSS MicaSense Rededge CAD Work | accepted | 3 | 1702 | M | 3 | BJ Arun
MAPSS | 1273 – MAPSS MicaSense Rededge CAD Work | accepted | 3 | 1703 | M | 3 | Kelsey Gabel
MAPSS | 1273 – MAPSS MicaSense Rededge CAD Work | accepted | 3 | 1702 | M | 3 | Brett Myers
JCATI 2016 | 1275 - MARV JCATI Flight Test (copy) | accepted | 3 | 1701 | M | 3 | Zachary Williams |  | 100%
MAPSS | 1276 – MAPSS Flight Test Analysis | accepted | 3 | 1704 | XS | 1 | Kelsey Gabel
General AFSL Lab | 1276 – Perforce Visual Client (copy) | accepted | 3 | 1703 | S | 2 | Sam Buxton
MAPSS | 1277 – MAPSS Flight Test Analysis (copy) | accepted | 3 | 1704 | XS | 1 | BJ Arun
MAPSS | 1278 – MAPSS Flight Test Analysis (copy) | accepted | 3 | 1704 | M | 3 | Zach Caratao
MAPSS | 1279 – MAPSS Flight Test Analysis (copy) | accepted | 3 | 1704 | XS | 1 | Brett Myers
Collision Awareness | 128 – Developer WebEx Account Setup (Group 15) | accepted | 3 | 1312 | XS | 1 | Richard Fukutome | no
MAPSS | 1280 – MAPSS Flight Test RedEdge Data Acquisition | accepted | 3 | 1704 | XS | 1 | Kelsey Gabel
MAPSS | 1281 – MAPSS Flight Test RedEdge Data Acquisition (copy) | accepted | 3 | 1704 | XS | 1 | BJ Arun
MAPSS | 1282 – MAPSS Flight Test RedEdge Data Acquisition (copy) | accepted | 3 | 1704 | M | 3 | Zach Caratao
MAPSS | 1283 – MAPSS Flight Test RedEdge Data Acquisition (copy) | accepted | 3 | 1704 | XS | 1 | Brett Myers
Flight Operations | 1284 – Flight Training Program – Fixed Wing (copy) | accepted | 3 | 1712 | L | 5 | Karine Chen |  | 90% | completed up through flying mini skywalker, but graduating
General AFSL Lab | 1285 – Electronics Development Workstation | accepted | 3 | 1703 | M | 3 | Maius Wong
Flight Operations | 1286 – Flight Incidents Documentation | accepted | 3 | 1706 | M | 3 | Hannah Rotta
Flight Operations | 1287 – Anakin Post-Mortem Analysis | dropped | #N/A | 1703 | M | 3 | Riley Turk
Flight Operations | 1288 – Anakin Rebuild | accepted | 3 | 1703 | L | 5 | Selina Lui
Flight Operations | 1289 – SAM Rebuild (copy) | accepted | 3 | 1704 | XS | 1 | Nikita Filippov |  | 100%
Collision Awareness | 129 – Visual Studio 2012 Unit Test Workflow | accepted | 3 | 1312 | M | 3 | Christopher Lum | yes
Flight Operations | 1290 – Anakin Rebuild (copy) | dropped | #N/A | 1703 | M | 3 | -
MAPSS | 1291 – MAPSS Poster Session 2/3 | accepted | 3 | 1702 | M | 3 | Kelsey Gabel
MAPSS | 1292 – MAPSS Poster Session 2/3 (copy) | accepted | 3 | 1702 | M | 3 | BJ Arun
MAPSS | 1293 – MAPSS Poster Session 2/3 (copy) | accepted | 3 | 1702 | M | 3 | Zach Caratao
MAPSS | 1294 – MAPSS Poster Session 2/3 (copy) | accepted | 3 | 1702 | M | 3 | Brett Myers
MAPSS | 1295 – MAPSS Gimbal Software Integration | accepted | 3 | 1703 | XS | 1 | Brett Myers
MAPSS | 1296 – MAPSS Gimbal Software Integration (copy) | dropped | #N/A | 1703 | L | 5 | Zach Caratao
MAPSS | 1297 – MAPSS Gimbal Software Integration (copy) | accepted | 3 | 1702 | S | 2 | Kelsey Gabel
MAPSS | 1298 – MAPSS Gimbal Software Integration (copy) | dropped | #N/A | 1703 | XS | 1 | BJ Arun
Flight Operations | 1299 – Student Technology Fee Proposal (copy) – LIDAR | accepted | 3 | 1701 | M | 3 | Zachary Williams |  | 100%
Collision Awareness | 130 – Sprint 1312 Administration | accepted | 3 | 1312 | M | 3 | Christopher Lum | no
Visual Anchoring | 1300 - Apprehend the usage of Image Acquisition Toolbox | accepted | 3 | 1702 | M | 3 | Simeng Zhu
Visual Anchoring | 1301 – Unit test for integrated visual anchoring algorithm | dropped | #N/A | 1703 | L | 5 | Simeng Zhu
Visual Anchoring | 1302 – Clean up unused visual anchoring code | accepted | 3 | 1702 | S | 2 | Simeng Zhu
Visual Anchoring | 1303 – Recruit more people for visual anchoring project | accepted | 3 | 1703 | XS | 1 | Simeng Zhu
Visual Anchoring | 1304 – Ground test 1 for visual anchoring | accepted | 3 | 1702 | XL | 8 | Simeng Zhu
Visual Anchoring | 1305 - Develop and Document Slant Range Algorithm | accepted | 3 | 1701 | M | 3 | Ryan Grimes |  | 100%
Visual Anchoring | 1306 - Configure and Install Camera Gimbal and Video Transmitter | accepted | 3 | 1703 | L | 5 | Ryan Grimes
Visual Anchoring | 1307 - Unit Test Slant Range Algorithm | accepted | 3 | 1705 | L | 5 | Ryan Grimes |  | 50%
Visual Anchoring | 1308 - Clean up unused visual anchoring code (copy) | accepted | 3 | 1702 | S | 2 | Ryan Grimes
Flight Operations | 1309 - Investigating RC Inputs and Outputs | accepted | 3 | 1705 | XS | 1 | Riley Turk
Collision Awareness | 131 – Forward State Estimator Improvements | accepted | 3 | 1402 | M | 3 | Kevin Ueunten |  |  | 100%
Flight Operations | 1310 – Student Technology Fee Proposal (copy) – LIDAR | accepted | 3 | 1701 | XS | 1 | Hannah Rotta |  | 100%
Flight Operations | 1311 – Optimizing Various Mission Planner Parameters | dropped | #N/A | 1902 | M | 3 | -
Flight Operations | 1312 – Flight Training Program – Multi-Rotor (copy) | dropped | #N/A | 1706 | L | 5 | Zach Caratao
Flight Operations | 1313 – Aircraft Part Familiarization (copy) | accepted | 3 | 1702 | S | 2 | Truc Hoa |  | 100%
Flight Operations | 1313 – Aircraft Part Familiarization (copy) | accepted | 3 | 1703 | S | 2 | Shumin Lin |  | 100%
Flight Operations | 1314 - Part 107 Test Preparation (copy) | accepted | 3 | 1702 | XS | 1 | Riley Turk |  | 100%
Flight Operations | 1315 - Anakin Crash Analysis | accepted | 3 | 1704 | M | 3 | Riley Turk
Flight Operations | 1316 – Swarm Waiver | dropped | #N/A | 1703 | L | 5 | -
MAPSS | 1317 - MAPSS PDR Session (3/10) | accepted | 3 | 1703 | M | 3 | BJ Arun
MAPSS | 1318 - MAPSS PDR Session (3/10) (copy) | accepted | 3 | 1703 | M | 3 | Zach Caratao
MAPSS | 1319 - MAPSS PDR Session (3/10) (copy) | accepted | 3 | 1703 | M | 3 | Kelsey Gabel
Collision Awareness | 132 – Unit Testing Background Training (copy) | accepted | 3 | 1401 | M | 3 | Al Creigh
MAPSS | 1320 - MAPSS PDR Session (3/10) (copy) | accepted | 3 | 1703 | M | 3 | Brett Myers
MAPSS | 1321 - MAPSS CDR Session (4/28) | accepted | 3 | 1704 | S | 2 | BJ Arun
MAPSS | 1322 - MAPSS CDR Session (4/28) (copy) | accepted | 3 | 1704 | M | 3 | Zach Caratao
MAPSS | 1323 - MAPSS CDR Session (4/28) (copy) | accepted | 3 | 1704 | M | 3 | Kelsey Gabel
MAPSS | 1324 - MAPSS CDR Session (4/28) (copy) | accepted | 3 | 1704 | S | 2 | Brett Myers
MAPSS | 1325 - MAPSS FDR Session (6/5) | accepted | 3 | 1706 | M | 3 | BJ Arun
MAPSS | 1326 - MAPSS FDR Session (6/5) (copy) | accepted | 3 | 1706 | M | 3 | Zach Caratao
MAPSS | 1327 - MAPSS FDR Session (6/5) (copy) | accepted | 3 | 1706 | M | 3 | Kelsey Gabel
MAPSS | 1328 - MAPSS FDR Session (6/5) (copy) | accepted | 3 | 1706 | M | 3 | Brett Myers
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1702 | accepted | 3 | 1702 | M | 3 | BJ Arun
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1703 | accepted | 3 | 1703 | S | 2 | BJ Arun
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1703 | accepted | 3 | 1703 | S | 2 | Zach Caratao
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1703 | accepted | 3 | 1703 | S | 2 | Kelsey Gabel
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1703 | accepted | 3 | 1703 | S | 2 | Brett Myers
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1704 | accepted | 3 | 1704 | M | 3 | BJ Arun
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1704 | accepted | 3 | 1704 | M | 3 | Zach Caratao
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1704 | accepted | 3 | 1704 | M | 3 | Kelsey Gabel
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1704 | accepted | 3 | 1704 | M | 3 | Brett Myers
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1705 | accepted | 3 | 1705 | S | 2 | BJ Arun
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1705 | accepted | 3 | 1705 | S | 2 | Zach Caratao
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1705 | accepted | 3 | 1705 | S | 2 | Kelsey Gabel
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1705 | accepted | 3 | 1705 | S | 2 | Brett Myers
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1706 | dropped | #N/A | 1705 | S | 2 | BJ Arun
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1706 | dropped | #N/A | 1705 | S | 2 | Zach Caratao
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1706 | dropped | #N/A | 1705 | S | 2 | Kelsey Gabel
MAPSS | 1329 - MAPSS Meeting Attendance Sprint 1706 | dropped | #N/A | 1705 | S | 2 | Brett Myers
Collision Awareness | 133 – Unit Testing Background Training (copy) | accepted | 3 | 1312 | M | 3 | Bao Le | no
MAPSS | 1330 - MAPSS Meeting Attendance Sprint 1702 | accepted | 3 | 1702 | M | 3 | Zach Caratao
MAPSS | 1331 - MAPSS Meeting Attendance Sprint 1702 | accepted | 3 | 1702 | M | 3 | Kelsey Gabel
MAPSS | 1332 - MAPSS Meeting Attendance Sprint 1702 | accepted | 3 | 1702 | M | 3 | Brett Myers
MAPSS | 1333 - MAPSS Gimbal Flight Test- Prototype 1 | dropped | #N/A | 1705 | S | 2 | Brett Myers
MAPSS | 1334 - MAPSS Gimbal Flight Test- Prototype 1 (copy) | dropped | #N/A | 1705 | S | 2 | BJ Arun
MAPSS | 1335 - MAPSS Gimbal Flight Test- Prototype 1 (copy) | dropped | #N/A | 1705 | S | 2 | Zach Caratao
MAPSS | 1336 - MAPSS Gimbal Flight Test- Prototype 1 (copy) | dropped | #N/A | 1705 | S | 2 | Kelsey Gabel
MAPSS | 1337 - MAPSS Gimbal-less Rededge Flight Test | dropped | #N/A | 1704 | M | 3 | BJ Arun |  |  | Update needed
MAPSS | 1337 - MAPSS Gimbal-less Rededge Flight Test (copy) | dropped | #N/A | 1704 | M | 3 | Zach Caratao |  |  | Update needed
MAPSS | 1337 - MAPSS Gimbal-less Rededge Flight Test (copy) | dropped | #N/A | 1704 | M | 3 | Kelsey Gabel |  |  | Update needed
MAPSS | 1337 - MAPSS Gimbal-less Rededge Flight Test (copy) | dropped | #N/A | 1704 | M | 3 | Brett Myers |  |  | Update needed
MAPSS | 1338 - MAPSS Accessory Sensor Testing | accepted | 3 | 1704 | XS | 1 | BJ Arun
MAPSS | 1338 - MAPSS Accessory Sensor Testing (copy) | accepted | 3 | 1704 | M | 3 | Zach Caratao
MAPSS | 1338 - MAPSS Accessory Sensor Testing (copy) | accepted | 3 | 1704 | XS | 1 | Kelsey Gabel
MAPSS | 1338 - MAPSS Accessory Sensor Testing (copy) | accepted | 3 | 1704 | XS | 1 | Brett Myers
MAPSS | 1339 - MAPSS Vibrational Testing setup | accepted | 3 | 1703 | S | 2 | Brett Myers
Collision Awareness | 134 – Unit Testing Background Training (copy) | accepted | 3 | 1312 | M | 3 | Daniel Ablog |  |  | 0%
MAPSS | 1340 - MAPSS Final Paper (Part 2) (6/8) | accepted | 3 | 1706 | M | 3 | BJ Arun
MAPSS | 1341 - MAPSS Final Paper (Part 2) (6/8) (COPY) | accepted | 3 | 1706 | M | 3 | Zach Caratao
MAPSS | 1342 - MAPSS Final Paper (Part 2) (6/8) (COPY) | accepted | 3 | 1706 | M | 3 | Kelsey Gabel
MAPSS | 1343 - MAPSS Final Paper (Part 2) (6/8) (COPY) | accepted | 3 | 1706 | M | 3 | Brett Myers
MAPSS | 1344 - MAPSS Gimbal Flight Test | dropped | #N/A | 1704 | M | 3 | BJ Arun |  |  | Update needed
MAPSS | 1345 - MAPSS Gimbal Flight Test (copy) | dropped | #N/A | 1704 | M | 3 | Zach Caratao |  |  | Update needed
MAPSS | 1346 - MAPSS Gimbal Flight Test (copy) | dropped | #N/A | 1704 | M | 3 | Kelsey Gabel |  |  | Update needed
MAPSS | 1347 - MAPSS Gimbal Flight Test (copy) | dropped | #N/A | 1704 | M | 3 | Brett Myers |  |  | Update needed
MAPSS | 1348 - MAPSS Gimbal vs Non-Gimbal Flight Test Quality Comparison (MTF) | dropped | #N/A | 1704 | S | 2 | BJ Arun |  |  | Update needed
MAPSS | 1349 - MAPSS Gimbal vs Non-Gimbal Flight Test Quality Comparison (MTF) (copy) | dropped | #N/A | 1704 | S | 2 | Zach Caratao |  |  | Update needed
Collision Awareness | 135 – Unit Testing Background Training (copy) | accepted | 3 | 1401 | M | 3 | Federico Alvarez
MAPSS | 1350 - MAPSS Gimbal vs Non-Gimbal Flight Test Quality Comparison (MTF) (copy) | dropped | #N/A | 1704 | S | 2 | Kelsey Gabel |  |  | Update needed
MAPSS | 1351 - MAPSS Gimbal vs Non-Gimbal Flight Test Quality Comparison (MTF) (copy) | dropped | #N/A | 1704 | S | 2 | Brett Myers |  |  | Update needed
Flight Operations | 1352 – VTOL/QuadPlane | dropped | #N/A | 1906 | XL | 8 | -
General AFSL Lab | 1353 – Engineering Discovery Days Prep | accepted | 3 | 1704 | M | 3 | Hannah Rotta
General AFSL Lab | 1354 – Perforce Visual Client (copy) | accepted | 3 | 1702 | S | 2 | Nikita Filippov
MAPSS | 1355 – MAPSS Prototype 1 Documentation | accepted | 3 | 1702 | S | 2 | Zach Caratao
MAPSS | 1356 – MAPSS SONY A5100 Documentation | accepted | 3 | 1702 | M | 3 | Zach Caratao
MAPSS | 1357 – Modulation Transfer Function Research & Documentation | accepted | 3 | 1704 | M | 3 | Zach Caratao
MAPSS | 1358 – MAPSS Test Card Creation (Part 1) | accepted | 3 | 1702 | S | 2 | Zach Caratao
MAPSS | 1359 – MAPSS MTF Poster Creation (Part 1) | accepted | 3 | 1703 | XS | 1 | Kelsey Gabel
Collision Awareness | 136 – Unit Testing Background Training (copy) | accepted | 3 | 1312 | M | 3 | Kevin Ueunten | no |  | 10%
Flight Operations | 1360 – Luke Rebuild | accepted | 3 | 1706 | XS | 1 | Sicong Huang
General AFSL Lab | 1362 – Perforce Visual Client (copy) | accepted | 3 | 1705 | S | 2 | Nick Armstrong
General AFSL Lab | 1362 – Perforce Visual Client (copy) | accepted | 3 | 1705 | S | 2 | Nico Miguel
General AFSL Lab | 1363 – Perforce Visual Client (copy) | accepted | 3 | 1706 | S | 2 | Nicholas Price
General AFSL Lab | 1364 - Indoor Flight Testing Location | accepted | 3 | 1703 | S | 2 | Zach Caratao
Flight Operations | 1365 - Cera build | accepted | 3 | 1705 | L | 5 | Riley Turk
Flight Operations | 1365 - Cera build (copy) | accepted | 3 | 1706 | L | 5 | Jason Borgida |  | 90% | Needs Flight test Saturday
Collision Awareness | 137 – Unit Testing Background Training (copy) | accepted | 3 | 1312 | M | 3 | Matthew Davis | no
Visual Anchoring | 1370 - Gimbal Trade Study and Integration for Visual Anchoring | accepted | 3 | 1703 | XL | 8 | Michael Brady | yes
Visual Anchoring | 1371 - Adapter for new PC power supply for charging | accepted | 3 | 1702 | S | 2 | Michael Brady | yes |  | 100%
Visual Anchoring | 1372 - Pixhawk mounting for vibration dampening | accepted | 3 | 1703 | M | 3 | Michael Brady | yes
Flight Operations | 1373 – Flight Ops Administration (1702) | accepted | 3 | 1702 | L | 5 | Hannah Rotta
JCATI 2016 | 1374 - JCATI To-Do | accepted | 3 | 1702 | L | 5 | Connor Kafka |  | 100%
JCATI 2016 | 1375 – JCATI LLNL Ground Test | accepted | 3 | 1703 | M | 3 | Zachary Williams
JCATI 2016 | 1375 – JCATI LLNL Ground Test | accepted | 3 | 1703 | M | 3 | Connor Kafka
JCATI 2016 | 1376 – JCATI Poster | accepted | 3 | 1703 | S | 2 | Zachary Williams
JCATI 2016 | 1376 – JCATI Poster | accepted | 3 | 1703 | S | 2 | Connor Kafka
JCATI 2016 | 1377 – JCATI SDR Integration & Flight Test | accepted | 3 | 1704 | M | 3 | Zachary Williams
General AFSL Lab | 1378 – LiDAR Procurement | accepted | 3 | 1707 | XL | 8 | Karine Chen |  | 100%
General AFSL Lab | 1379 – Lab Component Inventory | accepted | 3 | 1703 | M | 3 | Zach Caratao |  | 33%
Collision Awareness | 138 – Unit Testing Background Training (copy) | accepted | 3 | 1312 | M | 3 | Noel Kimber | no
General AFSL Lab | 1380 – Clean Scissors | accepted | 3 | 1703 | XS | 1 | Kibaek Jeong
General AFSL Lab | 1381 – Reorganize Lab’s Airspace | accepted | 3 | 1704 | XS | 1 | Max McDonald
Flight Operations | 1382 – Repair GROVER | dropped | #N/A | 1706 | M | 3 | Nick Armstrong
Flight Operations | 1383 – New Swarm Research Ground Vehicle | dropped | #N/A | 1708 | L | 5 | -
Flight Operations | 1384 – Flight Training Program – Multi-Rotor | accepted | 3 | 1802 | L | 5 | Hannah Rotta
General AFSL Lab | 1385 – Plimp Proposal | accepted | 3 | 1702 | M | 3 | Hannah Rotta
JCATI 2015 | 1386 - Master's Thesis Presentation (Larson) (copy) | accepted | 3 | 1702 | XL | 8 | Robert Larson
JCATI 2016 | 1387 JCATI To-Do (Copy) | accepted | 3 | 1702 | L | 5 | Zachary Williams |  | 100%
General AFSL Lab | 1388 - Piksi RTK Flight Test (Copy) | dropped | #N/A | 1906 | M | 3 | -
Collision Awareness | 139 – Unit Testing Background Training (copy) | accepted | 3 | 1312 | M | 3 | Henry Qin | no |  | 35%
Flight Operations | 1390 – STF Proposal Part 2 | accepted | 3 | 1702 | M | 3 | Karine Chen |  | 100%
General AFSL Lab | 1391 – Perforce Visual Client (copy) | accepted | 3 | 1703 | S | 2 | Alex Banh
Flight Operations | 1392 – Flight Training Program – Multi-Rotor (copy) | dropped | #N/A | 1903 | L | 5 | Nicholas Price
Flight Operations | 1393 – Flight Training Program – Fixed Wing (copy) | dropped | #N/A | 1903 | L | 5 | Nicholas Price
Flight Operations | 1394 – Flight Training Program – Fixed Wing (copy) | accepted | 3 | 1805 | L | 5 | Cory Cantey
Flight Operations | 1395 – Flight Training Program – Multi-Rotor (copy) | accepted | 3 | 1802 | XL | 8 | Dylan Hoff
Flight Operations | 1396 – Flight Training Program – Multi-Rotor (copy) | dropped | #N/A | 1902 | L | 5 | Chung Choi
Flight Operations | 1397 – Flight Training Program – Multi-Rotor (copy) | dropped | #N/A | 1903 | L | 5 | Christopher Lum
Flight Operations | 1398 – VTOL/QuadPlane (copy) | accepted | 3 | 1707 | XL | 8 | Kai Simpson
Flight Operations | 1399 – VTOL/QuadPlane (copy) | accepted | 3 | 1708 | XL | 8 | Cole Morgan
Collision Awareness | 140 – Unit Testing Background Training (copy) | accepted | 3 | 1312 | M | 3 | Keisuke Tsujita | no |  | 25%
Flight Operations | 1400 – VTOL/QuadPlane (copy) | accepted | 3 | 1708 | XL | 8 | Zach Kirwan
General AFSL Lab | 1401 – Create an AFSL Promo Video for the Website | accepted | 3 | 1707 | M | 3 | Ge Bao |  | 85%
General AFSL Lab | 1402 – Create an AFSL Promo Video for the Website (copy) | accepted | 3 | 1706 | S | 2 | Sicong Huang
General AFSL Lab | 1403 – Create an AFSL Promo Video for the Website (copy) | accepted | 3 | 1707 | XS | 1 | Karine Chen |  | 100%
Flight Operations | 1404 – Student Technology Fee Proposal (copy) – LIDAR | accepted | 3 | 1703 | M | 3 | Connor Kafka
Flight Operations | 1405 – Aircraft Part Familiarization (copy) | accepted | 3 | 1712 | S | 2 | Karine Chen |  | 100%
General AFSL Lab | 1406 - Sprint 1701 Administration | accepted | 3 | 1701 | XL | 8 | Christopher Lum
General AFSL Lab | 1407 - Sprint 1702 Administration | accepted | 3 | 1702 | XL | 8 | Christopher Lum
General AFSL Lab | 1408 - Sprint 1703 Administration | accepted | 3 | 1703 | XL | 8 | Christopher Lum
General AFSL Lab | 1409 - Sprint 1704 Administration | accepted | 3 | 1704 | XL | 8 | Christopher Lum
Collision Awareness | 141 – Unit Testing Background Training (copy) | accepted | 3 | 1401 | M | 3 | Seunghyun Ko |  |  | 100%
General AFSL Lab | 1410 - Sprint 1705 Administration | accepted | 3 | 1705 | XL | 8 | Christopher Lum
General AFSL Lab | 1411 - Sprint 1706 Administration | accepted | 3 | 1706 | XL | 8 | Christopher Lum
General AFSL Lab | 1412 - Sprint 1707 Administration | accepted | 3 | 1707 | XL | 8 | Christopher Lum
General AFSL Lab | 1413 - Sprint 1708 Administration | accepted | 3 | 1708 | XL | 8 | Christopher Lum
General AFSL Lab | 1414 - Sprint 1709 Administration | accepted | 3 | 1709 | XL | 8 | Christopher Lum
General AFSL Lab | 1415 - Sprint 1710 Administration | accepted | 3 | 1710 | XL | 8 | Christopher Lum
General AFSL Lab | 1416 - Sprint 1711 Administration | accepted | 3 | 1711 | XL | 8 | Christopher Lum
General AFSL Lab | 1417 - Sprint 1712 Administration | accepted | 3 | 1802 | XL | 8 | Christopher Lum
Flight Operations | 1418 – BVLOS Waiver | dropped | #N/A | 1703 | L | 5 | -
Flight Operations | 1419 – Aircraft Lights for Altitude Waiver | dropped | #N/A | 1705 | L | 5 | Nikita Filippov
Collision Awareness | 142 – Unit Testing Background Training (copy) | accepted | 3 | 1402 | M | 3 | Dai Tsukada |  |  | 80%
General AFSL Lab | 1420 - Perforce Visual Client (copy) | accepted | 3 | 1703 | S | 2 | Conor Reiland
Visual Anchoring | 1421 - Research Mission Planner | dropped | #N/A | 1703 | M | 3 | Conor Reiland
Flight Operations | 1422 – Flight Training Program – Multi-Rotor (part 1) | accepted | 3 | 1703 | M | 3 | Zach Caratao
Flight Operations | 1423 - RF Spectrum Analyzer Manual | accepted | 3 | 1703 | XS | 1 | Maius Wong
General AFSL Lab | 1424 - Perforce Visual Client (copy) | accepted | 3 | 1704 | S | 2 | Kai Simpson
General AFSL Lab | 1425 - Perforce Visual Client (copy) | accepted | 3 | 1704 | S | 2 | Cole Morgan
General AFSL Lab | 1426 - Perforce Visual Client (copy) | accepted | 3 | 1704 | S | 2 | Zach Kirwan
Flight Operations | 1427 – Auto Takeoff | accepted | 3 | 1705 | S | 2 | Tadej Kosel
Flight Operations | 1428 – Auto Landing | accepted | 3 | 1706 | M | 3 | Tadej Kosel
Flight Operations | 1429 – DJI Phantom 3 Usage Study | dropped | #N/A | 1704 | M | 3 | Maius Wong
Collision Awareness | 143 – Unit Testing Background Training (copy) | accepted | 3 | 1312 | M | 3 | Richard Fukutome | no
Flight Operations | 1430 – GCS Software Upgrades | accepted | 3 | 1708 | M | 3 | Helen Kuni
Flight Operations | 1431 – New Swarm Research Ground Vehicle (copy) | accepted | 3 | 1710 | XS | 1 | Nicholas Price
Flight Operations | 1432 – New Swarm Research Ground Vehicle (copy) | accepted | 3 | 1707 | M | 3 | Nick Armstrong
Flight Operations | 1433 – New Swarm Research Ground Vehicle (copy) | accepted | 3 | 1707 | L | 5 | Nikita Filippov
Flight Operations | 1434 – Multi-Rotor Training Document | accepted | 3 | 1706 | M | 3 | Connor Kafka
Flight Operations | 1435 – Self-Contained FPV Research | accepted | 3 | 1705 | XS | 1 | Aaron Goldfogel |  |  | finished except for presentation
MAPSS | 1436 - MAPSS Vibration Sensor Acquisition and Testing | accepted | 3 | 1704 | M | 3 | Zach Caratao
MAPSS | 1437 - MAPSS Shaker Table Testing (Part 1) | dropped | #N/A | 1705 | M | 3 | Brett Myers
MAPSS | 1438 - MAPSS Gimbal Structural Component Research | accepted | 3 | 1705 | XS | 1 | Brett Myers
MAPSS | 1439 - MAPSS FLIR VUE Plate Design | accepted | 3 | 1704 | M | 3 | Kelsey Gabel
Collision Awareness | 144 – Unit Testing Background Training (copy) | accepted | 3 | 1312 | M | 3 | Brian Chang | no |  | 0%
MAPSS | 1440 - MAPSS FLIR VUE Plate Manufacturing | accepted | 3 | 1704 | M | 3 | BJ Arun
MAPSS | 1441 – MAPSS Prototype 2 Reconstruction | accepted | 3 | 1703 | S | 2 | Brett Myers
MAPSS | 1442 – MAPSS Camera Payload Plate Final Design | accepted | 3 | 1704 | M | 3 | Kelsey Gabel
MAPSS | 1443 – MAPSS FLIR VUE model reprint/reweigh | dropped | #N/A | 1705 | XS | 1 | Kelsey Gabel
MAPSS | 1444 – MAPSS Flight Test Readiness | accepted | 3 | 1704 | S | 2 | Zach Caratao
MAPSS | 1445 – MAPSS Carbon Fiber Supply | accepted | 3 | 1703 | XS | 1 | BJ Arun
MAPSS | 1446 – MAPSS Electrical System Research | accepted | 3 | 1705 | L | 5 | Zach Caratao
MAPSS | 1447 – MAPSS Prototype 3 Design | accepted | 3 | 1704 | XS | 1 | Zach Caratao
MAPSS | 1448 – MAPSS Prototype 3 Design | accepted | 3 | 1704 | XS | 1 | Kelsey Gabel
MAPSS | 1449 – MAPSS Prototype 3 Design | accepted | 3 | 1704 | XS | 1 | BJ Arun
Collision Awareness | 145 – Unity Game Engine Research | accepted | 3 | 1312 | M | 3 | Madison Peck | yes
MAPSS | 1450 – MAPSS Prototype 3 Design | accepted | 3 | 1704 | XS | 1 | Brett Myers
MAPSS | 1451 – MAPSS Camera Payload Plate Final Design (copy) | accepted | 3 | 1704 | M | 3 | BJ Arun
MAPSS | 1452 – MAPSS Prototype 2 Design and Construction | accepted | 3 | 1703 | M | 3 | Kelsey Gabel
MAPSS | 1453 – MAPSS Prototype 2 Design and Construction (copy) | accepted | 3 | 1703 | M | 3 | Zach Caratao
MAPSS | 1454 – MAPSS Prototype 2 Design and Construction (copy) | accepted | 3 | 1703 | L | 5 | Brett Myers
MAPSS | 1455 – MAPSS Prototype 2 Design and Construction (copy) | accepted | 3 | 1703 | M | 3 | BJ Arun
General AFSL Lab | 1456 – Social Media Updates (copy) – APR ’17 | accepted | 3 | 1705 | M | 3 | Karine Chen |  | 100%
Flight Operations | 1457 – Flight Training Program – Multi-Rotor (copy) | dropped | #N/A | 1705 | L | 5 | Michael Brady
Flight Operations | 1458 – Flight Training Program – Fixed Wing (copy) | accepted | 3 | 1705 | L | 5 | Michael Brady
Flight Operations | 1459 – Troubleshoot CERES (part 2) | accepted | 3 | 1704 | M | 3 | Aaron Goldfogel
Collision Awareness | 146 – Unity Scripting or Module for Automatic Scenario Visualization | accepted | 3 | 1401 | L | 5 | Madison Peck | yes |  | 5 minutes
Flight Operations | 1460 – 3DR Solo Usage Study | accepted | 3 | 1704 | XS | 1 | Aaron Goldfogel
JCATI 2015 | 1461 - Master's Thesis Polishing (Larson) (copy) | accepted | 3 | 1703 | XL | 8 | Robert Larson
JCATI 2015 | 1462 - AIAA SciTech Conference Paper Draft Writing (copy) | accepted | 3 | 1703 | XL | 8 | Robert Larson
General AFSL Lab | 1463 – Perforce Visual Client (copy) | accepted | 3 | 1703 | S | 2 | Lanhao Wu
Flight Operations | 1464 – Auto Takeoff (copy) | accepted | 3 | 1706 | M | 3 | Tadej Kosel
MAPSS | 1465 - MAPSS File Uploading | dropped | #N/A | 1706 | XS | 1 | -
MAPSS | 1466 – MAPSS MTF Poster Creation (Part 2) | accepted | 3 | 1704 | S | 2 | Brett Myers
MAPSS | 1467 – MAPSS Prototype Iteration | accepted | 3 | 1705 | M | 3 | BJ Arun
MAPSS | 1468 – MAPSS Prototype Iteration | accepted | 3 | 1705 | XS | 1 | Zach Caratao
MAPSS | 1469 – MAPSS Prototype Iteration | accepted | 3 | 1705 | M | 3 | Kelsey Gabel
General AFSL Lab | 147 – Jira Bug Tracker Research | in backlog | 0 | - | M | 3 | - |  |  | madison orginally worked on this but I think we need to do it again
MAPSS | 1470 – MAPSS Prototype Iteration | accepted | 3 | 1705 | M | 3 | Brett Myers
MAPSS | 1471 – MAPSS Manufacturability Trade Study | accepted | 3 | 1704 | M | 3 | BJ Arun
MAPSS | 1472 – MAPSS Manufacturability Trade Study (copy) | accepted | 3 | 1704 | M | 3 | Brett Myers
General AFSL Lab | 1473 - Part 107 Test Preparation (copy) | accepted | 3 | 1705 | M | 3 | Michael Brady
Visual Anchoring | 1474 - CONDOR Post-Mortem Analysis (copy) | accepted | 3 | 1705 | M | 3 | Michael Brady | yes
Flight Operations | 1475 – Aircraft Lights Preliminary Integration (Ben) | accepted | 3 | 1711 | S | 2 | Karine Chen |  | 50% | Ben never came home. )':
Flight Operations | 1476 – Request a Waiver for sUAS – BVLOS | accepted | 3 | 1704 | S | 2 | Karine Chen |  | 100%
Flight Operations | 1477 – Request a Waiver for sUAS – Swarm | accepted | 3 | 1805 | XS | 1 | Karine Chen |  | 50%
JCATI 2016 | 1478 -- JCATI Pitch & Symposium | accepted | 3 | 1704 | S | 2 | Zachary Williams
JCATI 2016 | 1479 -- JCATI Pitch & Symposium (copy) | accepted | 3 | 1704 | XS | 1 | Connor Kafka
Collision Awareness | 148 – Unity Game Engine Training | dropped | #N/A | 1402 | M | 3 | Matthew Davis |  |  | madison or richard
JCATI 2016 | 1480 -- JCATI Flight Test I | accepted | 3 | 1704 | M | 3 | Connor Kafka
JCATI 2016 | 1481 -- JCATI Flight Test I | accepted | 3 | 1704 | L | 5 | Zachary Williams
Flight Operations | 1482 – Equipment Verification | dropped | #N/A | 1708 | XS | 1 | -
JCATI 2016 | 1483 – AIAA SciTech Paper JCATI2016 | accepted | 3 | 1706 | M | 3 | Connor Kafka
JCATI 2016 | 1484 – AIAA SciTech Paper JCATI2016 (copy) | accepted | 3 | 1706 | L | 5 | Zachary Williams
JCATI 2016 | 1485 – AIAA SciTech Paper JCATI2016 (copy) | accepted | 3 | 1706 | L | 5 | Hannah Rotta
JCATI 2016 | 1486 – Publishing JCATI Data Online | accepted | 3 | 1801 | M | 3 | Hannah Rotta |  |  | deadline before paper presentation
Flight Operations | 1487 – Research New Pixhawks | accepted | 3 | 1704 | S | 2 | Sam Buxton
Flight Operations | 1488 – Flight Training Program – Fixed Wing (copy) | dropped | #N/A | 1902 | L | 5 | -
General AFSL Lab | 1489 – Perforce Visual Client (copy) | accepted | 3 | 1704 | S | 2 | Carter Kraus
Collision Awareness | 149 – Unity Game Engine Training (copy) | accepted | 3 | 1312 | M | 3 | Richard Fukutome | yes
Flight Operations | 1490 – Investigate INEXA | accepted | 3 | 1704 | S | 2 | Connor Kafka
JCATI 2015 | 1491 – Updating AIAA Conference Paper (Position 1) | accepted | 3 | 1705 | L | 5 | Selina Lui
LiDAR | 1492 – Build MATLAB Script for Real-Time Modeling | in backlog | 0 | 1908 | L | 5 | - |  |  | reviewed in 1901, decided to defer until 1906
Flight Operations | 1493 – MATLAB for ArduCopter Battery Info | dropped | #N/A | 1902 | S | 2 | -
Flight Operations | 1494 – Flight Ops Administration (1703) | accepted | 3 | 1703 | XL | 8 | Hannah Rotta
General AFSL Lab | 1495 – Donated Drone Investigation | dropped | #N/A | 1706 | M | 3 | Jason Borgida
JCATI 2016 | 1496 -- JCATI 1703 Tasks | accepted | 3 | 1703 | M | 3 | Connor Kafka
JCATI 2016 | 1496 – JCATI 1703 Tasks | accepted | 3 | 1703 | M | 3 | Zachary Williams
Flight Operations | 1497 – DJI Phantom 3 MicaSense Mount | accepted | 3 | 1704 | M | 3 | Maius Wong
General AFSL Lab | 1498 – Solder AA Battery Housing | dropped | #N/A | 1705 | XS | 1 | Carter Kraus
Flight Operations | 1499 – Turnigy 9X Buddy Box | accepted | 3 | 1706 | S | 2 | Matthew Lemelin
Collision Awareness | 150 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1402 | L | 5 | John Marshall |  |  | 100%
Flight Operations | 1500 – Checklist Formatting | accepted | 3 | 1706 | M | 3 | Helen Kuni
General AFSL Lab | 1501 – Archiving UAS Articles | accepted | 3 | 1704 | XS | 1 | Helen Kuni
Flight Operations | 1502 – GCS and Aircraft Software/Firmware Upgrades Part 2 | accepted | 3 | 1704 | S | 2 | Carter Kraus
General AFSL Lab | 1503 – Perforce Visual Client (copy) | accepted | 3 | 1705 | S | 2 | Keegan McGrath
General AFSL Lab | 1504 – Setup GPS Repeater | accepted | 3 | 1705 | S | 2 | Scott An
Flight Operations | 1505 – SAM Rebuild (copy) | accepted | 3 | 1704 | S | 2 | Hannah Rotta |  | 100%
Flight Operations | 1506 - Test Location Viewing | accepted | 3 | 1704 | XS | 1 | Hannah Rotta |  | 100%
Flight Operations | 1507 - Test Location Viewing (copy) | accepted | 3 | 1704 | XS | 1 | Karine Chen |  | 100%
Flight Operations | 1508 – Standardize Failsafes | accepted | 3 | 1705 | XS | 1 | Riley Turk
Flight Operations | 1509 – Headset Repair | accepted | 3 | 1704 | XS | 1 | Matthew Lee
Collision Awareness | 151 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1402 | L | 5 | Robert McSwain |  |  | 100%
General AFSL Lab | 1510 – Fix and Organize the Battery Box | accepted | 3 | 1704 | XS | 1 | Matthew Lee
General AFSL Lab | 1511 – Luke Rebuild (copy) | accepted | 3 | 1710 | M | 3 | Tinnabhand Patana-anake
General AFSL Lab | 1512 – Perforce Visual Client (copy) | accepted | 3 | 1706 | S | 2 | Tom Pflibsen
General AFSL Lab | 1513 – Perforce Visual Client (copy) | accepted | 3 | 1704 | S | 2 | Ken Sekine
General AFSL Lab | 1514 – Perforce Visual Client (copy) | accepted | 3 | 1705 | S | 2 | Matthew Lee
General AFSL Lab | 1515 – Perforce Visual Client (copy) | accepted | 3 | 1704 | S | 2 | Gavin Cai
Flight Operations | 1516 – Flight Training Program – Fixed Wing (copy) | accepted | 3 | 1807 | L | 5 | Helen Kuni
General AFSL Lab | 1517 – Perforce Visual Client (copy) | accepted | 3 | 1705 | S | 2 | Richard Jiang
General AFSL Lab | 1518 - Laptop Research & Setup | accepted | 3 | 1705 | S | 2 | Lanhao Wu
General AFSL Lab | 1519 - Laptop Research & Setup(copy) | accepted | 3 | 1705 | M | 3 | Aaron Goldfogel |  | 95%
Collision Awareness | 152 – Unit Testing Background Training (copy) | accepted | 3 | 1403 | M | 3 | John Marshall |  |  | 50%
JCATI 2016 | 1520 -- JCATI 1704 Flight Ops / Tasks | accepted | 3 | 1704 | XL | 8 | Connor Kafka
MAPSS | 1521 – MAPSS Flight Test 4-6-2017 | accepted | 3 | 1704 | S | 2 | Zach Caratao
MAPSS | 1522 – MAPSS Flight Test 4-6-2017 (copy) | accepted | 3 | 1704 | S | 2 | Kelsey Gabel
MAPSS | 1523 – MAPSS Flight Test 4-6-2017 (copy) | accepted | 3 | 1704 | S | 2 | Brett Myers
MAPSS | 1524 – MAPSS Flight Test 4-6-2017 (copy) | accepted | 3 | 1704 | S | 2 | BJ Arun
MAPSS | 1525 – MAPSS Flight Test 4-22-2017 | accepted | 3 | 1704 | M | 3 | Zach Caratao
MAPSS | 1525 – MAPSS Flight Test 4-22-2017 (copy) | accepted | 3 | 1704 | M | 3 | Brett Myers
MAPSS | 1525 – MAPSS Flight Test 4-22-2017 (copy) | accepted | 3 | 1704 | M | 3 | BJ Arun
MAPSS | 1526 – MAPSS Flight Test 4-22-2017 (copy) | accepted | 3 | 1704 | M | 3 | Kelsey Gabel
MAPSS | 1529 – MAPSS Flight Test Transportation | accepted | 3 | 1704 | XS | 1 | BJ Arun
Collision Awareness | 153 – Unit Testing Background Training (copy) | accepted | 3 | 1402 | M | 3 | Robert McSwain |  |  | 100%
MAPSS | 1530 – MAPSS Flight Test Transportation (copy) | accepted | 3 | 1704 | XS | 1 | Brett Myers
MAPSS | 1531 – MAPSS MTF Poster Creation (Part 2) (copy) | accepted | 3 | 1704 | S | 2 | Kelsey Gabel
MAPSS | 1532 – MAPSS Sci-Tech Paper Updates (part 1) | accepted | 3 | 1704 | S | 2 | BJ Arun
MAPSS | 1533 – MAPSS Administration and Budget 1704 | accepted | 3 | 1704 | L | 5 | Zach Caratao
MAPSS | 1534 – MAPSS Manufacturing and Assembly 1704 | accepted | 3 | 1704 | S | 2 | Kelsey Gabel
MAPSS | 1535 – MAPSS Manufacturing and Assembly 1704 (copy) | accepted | 3 | 1704 | L | 5 | Brett Myers
MAPSS | 1536 – MAPSS Manufacturing and Assembly 1704 (copy) | accepted | 3 | 1704 | L | 5 | BJ Arun
MAPSS | 1537 – MAPSS Design 1704 | accepted | 3 | 1704 | L | 5 | Kelsey Gabel
MAPSS | 1538 – MAPSS Design 1704 (copy) | accepted | 3 | 1704 | S | 2 | Brett Myers
MAPSS | 1539 – MAPSS Design 1704 (copy) | accepted | 3 | 1704 | S | 2 | BJ Arun
Collision Awareness | 154 – Developer WebEx Account Setup (Group 16) | accepted | 3 | 1312 | XS | 1 | John Marshall | no |  | 0%
MAPSS | 1540 – MAPSS Design 1704 (copy) | accepted | 3 | 1704 | XS | 1 | Zach Caratao
General AFSL Lab | 1541 – Luke Rebuild (copy) | accepted | 3 | 1706 | XS | 1 | Ge Bao
Flight Operations | 1542 – Troubleshoot CERES (part 3) | accepted | 3 | 1705 | S | 2 | Aaron Goldfogel
Flight Operations | 1543 – Troubleshoot CERES (part 3) (copy) | accepted | 3 | 1705 | M | 3 | Keegan McGrath
Flight Operations | 1544 – Telemetry Radio Investigation | accepted | 3 | 1705 | M | 3 | Matthew Lee
General AFSL Lab | 1545 – MFOC Weight and Balance | accepted | 3 | 1705 | S | 2 | Ken Sekine
Flight Operations | 1546 – Flight Ops Administration (1704) | accepted | 3 | 1704 | XL | 8 | Hannah Rotta
Flight Operations | 1547 – Flight Ops Administration (1705) | accepted | 3 | 1705 | XL | 8 | Hannah Rotta
General AFSL Lab | 1548 - Cera flight manual | accepted | 3 | 1705 | S | 2 | Riley Turk
Flight Operations | 1549 – Cera To-Do Items | accepted | 3 | 1706 | S | 2 | Tadej Kosel |  | 25% | investigated loiter issues, did not resolve
Collision Awareness | 155 – Developer WebEx Account Setup (Group 17) | accepted | 3 | 1402 | XS | 1 | Robert McSwain |  |  | 100%
Flight Operations | 1550 – Anakin To-Do Items | accepted | 3 | 1705 | S | 2 | Carter Kraus
Flight Operations | 1551 – SAM To-Do Items | accepted | 3 | 1805 | S | 2 | Taehan Kook |  |  | Needs Flight Test
Flight Operations | 1552 – Argo Data Flash Logs | accepted | 3 | 1801 | XS | 1 | Joshua Brockschmidt
Flight Operations | 1553 – MFOC Maintenance Items | dropped | #N/A | 1902 | M | 3 | -
General AFSL Lab | 1554 – Precision02 Hard Drive Cleanup | accepted | 3 | 1705 | XS | 1 | Aaron Goldfogel
Flight Operations | 1555 – Cera To-Do Items (copy) | accepted | 3 | 1706 | S | 2 | Jason Borgida
General AFSL Lab | 1556 – UW C++ SDK Development | dropped | #N/A | 1902 | M | 3 | -
Flight Operations | 1557 – MFOC Maintenance Items (copy) | accepted | 3 | 1802 | M | 3 | Taehan Kook
Flight Operations | 1558 – Anakin To-Do Items (copy) | accepted | 3 | 1705 | S | 2 | Helen Kuni
Flight Operations | 1559 – SAM To-Do Items (copy) | accepted | 3 | 1705 | S | 2 | Richard Jiang
Collision Awareness | 156 – Perforce Visual Client (copy) | accepted | 3 | 1313 | S | 2 | Robert McSwain
Mapping(New) | 1560 – Literature Review for the 3D Rendering Mapping Project | accepted | 3 | 1705 | S | 2 | Sicong Huang
Mapping(New) | 1561 – Target Environment Rendering with Unity Engine | accepted | 3 | 1707 | M | 3 | Gavin Cai
Mapping(New) | 1562 – Target Environment Rendering with Unity Engine(copy) | accepted | 3 | 1707 | M | 3 | Richard Jiang
Visual Anchoring | 1563 - Build and Simulate ArduPlane 3.7.1 | accepted | 3 | 1705 | L | 5 | Alex Banh
Visual Anchoring | 1564 - Implement Orbit Controllers in ArduPlane 3.7.1 | dropped | #N/A | 1708 | L | 5 | -
General AFSL Lab | 1565 – Perforce Visual Client (copy) | accepted | 3 | 1709 | S | 2 | Chung Choi
General AFSL Lab | 1566 – Perforce Visual Client (copy) | accepted | 3 | 1710 | S | 2 | Bryson Bruno
General AFSL Lab | 1567 – Perforce Visual Client (copy) | accepted | 3 | 1705 | S | 2 | Mircea Cozmei
General AFSL Lab | 1568 – Perforce Visual Client (copy) | accepted | 3 | 1705 | S | 2 | Tinnabhand Patana-anake
Flight Operations | 1569 – Troubleshoot CERES (part 3) (copy) | accepted | 3 | 1705 | M | 3 | Tinnabhand Patana-anake
Collision Awareness | 157 – New Team Member Orientation (Sprint 1312) | accepted | 3 | 1312 | XS | 1 | Federico Alvarez | no
Visual Anchoring | 1570 - CONDOR first flight prep and flight test | accepted | 3 | 1705 | S | 2 | Michael Brady
Visual Anchoring | 1571 - Update CONDOR AFM and Maintenance Manual | accepted | 3 | 1705 | L | 5 | Michael Brady
General AFSL Lab | 1572 – Perforce Visual Client (copy) | accepted | 3 | 1707 | S | 2 | David Kim
Flight Operations | 1573 – Telemetry Radio Testing | accepted | 3 | 1706 | S | 2 | Matthew Lee
General AFSL Lab | 1574 – Perforce Visual Client (copy) | accepted | 3 | 1706 | S | 2 | Matthew Lemelin
General AFSL Lab | 1575 – Perforce Visual Client (copy) | accepted | 3 | 1705 | S | 2 | Forrest Malcolm
General AFSL Lab | 1576 – Perforce Visual Client (copy) | accepted | 3 | 1705 | S | 2 | Rick Huang
Visual Anchoring | 1577 - Add Visual Anchoring video capability to Leia and test | accepted | 3 | 1705 | S | 2 | Michael Brady
Visual Anchoring | 1578 - Validate UW Mode 2 on Leia | accepted | 3 | 1706 | L | 5 | Ryan Grimes
Visual Anchoring | 1579 - Validate Vision System on Leia | accepted | 3 | 1708 | XL | 8 | Ryan Grimes
Collision Awareness | 158 – Risk Assessment Website Re-Activation | accepted | 3 | 1401 | M | 3 | Keisuke Tsujita | yes |  | 2-3 minutes for this external demo
Visual Anchoring | 1580 - Validate UW Mode 3 on Leia | accepted | 3 | 1710 | L | 5 | Ryan Grimes
Visual Anchoring | 1581 - Implement Orbit Controllers in ArduPlane 3.7.1 (copy) | accepted | 3 | 1708 | L | 5 | Ryan Grimes
Flight Operations | 1582 – Request a Waiver for sUAS – BVLOS (Part 2) | accepted | 3 | 1706 | S | 2 | Karine Chen |  | 100%
General AFSL Lab | 1583 – Social Media Updates (copy) – MAY ’17 | accepted | 3 | 1706 | M | 3 | Karine Chen |  | 100%
General AFSL Lab | 1584 – Social Media Updates (copy) – JUN ’17 | accepted | 3 | 1707 | S | 2 | Karine Chen |  | 100%
General AFSL Lab | 1585 – AFSL Website (Research) – JCATI 2016 | accepted | 3 | 1707 | XS | 1 | Connor Kafka
General AFSL Lab | 1586 – AFSL Website (Research) – Visual Anchoring | accepted | 3 | 1801 | XS | 1 | Ryan Grimes
General AFSL Lab | 1587 – AFSL Website (Research) – MAPPS | accepted | 3 | 1708 | XS | 1 | Karine Chen |  | 100%
General AFSL Lab | 1588 – AFSL Website (Research) – Quad Plane | dropped | #N/A | 1906 | XS | 1 | Christopher Lum
General AFSL Lab | 1589 – AFSL Website (Research) – Mapping | accepted | 3 | 1805 | XS | 1 | Shida Xu
Collision Awareness | 159 – Risk Assessment Website Testing | accepted | 3 | 1401 | S | 2 | Keisuke Tsujita
MAPSS | 1590 – MAPSS Final Paper (Part 1) | accepted | 3 | 1705 | L | 5 | BJ Arun
MAPSS | 1591 – MAPSS Final Paper (Part 1) (copy) | accepted | 3 | 1705 | L | 5 | Zach Caratao
MAPSS | 1592 – MAPSS Final Paper (Part 1) (copy) | accepted | 3 | 1705 | L | 5 | Kelsey Gabel
MAPSS | 1593 – MAPSS Final Paper (Part 1) (copy) | accepted | 3 | 1705 | L | 5 | Brett Myers
MAPSS | 1594 – MAPSS MicaSense Poster Printing for Demo. Flight PR | accepted | 3 | 1705 | XS | 1 | Kelsey Gabel
MAPSS | 1595 – MAPSS Flight Test 17_5_06 | accepted | 3 | 1705 | S | 2 | BJ Arun
MAPSS | 1596 – MAPSS Flight Test 17_5_06 (copy) | accepted | 3 | 1705 | S | 2 | Zach Caratao
MAPSS | 1597 – MAPSS Flight Test 17_5_06 (copy) | accepted | 3 | 1705 | S | 2 | Kelsey Gabel
MAPSS | 1598 – MAPSS Flight Test 17_5_06 (copy) | accepted | 3 | 1705 | XS | 1 | Brett Myers
MAPSS | 1599 – MAPSS Flight Test 17_5_25 | accepted | 3 | 1705 | M | 3 | BJ Arun
General AFSL Lab | 160 – Visual Studio 2012 Unit Testing Directories | in backlog | 0 | - | M | 3 | - |  |  | Henry's build has a problem. Chris L's secondary build has a problem.
MAPSS | 1600 – MAPSS Flight Test 17_5_25 (copy) | accepted | 3 | 1705 | M | 3 | Zach Caratao
MAPSS | 1601 – MAPSS Flight Test 17_5_25 (copy) | accepted | 3 | 1705 | M | 3 | Kelsey Gabel
MAPSS | 1602 – MAPSS Flight Test 17_5_25 (copy) | accepted | 3 | 1705 | M | 3 | Brett Myers
MAPSS | 1603 – MAPSS Flight Test Analysis | accepted | 3 | 1705 | S | 2 | Zach Caratao
MAPSS | 1604 – MAPSS Electrical System Wiring | accepted | 3 | 1705 | S | 2 | Zach Caratao
MAPSS | 1605 – MAPSS Trade Studies Document and Bill of Materials | accepted | 3 | 1706 | S | 2 | Kelsey Gabel
MAPSS | 1606 – MAPSS Technical Drawing | accepted | 3 | 1705 | S | 2 | Kelsey Gabel
MAPSS | 1607 – MAPSS Administration and Budget Role Sprint 1705 | accepted | 3 | 1705 | L | 5 | Zach Caratao
MAPSS | 1608 – MAPSS Technical Drawing | accepted | 3 | 1705 | S | 2 | BJ Arun
General AFSL Lab | 1609 – 3D Printing Instruction | accepted | 3 | 1705 | XS | 1 | Selina Lui
Collision Awareness | 161 – JCATI Marketing Video Approval | accepted | 3 | 1404 | S | 2 | Henry Qin |  |  | high priority
JCATI 2015 | 1610 – AIAA Videos for Presentation | accepted | 3 | 1706 | XS | 1 | Selina Lui
General AFSL Lab | 1611 – 3D Printing Course (Position 1) | accepted | 3 | 1705 | XS | 1 | Tinnabhand Patana-anake
Mapping(New) | 1612 – New Mapping Project Preliminary Development | accepted | 3 | 1705 | XL | 8 | Shida Xu |  | 100% | Describes work done in April
Mapping(New) | 1613 – New Mapping Project AIAA Paper Abstract Composition and Project Management(Part 1) | accepted | 3 | 1705 | XL | 8 | Shida Xu
Flight Operations | 1614 - Grover Repairs | accepted | 3 | 1705 | L | 5 | Nick Armstrong
Flight Operations | 1615 - Swarm Control Research and Ideations | accepted | 3 | 1705 | M | 3 | Nick Armstrong
General AFSL lLab | 1616 - Mac Perforce guide using cask brewmaster | accepted | 3 | 1705 | XS | 1 | Nick Armstrong
Flight Operations | 1617 - Grover Flight Plan | accepted | 3 | 1705 | XS | 1 | Nick Armstrong
Flight Operations | 1618 - CERES Maintenance and Test Cards | accepted | 3 | 1708 | S | 2 | Tinnabhand Patana-anake
Flight Operations | 1618 - CERES Maintenance and Test Cards | accepted | 3 | 1708 | S | 2 | Keegan McGrath
Mapping(New) | 1619 – New Mapping Project AIAA Paper Abstract Composition and Project Management(Part 2) | accepted | 3 | 1706 | XL | 8 | Shida Xu
Collision Awareness | 162 – Unity Asset Generation | dropped | #N/A | 1403 | M | 3 | Henry Qin
Mapping(New) | 1620 – Machine Learning Project Conceptual Development | accepted | 3 | 1705 | M | 3 | Shida Xu |  |  | Describes work done in March
Flight Operations | 1621 – Canada Operations Research | accepted | 3 | 1706 | XS | 1 | Eric Wang
Flight Operations | 1622 – Firmware Upgrade Across Fleet | accepted | 3 | 1706 | S | 2 | Richard Jiang
General AFSL Lab | 1623 – DSLR Focus Problem Investigation | accepted | 3 | 1710 | XS | 1 | Tinnabhand Patana-anake
Flight Operations | 1624 – Update Mission Planner on Lab Computers | accepted | 3 | 1710 | S | 2 | Helen Kuni |  |  | 1.3.49
Flight Operations | 1625 – Standardize Parameters Across Fixed Wing Fleet | accepted | 3 | 1710 | S | 2 | Ryan Grimes
Flight Operations | 1626 – Flight Ops Administration (1706) | accepted | 3 | 1706 | XL | 8 | Hannah Rotta
Flight Operations | 1627 – Flight Ops Administration (1707) | accepted | 3 | 1707 | XL | 8 | Hannah Rotta
Flight Operations | 1628 – Pixhawk 2 Testing | accepted | 3 | 1706 | M | 3 | Mircea Cozmei
Flight Operations | 1629 – Investigate Irrecoverable 45˚ Descents & Crashes | accepted | 3 | 1710 | S | 2 | Helen Kuni
Collision Awareness | 163 – Software Best Practices Poster and Presentations (Session 1) | accepted | 3 | 1401 | M | 3 | Madison Peck |  |  | to present on the 9th.
General AFSL Lab | 1630 – Battery Soldering | accepted | 3 | 1706 | XS | 1 | Eric Wang
General AFSL Lab | 1631 – Perforce Visual Client (copy) | accepted | 3 | 1706 | S | 2 | Eric Wang
General AFSL Lab | 1632 – Public Relations Prep | accepted | 3 | 1710 | M | 3 | Hannah Rotta
General AFSL Lab | 1633 – Clean Air Vent | accepted | 3 | 1706 | XS | 1 | Eric Wang
Mapping | 1634 - Pix4D Familiarization | accepted | 3 | 1706 | M | 3 | Carter Kraus
Flight Operations | 1635 – Flight Training Program – Fixed Wing (copy) | dropped | #N/A | 1902 | L | 5 | -
Flight Operations | 1636 – New Swarm Research Ground Vehicle (copy) | accepted | 3 | 1707 | L | 5 | Tinnabhand Patana-anake
Flight Operations | 1637 – Repair GROVER (copy) | dropped | #N/A | 1706 | M | 3 | Tinnabhand Patana-anake
General AFSL Lab | 1638 – Luke Rebuild (copy) | accepted | 3 | 1707 | S | 2 | Nick Armstrong
Flight Operations | 1639 – Flight Training Program – Fixed Wing (copy) | accepted | 3 | 1706 | M | 3 | Mircea Cozmei
Collision Awareness | 164 – Software Best Practices Poster and Presentations (Session 2) | accepted | 3 | 1402 | M | 3 | Christopher Lum
Flight Operations | 1640 – Flight Training Program – Multi-Rotor (copy) | accepted | 3 | 1706 | M | 3 | Mircea Cozmei
Flight Operations | 1641 – Part 107 Test Preparation (copy) | accepted | 3 | 1707 | S | 2 | Mircea Cozmei
Flight Operations | 1641 – Part 107 Test Preparation (copy) | accepted | 3 | 1805 | S | 2 | Shida Xu |  |  | Temporary License Obtianed
Flight Operations | 1641 – Part 107 Test Preparation (copy) | dropped | #N/A | 1807 | S | 2 | Taehan Kook
Flight Operations | 1642 - Grover Repairs 2 | accepted | 3 | 1706 | M | 3 | Nick Armstrong
Flight Operations | 1643 – New Swarm Research Ground Vehicle (copy) | accepted | 3 | 1710 | M | 3 | Eric Wang
Flight Operations | 1644 - Grover Repairs 2 (Copy) | dropped | #N/A | 1706 | M | 3 | Eric Wang
General AFSL Lab | 1645 – Luke Rebuild (copy) | accepted | 3 | 1710 | L | 5 | Rick Huang
General AFSL Lab | 1646 – Luke Rebuild (copy) | accepted | 3 | 1710 | M | 3 | Eric Wang
Flight Operations | 1647 – Luke Rebuild (copy) | accepted | 3 | 1710 | M | 3 | Mircea Cozmei
Flight Operations | 1648 – Firmware Upgrade Across Fleet (Copy) | accepted | 3 | 1706 | S | 2 | Gavin Cai
Flight Operations | 1649 – Firmware Upgrade Across Fleet (Copy) | accepted | 3 | 1706 | S | 2 | Forrest Malcolm
Collision Awareness | 165 – Software Best Practices Poster and Presentations (Session 3) | accepted | 3 | 1404 | M | 3 | Christopher Lum
General AFSL Lab | 1650 – Perforce Visual Client (copy) | accepted | 3 | 1706 | S | 2 | Alex Lange
JCATI 2016 | 1651 - Argo battery monitor | accepted | 3 | 1706 | L | 5 | Connor Kafka
Flight Operations | 1652 - CERA fixes | accepted | 3 | 1706 | M | 3 | Connor Kafka
Flight Operations | 1653 - INEXA Flight test | accepted | 3 | 1706 | S | 2 | Connor Kafka
Flight Operations | 1654 – Flight Operations Data Archival and MATLAB License Update | accepted | 3 | 1706 | S | 2 | Selina Lui
Flight Operations | 1655 – Learning Flight Operations Data Archival | accepted | 3 | 1706 | XS | 1 | Tinnabhand Patana-anake
Flight Operations | 1656 – Leia Rebuild | accepted | 3 | 1710 | XL | 8 | Rick Huang
Flight Operations | 1657 – Leia Rebuild (copy) | dropped | #N/A | 1710 | L | 5 | -
JCATI 2017 | 1658 – Dust Off TRAPIS Software | dropped | #N/A | 1707 | S | 2 | Hannah Rotta
JCATI 2017 | 1659 – Dust Off TRAPIS Hardware | dropped | #N/A | 1707 | L | 5 | Hannah Rotta
General AFSL Lab | 166 – Software Best Practices Poster and Presentations (Session 4) | in backlog | 0 | - | M | 3 | -
Flight Operations | 1660 – Setup FPV on Multirotor | accepted | 3 | 1707 | XS | 1 | David Kim
Flight Operations | 1661 – Optimize Flight Test Videoing | accepted | 3 | 1804 | S | 2 | Joshua Brockschmidt
General AFSL Lab | 1662 – Set Up Simulator | accepted | 3 | 1707 | XS | 1 | David Kim
Mapping | 1663 - QGIS Familiarization | accepted | 3 | 1706 | XS | 1 | Carter Kraus
Swarm | 1665 – CASE Set-up and Waypoints test | accepted | 3 | 1707 | S | 2 | Tinnabhand Patana-anake
Swarm | 1666 – CASE Set-up and Waypoints test | accepted | 3 | 1707 | S | 2 | Eric Wang
Swarm | 1667 – CASE Set-up and Waypoints test | accepted | 3 | 1707 | S | 2 | Mircea Cozmei
Swarm | 1668 – CASE Set-up and Waypoints test | accepted | 3 | 1707 | S | 2 | Nick Armstrong
General AFSL Lab | 1669 – Social Media Updates (copy) – JUL ’17 | accepted | 3 | 1708 | S | 2 | Karine Chen |  | 100%
Collision Awareness | 167 – Perforce Licensing | accepted | 3 | 1402 | S | 2 | Brian Chang |  |  | high priority
General AFSL Lab | 1670 – AFSL Website Updates (People Section) (copy) | accepted | 3 | 1710 | S | 2 | Karine Chen |  | 100%
Flight Operations | 1671 – VTOL/QuadPlane (copy) | accepted | 3 | 1708 | XL | 8 | Emilynn Roehrich
Flight Operations | 1672 – VTOL/QuadPlane (copy) | accepted | 3 | 1708 | XL | 8 | Areesa Trevino
Mapping | 1673 – Matlab Analysis of DSMs (copy) | accepted | 3 | 1707 | XL | 8 | Matthew Lemelin |  | 30%
Flight Operations | 1674 – Leia Rebuild (copy) | accepted | 3 | 1710 | L | 5 | Mircea Cozmei
General AFSL Lab | 1675 – Perforce Visual Client (copy) | accepted | 3 | 1707 | S | 2 | Ravi Patel
JCATI 2016 | 1676 – JCATI2016 Timestamp Analysis for Database | accepted | 3 | 1707 | S | 2 | David Kim
Flight Operations | 1677 – Leia Rebuild (copy) | accepted | 3 | 1710 | M | 3 | Eric Wang
Visual Anchoring | 1678 - Visual Anchoring Journal Article | accepted | 3 | 1806 | XL | 8 | Ryan Grimes
Flight Operations | 1679 – Leia Rebuild (copy) | accepted | 3 | 1710 | M | 3 | Nikita Filippov
Collision Awareness | 168 – Seattle Area Game Developers Association Meetings | accepted | 3 | 1401 | XS | 1 | Madison Peck
Swarm | 1680 - Familarize with Raspberry Pi and Pixhawk | accepted | 3 | 1707 | S | 2 | Tinnabhand Patana-anake
Swarm | 1681 – Control pixhawk via basic python script using SITL | dropped | #N/A | 1801 | M | 3 | Tinnabhand Patana-anake
Swarm | 1681 – Control pixhawk via basic python script using SITL | accepted | 3 | 1711 | XS | 1 | Nicholas Price
Flight Operations | 1682 – Leia Rebuild (copy) | accepted | 3 | 1710 | L | 5 | Tinnabhand Patana-anake
Swarm | 1683 - Familarize with Raspberry Pi and Pixhawk (copy) | accepted | 3 | 1707 | S | 2 | Nikita Filippov
Swarm | 1684 - Familarize with Raspberry Pi and Pixhawk (copy) | accepted | 3 | 1707 | S | 2 | Eric Wang
Swarm | 1685 - Familarize with Raspberry Pi and Pixhawk (copy) | accepted | 3 | 1707 | S | 2 | Mircea Cozmei
Swarm | 1686 – Control pixhawk via basic python script using SITL (copy) | dropped | #N/A | 1801 | M | 3 | Nikita Filippov
Swarm | 1687 – Control pixhawk via basic python script using SITL (copy) | dropped | #N/A | 1711 | M | 3 | -
Swarm | 1688 – Control pixhawk via basic python script using SITL (copy) | dropped | #N/A | 1711 | M | 3 | -
Flight Operations | 1689 - Sorting equipments from Leia, Luke, Case, Tars, and Grover | accepted | 3 | 1707 | XS | 1 | Tinnabhand Patana-anake
Collision Awareness | 169 – Software Quality Assurance for Sprint 1401 (Position 1) | accepted | 3 | 1403 | S | 2 | Noel Kimber
Flight Operations | 1690 - Sorting equipments from Leia, Luke, Case, Tars, and Grover (copy) | accepted | 3 | 1707 | M | 3 | Andrew Redd
General AFSL Lab | 1691 – Anakin Upgrades | accepted | 3 | 1708 | XS | 1 | Helen Kuni
General AFSL Lab | 1692 – Sort RC Parts Medium | accepted | 3 | 1708 | XS | 1 | David Kim
General AFSL | 1693 - Matlab Script for Reference Propeller Data | accepted | 3 | 1708 | S | 2 | Carter Kraus
Flight Operations | 1694 - Mission Planner Control Panel | accepted | 3 | 1708 | XL | 8 | Connor Kafka
Swarm | 1695 – CASE Set-up and Waypoints test (copy) | accepted | 3 | 1707 | S | 2 | Nikita Filippov
General AFSL Lab | 1696 – Eachine TX03 FPV Camera Setup | accepted | 3 | 1712 | S | 2 | Dylan Hoff
Visual Anchoring | 1697 - Implement Orbit Controllers in ArduPlane 3.8.0 | accepted | 3 | 1708 | L | 5 | Ravi Patel
Flight Operations | 1698 – Carnation Flight Test | accepted | 3 | 1707 | S | 2 | Nikita Filippov
Flight Operations | 1699 – Telemetry Radio Pairing | accepted | 3 | 1708 | M | 3 | Ryan Grimes
Collision Awareness | 170 – Software Quality Assurance for Sprint 1402 (Position 1) | accepted | 3 | 1406 | S | 2 | Aleksandr Tereshchenkov |  |  | math related functions
Flight Operations | 1700 – Aircraft Firmware Upgrades | accepted | 3 | 1710 | S | 2 | Helen Kuni
AMFAV | 1701 – Carnation Flight Test AMFAV July | accepted | 3 | 1707 | M | 3 | Shida Xu
Mapping(New) | 1702 – AIAA SciTech Mapping Paper Composition July | accepted | 3 | 1707 | M | 3 | Shida Xu
AMFAV | 1702 – AMFAV Commissioned Project Development July | accepted | 3 | 1707 | L | 5 | Shida Xu
Swarm | 1703 – Creating CASE Wheels | accepted | 3 | 1708 | XS | 1 | Ravi Patel
General AFSL Lab | 1704 – LiDAR Procurement (copy) | accepted | 3 | 1707 | XL | 8 | Karine Chen |  | 100%
General AFSL Lab | 1705 – LiDAR Equipment Box Procurement | accepted | 3 | 1708 | S | 2 | Karine Chen |  | 100%
General AFSL Lab | 1706 – Social Media Updates (copy) – AUG ‘17 | accepted | 3 | 1709 | XS | 1 | Karine Chen |  | 100%
LiDAR | 1707 – LiDAR Unboxing and Integration | accepted | 3 | 1708 | XS | 1 | Karine Chen |  | 100%
General AFSL Lab | 1708 – Plum Airworthiness | dropped | #N/A | 1804 | S | 2 | - |  |  | what about lights for night operation
General AFSL Lab | 1709 – Excelsior Airworthiness | accepted | 3 | 1805 | M | 3 | Grant Bringham
Collision Awareness | 171 – Software Quality Assurance for Sprint 1402 (Position 2) | in backlog | 0 | - | S | 2 | - |  | 15% | conflict calculator related functions
General AFSL Lab | 1710 – Learning Python Basics | accepted | 3 | 1708 | XS | 1 | Ravi Patel
General AFSL Lab | 1711 – MissionPlanner Simulation Setup | accepted | 3 | 1708 | S | 2 | Ravi Patel
Mapping(New) | 1712 – AIAA SciTech Mapping Paper Composition July | accepted | 3 | 1708 | S | 2 | Shida Xu
AMFAV | 1713 – AMFAV Commissioned Project Development July | accepted | 3 | 1708 | L | 5 | Shida Xu
Mapping(New) | 1714 – Rendering Research | accepted | 3 | 1708 | S | 2 | Gavin Cai
General AFSL Lab | 1715 – Social Media Updates (copy) – SEP ‘17 | accepted | 3 | 1803 | M | 3 | Bryson Bruno
LiDAR | 1716 – LiDAR Documentation | accepted | 3 | 1709 | S | 2 | Karine Chen |  | 100%
LiDAR | 1717 – VeloView Software Research | accepted | 3 | 1711 | XS | 1 | Chung Choi
LiDAR | 1718 – FugroViewer Software Research | accepted | 3 | 1709 | XS | 1 | Karine Chen |  | 100%
LiDAR | 1719 – Dummy Payload Testing | accepted | 3 | 1711 | XS | 1 | Jason Yarrow
General AFSL Lab | 172 – Investigate CodeLens in Visual Studio 2013 | in backlog | 0 | - | M | 3 | -
LiDAR | 1720 – LiDAR Flight System Mount Research (Position 1) | accepted | 3 | 1710 | M | 3 | Jason Yarrow |  | 100%
General AFSL Lab | 1721 – Plum Airworthiness (copy) | accepted | 3 | 1708 | XS | 1 | Karine Chen |  | 100%
TRAPIS2 | 1722 – Visual Studio 2017 Compatibility | accepted | 3 | 1709 | XS | 1 | Christopher Lum
TRAPIS2 | 1723 – Unit Background Testing (copy) | accepted | 3 | 1711 | S | 2 | Jacob Longhurst
TRAPIS2 | 1724 – TRAPIS to Mission Planner Interface | dropped | #N/A | 1803 | XL | 8 | -
TRAPIS2 | 1724 – Unit Testing for UWSDK | dropped | #N/A | 1902 | XL | 8 | -
General AFSL Lab | 1724 - Unit Testing for UWSK | accepted | 3 | 1802 | XS | 1 | Travis Clement
General AFSL Lab | 1724 - Unit Testing for UWSK | accepted | 3 | 1711 | XL | 8 | Nathan Isaman
TRAPIS2 | 1725 – ANPC LAMS Simulator Familiarization | accepted | 3 | 1710 | S | 2 | Connor Kafka |  |  | not a super high priority
TRAPIS2 | 1726 – TRAPIS Simulator Familiarization | accepted | 3 | 1710 | XL | 8 | Hannah Rotta
TRAPIS2 | 1727 – TRAPIS Flight Test Scenario Design | accepted | 3 | 1712 | L | 5 | Hannah Rotta
TRAPIS2 | 1728 – Mission Planner Customization for TRAPIS2 – Receive from TRAPIS | dropped | #N/A | 1803 | XL | 8 | -
TRAPIS2 | 1729 – Mission Planner Customization for TRAPIS2 – Send to UAV | dropped | #N/A | 1803 | XL | 8 | Connor Kafka |  |  | rescope this story pending Tintin and Jacob's demo
Collision Awareness | 173 – New Team Member Orientation (Sprint 1313) | accepted | 3 | 1313 | XS | 1 | Federico Alvarez
TRAPIS2 | 1730 – ArduPlane Customization for TRAPIS2 – WA_SMP | accepted | 3 | 1802 | S | 2 | Alex Banh
TRAPIS2 | 1731 – ArduPlane Customization for TRAPIS2 – Receive from GCS | dropped | #N/A | 1803 | XL | 8 | Zach Caratao
Flight Operations | 1732 – Upgrade Flight Logs | accepted | 3 | 1712 | S | 2 | Ken Sekine
General AFSL Lab | 1733 – Make Lab Stations Functional | accepted | 3 | 1710 | XS | 1 | Ravi Patel
Flight Operations | 1734 – Mobius Timestamp | accepted | 3 | 1710 | XS | 1 | Rick Huang
General AFSL Lab | 1735 – Organize Lab | accepted | 3 | 1710 | S | 2 | Jaspreet Sidhu
Flight Operations | 1736 – Checklist Updates | accepted | 3 | 1710 | S | 2 | Helen Kuni
Flight Operations | 1737 – Purchase Chairs | accepted | 3 | 1709 | S | 2 | Christopher Lum
Flight Operations | 1738 – Cockpit Voice Recorder | accepted | 3 | 1803 | S | 2 | Joshua Brockschmidt |  |  | add documentation onto manual
TRAPIS2 | 1739 – ArduPlane Development Workflow | accepted | 3 | 1802 | XL | 8 | Alex Banh
Collision Awareness | 174 –Risk Assessment Website Re-Activation (Helper) | dropped | #N/A | 1313 | S | 2 | Seunghyun Ko
TRAPIS2 | 1740 – Finwing Sabre Build (Peach) | accepted | 3 | 1801 | XL | 8 | Helen Kuni
TRAPIS2 | 1741 – TRAPIS Payload Familiarization | accepted | 3 | 1802 | XL | 8 | Selina Lui
TRAPIS2 | 1742 – ANPC LAMS Simulator Familiarization (copy) | accepted | 3 | 1710 | XS | 1 | Ravi Patel |  |  | not super high priority
JCATI 2016 | 1743 – SDR Familiarization | accepted | 3 | 1711 | S | 2 | Connor Kafka
General AFSL Lab | 1744 – Finish FUNRA | accepted | 3 | 1801 | XL | 8 | Zachary Williams
Flight Operations | 1745 – Install FPV DVR in MFOC | accepted | 3 | 1710 | S | 2 | Karine Chen |  | 100%
Flight Operations | 1746 – Address Aircraft Construction & Maintenance Logs | accepted | 3 | 1711 | M | 3 | Deepanshu Gupta
TRAPIS2 | 1747 – TRAPIS to Mission Planner Interface (copy) | accepted | 3 | 1711 | M | 3 | Connor Kafka
TRAPIS2 | 1748 – TRAPIS2 Strategic Planning | accepted | 3 | 1709 | XL | 8 | Christopher Lum
Flight Operations | 1749 – Investigate Plum’s Auto Takeoff | accepted | 3 | 1711 | S | 2 | Riley Turk
Collision Awareness | 175 – Unity Scripting or Module for Automatic Scenario Visualization (Position 2) | accepted | 3 | 1402 | L | 5 | Richard Fukutome
Flight Operations | 1750 – Test Data Transfer Cables | accepted | 3 | 1710 | XS | 1 | Sita Manne
Flight Operations | 1751 – Ground Penetrating Radar | dropped | #N/A | 1902 | XL | 8 | -
TRAPIS2 | 1752 – TRAPIS Position Estimate Selection Control | accepted | 3 | 1710 | XL | 8 | Christopher Lum
TRAPIS2 | 1753 – TRAPIS2 Preliminary Flight Test Using ADS-B Output | accepted | 3 | 1802 | L | 5 | Hannah Rotta
General AFSL Lab | 1754 – Organize Lab (copy) | accepted | 3 | 1709 | XS | 1 | Hannah Rotta |  | 100%
General AFSL Lab | 1755 – Organize Lab (copy) | accepted | 3 | 1709 | XS | 1 | Karine Chen |  | 100%
General AFSL Lab | 1756 – Organize Tapes and Glues Box | accepted | 3 | 1710 | S | 2 | Jaspreet Sidhu
General AFSL Lab | 1757 – Organize Raw Wires | accepted | 3 | 1710 | S | 2 | Jaspreet Sidhu
General AFSL Lab | 1758 – Organize Strings on the Ceiling | accepted | 3 | 1710 | S | 2 | Dylan Hoff
General AFSL Lab | 1759 – Luke Rebuild (copy) | accepted | 3 | 1710 | M | 3 | Helen Kuni
Collision Awareness | 176 – Unity Asset Generation (Helper) | accepted | 3 | 1401 | M | 3 | Daniel Ablog | no
Flight Operations | 1760 – Flight Ops Administration (1708) | accepted | 3 | 1708 | XL | 8 | Hannah Rotta
Flight Operations | 1761 – Flight Ops Administration (1709) | accepted | 3 | 1709 | XL | 8 | Hannah Rotta
Flight Operations | 1762 – Flight Ops Administration (1710) | accepted | 3 | 1710 | XL | 8 | Hannah Rotta
TRAPIS2 | 1763 – EFB for ADS-B in Traffic | accepted | 3 | 1710 | S | 2 | Sai Ranganathan
General AFSL Lab | 1764 - Perforce Visual Client (copy) | accepted | 3 | 1710 | S | 2 | Jason Yarrow
LiDAR | 1765 - LiDAR Flight System Mount Research (Position 2) | accepted | 3 | 1710 | M | 3 | Selina Lui |  | 100%
General AFSL Lab | 1766 – Fix 2 Cell Battery | accepted | 3 | 1710 | S | 2 | Nicholas Price
General AFSL Lab | 1767 – Assess Status of Pixhawk | accepted | 3 | 1710 | S | 2 | Selina Lui
General AFSL Lab | 1768 – Reprint Leia Cover | accepted | 3 | 1710 | S | 2 | Rick Huang
General AFSL Lab | 1769 – Reprint Leia Cover (copy) | accepted | 3 | 1710 | S | 2 | Selina Lui
Collision Awareness | 177 – Literature Review (STANAG-4586) | accepted | 3 | 1401 | M | 3 | Kevin Ueunten | yes |  | possibly move tasks. This should be a shorter demo (1 -2 minutes)
General AFSL Lab | 1770 – Perforce Visual Client (copy) | accepted | 3 | 1710 | S | 2 | Sita Manne
General AFSL Lab | 1771 – Perforce Visual Client (copy) | accepted | 3 | 1710 | S | 2 | Jaspreet Sidhu
General AFSL Lab | 1772 – Perforce Visual Client (copy) | accepted | 3 | 1710 | S | 2 | Sai Ranganathan
General AFSL Lab | 1773 – Perforce Visual Client (copy) | accepted | 3 | 1710 | S | 2 | Griffin Klett
General AFSL Lab | 1774 – Perforce Visual Client (copy) | accepted | 3 | 1710 | S | 2 | Dylan Hoff
Flight Operations | 1775 – Standardize Parameters Across Fixed Wing Fleet (copy) | accepted | 3 | 1710 | S | 2 | Hannah Rotta
Flight Operations | 1776 – Standardize Parameters Across Fixed Wing Fleet (copy) | accepted | 3 | 1710 | S | 2 | Helen Kuni
Flight Operations | 1777 – Aircraft Firmware Upgrades (copy) | accepted | 3 | 1710 | S | 2 | Hannah Rotta
Flight Operations | 1778 – Aircraft Firmware Upgrades (copy) | accepted | 3 | 1710 | S | 2 | Ryan Grimes
Visual Anchoring | 1779 – Visual Anchoring Conference Paper (copy) | accepted | 3 | 1712 | XL | 8 | Ryan Grimes
Collision Awareness | 178 – Sprint 1313 Administration | accepted | 3 | 1313 | M | 3 | Christopher Lum
Flight Operations | 1780 – Flight Training Program – Fixed Wing (copy) | dropped | #N/A | 1903 | L | 5 | Dylan Hoff
Flight Operations | 1780 – Flight Training Program – Fixed Wing (copy) | dropped | #N/A | 1807 | L | 5 | Taehan Kook
General AFSL Lab | 1781 – Perforce Visual Client (copy) | accepted | 3 | 1710 | S | 2 | Sid Raman
TRAPIS2 | 1782 – Finwing Sabre Build (Peach) (copy) | accepted | 3 | 1801 | XL | 8 | Riley Turk
TRAPIS2 | 1783 – Finwing Sabre Build (Peach) (copy) | accepted | 3 | 1801 | XL | 8 | Bryson Bruno
TRAPIS2 | 1784 – Finwing Sabre Builds (copy) | dropped | #N/A | 1710 | XL | 8 | -
General AFSL Lab | 1785 – Perforce Visual Client (copy) | accepted | 3 | 1710 | S | 2 | Deepanshu Gupta
General AFSL Lab | 1786 – Perforce Visual Client (copy) | accepted | 3 | 1711 | S | 2 | Tushar Lakhanpal
General AFSL Lab | 1787 – Perforce Visual Client (copy) | dropped | #N/A | 1804 | S | 2 | Firn Tieanklin
General AFSL Lab | 1788 – Perforce Visual Client (copy) | accepted | 3 | 1710 | S | 2 | Caelen Wang
General AFSL Lab | 1789 – Perforce Visual Client (copy) | accepted | 3 | 1711 | S | 2 | Joshua Brockschmidt
Collision Awareness | 179 – Unity Asset Generation (Helper) | dropped | #N/A | 1402 | M | 3 | John Marshall |  |  | 0%
General AFSL Lab | 1790 – Perforce Visual Client (copy) | dropped | #N/A | 1812 | S | 2 | Frederick Chandra
TRAPIS2 | 1791 – TRAPIS Simulator Familiarization (Copy) | dropped | #N/A | 1711 | S | 2 | -
TRAPIS2 | 1792 – TRAPIS Simulator Familiarization (Copy) | dropped | #N/A | 1711 | XL | 8 | -
General AFSL Lab | 1793 – Make Lab Stations Functional (copy) | accepted | 3 | 1710 | XS | 1 | Connor Kafka
General AFSL Lab | 1794 – Organize Lab (copy) | accepted | 3 | 1710 | XS | 1 | Sita Manne
General AFSL Lab | 1795 – Organize Strings on the Ceiling (copy) | accepted | 3 | 1710 | S | 2 | Joshua Brockschmidt
Flight Operations | 1796 – Address Aircraft Construction & Maintenance Logs (copy) | dropped | #N/A | 1902 | S | 2 | -
Flight Operations | 1797 – Drill Propeller | accepted | 3 | 1710 | XS | 1 | Firn Tieanklin
Flight Operations | 1798 – Emergency (Auto) Landing Preparation | accepted | 3 | 1711 | M | 3 | Sita Manne
Flight Operations | 1799 – Troubleshoot Transmitter A | accepted | 3 | 1711 | XS | 1 | Hannah Rotta
Collision Awareness | 180 – Unity Asset Generation (Helper) | accepted | 3 | 1313 | M | 3 | Robert McSwain
Flight Operations | 1800 – Change Excelsior Transmitter | accepted | 3 | 1803 | XS | 1 | Cory Cantey
General AFSL Lab | 1801 – Mission Planner Familiarization (Copy) | accepted | 3 | 1801 | S | 2 | Joshua Brockschmidt
General AFSL Lab | 1802 – Aircraft Part Familiarization (Copy) | dropped | #N/A | 1902 | S | 2 | -
Flight Operations | 1803 – COA Renewal | blocked | 5 | 1904 | S | 2 | -
TRAPIS2 | 1804 – TRAPIS Payload Familiarization (copy) | accepted | 3 | 1802 | XL | 8 | Karine Chen |  | 100%
General AFSL Lab | 1805 – Organize Strings on the Ceiling (copy) | accepted | 3 | 1710 | XS | 1 | Rick Huang
General AFSL Lab | 1806 – Organize Strings on the Ceiling (copy) | accepted | 3 | 1710 | XS | 1 | Tinnabhand Patana-anake
Quad Plane | 1807- Finish FUNRA Step 1 | accepted | 3 | 1712 | XL | 8 | Dylan Hoff
Quad Plane | 1808- Finish FUNRA Step 2 | accepted | 3 | 1712 | S | 2 | Sid Raman
Quad Plane | 1809- Finish FUNRA Step 3 | accepted | 3 | 1712 | S | 2 | Griffin Klett
General AFSL Lab | 181 – Perforce Visual Client (copy) | accepted | 3 | 1411 | XS | 1 | Jeremy Brenner |  | 90%
Flight Operations | 1810 – Investigate RTL Settings | accepted | 3 | 1711 | S | 2 | Jaspreet Sidhu
Flight Operations | 1811 – Standardize Aircraft Battery Mounting | dropped | #N/A | 1804 | S | 2 | Sai Ranganathan
TRAPIS2 | 1812 – Investigate Dallesport Wind History | accepted | 3 | 1711 | S | 2 | Helen Kuni
General AFSL Lab | 1813 – AA101/198 Promo Video | accepted | 3 | 1802 | XL | 8 | Tushar Lakhanpal
Mapping(New) | 1814 – New Mapping AIAA SciTech Mapping Paper Composition October | accepted | 3 | 1710 | L | 5 | Shida Xu
Mapping(New) | 1815 – New Mapping Project Software Developemnt | accepted | 3 | 1711 | L | 5 | Shida Xu
Mapping(New) | 1816 – New Mapping AIAA SciTech Mapping Paper Composition October | accepted | 3 | 1710 | L | 5 | Carter Kraus
General AFSL Lab | 1817 – Perforce Visual Client (copy) | accepted | 3 | 1710 | S | 2 | Varith Hong
JCATI 2016 | 1818 – JCATI2016 SciTech Conference Paper | accepted | 3 | 1712 | XL | 8 | Connor Kafka
JCATI 2016 | 1819 – JCATI2016 SciTech Conference Paper (copy) | accepted | 3 | 1712 | M | 3 | Zachary Williams
General AFSL Lab | 182 – Developer WebEx Account Setup (Group 16) | in backlog | 0 | - | XS | 1 | -
JCATI 2016 | 1820 – JCATI2016 SciTech Conference Paper (copy) | accepted | 3 | 1712 | XL | 8 | Hannah Rotta
Flight Operations | 1821 – Headset Repair | accepted | 3 | 1711 | XS | 1 | Sai Ranganathan
TRAPIS2 | 1822 – GPS-Denied Literature Review | accepted | 3 | 1804 | M | 3 | Karine Chen |  | 100%
General AFSL Lab | 1823 – Surplus Extra Computers | accepted | 3 | 1807 | S | 2 | Christopher Lum
General AFSL Lab | 1824 – Social Media Updates (copy) – AUT ‘17 | accepted | 3 | 1803 | M | 3 | Bryson Bruno
General AFSL Lab | 1825 – Supervise Social Media Updates | accepted | 3 | 1801 | XS | 1 | Karine Chen |  | 100%
General AFSL Lab | 1826 – Perforce Visual Client (copy) | accepted | 3 | 1710 | S | 2 | Vivian Hua
General AFSL Lab | 1827 – Perforce Visual Client (copy) | accepted | 3 | 1710 | S | 2 | Blake Fletcher
TRAPIS2 | 1828 – ArduPlane Development Workflow (copy) | accepted | 3 | 1712 | M | 3 | Connor Kafka
TRAPIS2 | 1829 – Arduplane Development Workflow (copy) | accepted | 3 | 1802 | XL | 8 | Ravi Patel
General AFSL Lab | 183 – Software Developer Background Training (Algorithm and Back End) (copy) | in backlog | 0 | - | L | 5 | -
General AFSL Lab | 1830 – Mission Planner Familiarization (copy) | dropped | #N/A | 1902 | S | 2 | -
Flight Operations | 1831 – Leia Maintenance | accepted | 3 | 1804 | S | 2 | Jaspreet Sidhu
Flight Operations | 1831 – Leia Maintenance | accepted | 3 | 1802 | S | 2 | Tushar Lakhanpal
Flight Operations | 1831 – Leia Maintenance | accepted | 3 | 1802 | XS | 1 | Sheershak Agarwal
Flight Operations | 1832 – Luke Maintenance | accepted | 3 | 1712 | S | 2 | Helen Kuni
General AFSL Lab | 1833 – Perforce Visual Client (copy) | accepted | 3 | 1711 | S | 2 | Orion Black-Brown
LiDAR | 1834 – VeloView Software Research (copy) | accepted | 3 | 1712 | S | 2 | Deepanshu Gupta
LiDAR | 1835 – VeloView Software Research (copy) | accepted | 3 | 1712 | S | 2 | Mike Kurnia
LiDAR | 1836 – Dummy Payload Testing (copy) | accepted | 3 | 1711 | XS | 1 | Firn Tieanklin
LiDAR | 1837 – Dummy Payload Testing (copy) | accepted | 3 | 1711 | XS | 1 | Varith Hong
LiDAR | 1838 – Raspberry Pi Integration | dropped | #N/A | 1801 | XS | 1 | Connor Kafka
LiDAR | 1839 – Raspberry Pi Integration (copy) | accepted | 3 | 1802 | XL | 8 | Joshua Brockschmidt |  |  | add documentation onto manual
General AFSL Lab | 184 – Unit Testing Background Training (copy) | in backlog | 0 | - | M | 3 | Zach Caratao
LiDAR | 1840 – Raspberry Pi Integration (copy) | accepted | 3 | 1802 | M | 3 | Sai Ranganathan |  |  | add documentation onto manual(final test with circuit and clock)
LiDAR | 1841 – LiDAR to Li-Po Power Supply | accepted | 3 | 1712 | XS | 1 | Selina Lui |  | 50%
LiDAR | 1842 – Continuous Waypoint Mapping | accepted | 3 | 1802 | XS | 1 | Hannah Rotta
LiDAR | 1843 – Minimize Data Error | accepted | 3 | 1711 | XS | 1 | Blake Fletcher
LiDAR | 1844 – Infrared Testing | in backlog | 0 | 1908 | M | 3 | - |  |  | reviewed in 1901, decided to defer until 1906
Flight Operations | 1845 – Request a Waiver for sUAS – BVLOS (Part 3) | dropped | #N/A | 1902 | S | 2 | -
Flight Operations | 1846 – Request a Waiver for sUAS – BVLOS (Part 3) (copy) | dropped | #N/A | 1806 | S | 2 | Karine Chen
Flight Operations | 1847 – Request a Waiver for sUAS – Night | accepted | 3 | 1803 | S | 2 | Hannah Rotta
Flight Operations | 1848 – Request a Waiver for sUAS – Night (copy) | accepted | 3 | 1803 | S | 2 | Karine Chen |  | 100%
LiDAR | 1849 – Stand-Alone GPS Integration | accepted | 3 | 1801 | XS | 1 | Sai Ranganathan
Collision Awareness | 185 – Risk Assessment Website Testing (Helper) | accepted | 3 | 1403 | M | 3 | Seunghyun Ko |  |  | 85%
LiDAR | 1850 – LiDAR Flight Test Scenario Design | accepted | 3 | 1802 | XS | 1 | Hannah Rotta
LiDAR | 1851 – Standardize LiDAR Parameters | accepted | 3 | 1803 | XS | 1 | Joshua Brockschmidt
Flight Operations | 1852 – Flight Ops Administration (1711) | accepted | 3 | 1711 | XL | 8 | Hannah Rotta
Flight Operations | 1853 – Flight Ops Administration (1712) | accepted | 3 | 1712 | L | 5 | Hannah Rotta
Visual Anchoring | 1854 - Design and Test Vision System | accepted | 3 | 1803 | XL | 8 | Ryan Grimes
General AFSL Lab | 1855 – Perforce Visual Client (copy) | accepted | 3 | 1712 | S | 2 | Travis Clement
Flight Operations | 1856 – ArduPilot Sofware Development Setup | accepted | 3 | 1804 | XS | 1 | Jacob Longhurst
Flight Operations | 1856 – ArduPilot Sofware Development Setup | dropped | #N/A | 1902 | M | 3 | -
Flight Operations | 1856 – ArduPilot Sofware Development Setup (copy) | accepted | 3 | 1802 | M | 3 | Yao Dou
Flight Operations | 1857 – ArduPilot Sofware Development Setup (copy) | accepted | 3 | 1802 | M | 3 | Mason Guiste
General AFSL Lab | 1858 – Perforce Visual Client (copy) | accepted | 3 | 1711 | S | 2 | Jacob Longhurst
Mapping(New) | 1859 – Finish Mapping SciTech Paper (November) | accepted | 3 | 1712 | XL | 8 | Shida Xu
Collision Awareness | 186 – Sprint 1401 Administration | accepted | 3 | 1401 | M | 3 | Christopher Lum
Mapping(New) | 1860 – Mapping SciTech Pesentation Slides | accepted | 3 | 1712 | L | 5 | Shida Xu
Mapping(New) | 1861 – Mapping SciTech Presentation | dropped | #N/A | 1801 | S | 2 | Shida Xu
TRAPIS2 | 1862 – Send Mavlink message with Python Dronekit Library | accepted | 3 | 1711 | S | 2 | Tinnabhand Patana-anake
General AFSL Lab | 1863 – Update lab computers to Windows 10 | accepted | 3 | 1711 | XS | 1 | Tinnabhand Patana-anake
TRAPIS2 | 1864 – Generate custom Mavlink message | accepted | 3 | 1801 | XL | 8 | Tinnabhand Patana-anake
Swarm | 1865 – User Interface for connecting Mavproxy to Pixhawk | accepted | 3 | 1711 | XS | 1 | Tinnabhand Patana-anake
TRAPIS2 | 1866 – Unit Background Testing (copy) | accepted | 3 | 1712 | M | 3 | Travis Clement
General AFSL Lab | 1867 – Unit Testing Background Training (copy) | accepted | 3 | 1711 | M | 3 | Sita Manne
General AFSL Lab | 1868 – Build Wing Rack for AFSL Lab | accepted | 3 | 1711 | M | 3 | Nicholas Price
General AFSL Lab | 1869 – Plum Wiring Replaced | accepted | 3 | 1711 | M | 3 | Nicholas Price
Collision Awareness | 187 – Collision Detection Engine (Part 1) | accepted | 3 | 1401 | L | 5 | Christopher Lum | yes
Swarm | 1870 – Control pixhawk via basic python script using SITL | dropped | #N/A | 1801 | M | 3 | Zachary Williams
Flight Operations | 1871-- Multirotor Training Administration | accepted | 3 | 1802 | L | 5 | Zachary Williams
JCATI 2016 | 1872-- JCATI 2016 AIAA Conference Presentation | accepted | 3 | 1712 | M | 3 | Zachary Williams
General AFSL Lab | 1873 – Perforce Visual Client (copy) | dropped | #N/A | 1812 | S | 2 | Grant Bringham
General AFSL Lab | 1874 – Perforce Visual Client (copy) | accepted | 3 | 1712 | S | 2 | Tao Jin
General AFSL Lab | 1875 – Perforce Visual Client (copy) | accepted | 3 | 1712 | S | 2 | Yao Dou
LiDAR | 1876 – VeloView Software Research (copy) | accepted | 3 | 1712 | S | 2 | Chung Choi
LiDAR | 1877 – Test LiDAR to Li-Po Power Supply | accepted | 3 | 1712 | XS | 1 | Sheershak Agarwal
LiDAR | 1878 – Minimize Data Error (copy) | accepted | 3 | 1712 | XS | 1 | Blake Fletcher
LiDAR | 1879 – Document Dummy Payload | dropped | #N/A | 1804 | XS | 1 | Firn Tieanklin |  |  | confirm documentation with Hannah/Karine
Collision Awareness | 188 – System Components High Level Design | accepted | 3 | 1401 | M | 3 | Christopher Lum
Flight Operations | 1880 – Request a Waiver for sUAS – Night (copy) | accepted | 3 | 1803 | S | 2 | Gabriella Sciuchetti
TRAPIS2 | 1881 – TRAPIS Software Quality Assurance (SQA) Testing | dropped | #N/A | 1803 | M | 3 | Taehan Kook
TRAPIS2 | 1882 – ANPC Remote LAMS Connection Testing | accepted | 3 | 1804 | S | 2 | Connor Kafka
General AFSL Lab | 1883 – Lab Safety | accepted | 3 | 1804 | XL | 8 | Taehan Kook
General AFSL Lab | 1884 – YouTube Tutorials | accepted | 3 | 1803 | L | 5 | Christopher Lum
JCATI 2016 | 1885 – AFSL Web Server Setup | dropped | #N/A | 1812 | XL | 8 | -
TRAPIS2 | 1886 – ArduPilotAFSL.sln Completion | accepted | 3 | 1801 | L | 5 | Taehan Kook
TRAPIS2 | 1886 – ArduPilotAFSL.sln Completion (copy) | accepted | 3 | 1801 | M | 3 | Yao Dou
TRAPIS2 | 1887 – MAVProxy Testing | dropped | #N/A | 1812 | L | 5 | -
General AFSL Lab | 1888 – Heinemann Book | accepted | 3 | 1802 | L | 5 | Hannah Rotta
Quad Plane | 1889 – Research and Develop FUNRA Safety Procedures | accepted | 3 | 1801 | M | 3 | Zachary Williams
Collision Awareness | 189 – Forward State Estimator Implementation (Orbit) | accepted | 3 | 1405 | L | 5 | Kevin Ueunten | 1 |  | need testing, lower priority for 1403, maybe move to 1404. 40%, possibly descope. Create another user story for the variance part of the algorithm.
Quad Plane | 1890 – Research and Develop FUNRA Safety Procedures (copy) | accepted | 3 | 1801 | M | 3 | Dylan Hoff
General AFSL Lab | 1891 – HiL Airworthiness | accepted | 3 | 1801 | L | 5 | Taehan Kook
General AFSL Lab | 1891 – HiL Airworthiness | accepted | 3 | 1804 | L | 5 | Taehan Kook
HIPPO | 1892 – Perforce Visual Client (copy) | accepted | 3 | 1801 | S | 2 | Alex Bernard
HIPPO | 1893 – Perforce Visual Client (copy) | accepted | 3 | 1802 | S | 2 | Christopher Lynch
HIPPO | 1894 – Perforce Visual Client (copy) | accepted | 3 | 1801 | S | 2 | Gabriella Sciuchetti
HIPPO | 1895 – Perforce Visual Client (copy) | accepted | 3 | 1801 | S | 2 | Samden Sherpa
TEMPEST | 1896 – Perforce Visual Client (copy) | accepted | 3 | 1802 | S | 2 | Zachary Rotter
TEMPEST | 1897 – Perforce Visual Client (copy) | accepted | 3 | 1802 | S | 2 | Laura Smit
TEMPEST | 1898 – Perforce Visual Client (copy) | accepted | 3 | 1805 | S | 2 | Kirby Taylor
TEMPEST | 1899 – Perforce Visual Client (copy) | accepted | 3 | 1803 | S | 2 | Bohao Zhu
Collision Awareness | 190 – Forward State Estimator Implementation (Flight Path) | accepted | 3 | 1403 | L | 5 | Bao Le | yes |  | need testing
HIPPO | 1900 – Senior Design Capstone Setup | accepted | 3 | 1802 | S | 2 | Alex Bernard
HIPPO | 1901 – Senior Design Capstone Setup (copy) | accepted | 3 | 1802 | S | 2 | Christopher Lynch
HIPPO | 1902 – Senior Design Capstone Setup (copy) | accepted | 3 | 1802 | S | 2 | Gabriella Sciuchetti
HIPPO | 1903 – Senior Design Capstone Setup (copy) | accepted | 3 | 1802 | S | 2 | Samden Sherpa
TEMPEST | 1904 – Senior Design Capstone Setup (copy) | accepted | 3 | 1801 | S | 2 | Zachary Rotter
TEMPEST | 1905 – Senior Design Capstone Setup (copy) | accepted | 3 | 1801 | S | 2 | Laura Smit
TEMPEST | 1906 – Senior Design Capstone Setup (copy) | accepted | 3 | 1801 | S | 2 | Kirby Taylor
TEMPEST | 1907 – Senior Design Capstone Setup (copy) | accepted | 3 | 1801 | S | 2 | Bohao Zhu
TRAPIS2 | 1908 – KDLS Airport Use Permissions | accepted | 3 | 1805 | S | 2 | Hannah Rotta
TRAPIS2 | 1909 – Mission Planner Custom Modes Procedure | accepted | 3 | 1802 | S | 2 | Ravi Patel
General AFSL Lab | 191 – Upgrade UW.sln from .Net 3.5 to .Net 4.0 | in backlog | 0 | - | S | 2 | Christopher Lum
TRAPIS2 | 1910 – WSTR Development | accepted | 3 | 1805 | M | 3 | Ravi Patel
HIPPO | 1911 – HIPPO First Steps | accepted | 3 | 1801 | M | 3 | Alex Bernard
LARAMID | 1912 – White Bird Aircraft Flight Manual Documentation | accepted | 3 | 1802 | M | 3 | Chung Choi |  | 100%
LARAMID | 1913 – Mini-Talon Build | accepted | 3 | 1804 | M | 3 | Chung Choi |  | 100%
TRAPIS2 | 1914 – ArduPlane Customization for TRAPIS2 – WA_SMP (copy) | dropped | #N/A | 1802 | M | 3 | -
Visual Anchoring | 1915 – Visual Anchoring Conference Presentation | accepted | 3 | 1712 | L | 5 | Ryan Grimes
General AFSL Lab | 1916 – Perforce Visual Client (copy) | accepted | 3 | 1803 | S | 2 | Sheershak Agarwal
General AFSL Lab | 1917- Part 107 Test Preparation (copy) | accepted | 3 | 1806 | M | 3 | Helen Kuni
Visual Anchoring | 1918 – Visual Anchoring Conference Powerpoint | dropped | #N/A | 1712 | L | 5 | Ryan Grimes
Flight Operations | 1919 – Luke Aircraft Flight Manual | accepted | 3 | 1801 | S | 2 | Nicholas Price
General AFSL Lab | 192 – Fix Method Names in ConflictEntityTest | in backlog | 0 | - | XS | 1 | -
Flight Operations | 1920 – Peach Aircraft Flight Manual | dropped | #N/A | 1806 | S | 2 | Nicholas Price
Flight Operations | 1921 – Pear Aircraft Flight Manual | dropped | #N/A | 1806 | S | 2 | Nicholas Price
Flight Operations | 1922 – Plum Aircraft Flight Manual | dropped | #N/A | 1907 | S | 2 | Nicholas Price
TRAPIS2 | 1923 – 3D Print Dummy Sagetech Transponder | accepted | 3 | 1801 | M | 3 | Blake Fletcher
Flight Operations | 1924 - Activate Argo's Landing Gear | accepted | 3 | 1712 | XS | 1 | Dylan Hoff
Flight Operations | 1925 - Copy of 1924 | accepted | 3 | 1712 | XS | 1 | Zachary Williams
TEMPEST | 1926 – TEMPEST First Steps | accepted | 3 | 1801 | M | 3 | Zachary Rotter
General AFSL Lab | 1927 – AFSL Website Updates (Public Relations/Media Section) | accepted | 3 | 1806 | M | 3 | Karine Chen |  | 100%
General AFSL Lab | 1927 – AFSL Website Updates (UWCUTS Section) | accepted | 3 | 1805 | XS | 1 | Karine Chen |  | 100%
Collision Awareness | 193 – Perforce Visual Client (copy) | accepted | 3 | 1401 | S | 2 | Taylor Campbell
HIPPO | 1930 – Research into Past Work | accepted | 3 | 1801 | XS | 1 | Alex Bernard
HIPPO | 1931 – Research into Past Work | accepted | 3 | 1801 | XS | 1 | Samden Sherpa
HIPPO | 1932 – Research into Past Work | accepted | 3 | 1801 | XS | 1 | Christopher Lynch
HIPPO | 1933 – Research into Past Work | accepted | 3 | 1801 | XS | 1 | Gabriella Sciuchetti
TEMPEST | 1934 - TEMPEST Preliminary Research | accepted | 3 | 1802 | S | 2 | Zachary Rotter
TEMPEST | 1935 - TEMPEST Preliminary Research | accepted | 3 | 1802 | S | 2 | Kirby Taylor
TEMPEST | 1936 - TEMPEST Preliminary Research | accepted | 3 | 1802 | S | 2 | Laura Smit
TEMPEST | 1937 - TEMPEST Preliminary Research | accepted | 3 | 1802 | S | 2 | Bohao Zhu
TEMPEST | 1938 – TEMPEST Financial First Steps | accepted | 3 | 1801 | S | 2 | Laura Smit
TEMPEST | 1939 - TEMPEST Project Plan Deliverables | accepted | 3 | 1801 | XS | 1 | Zachary Rotter
Collision Awareness | 194 – Developer WebEx Account Setup (Group 16) | accepted | 3 | 1401 | XS | 1 | Taylor Campbell
TEMPEST | 1940 - TEMPEST Project Plan Deliverables | dropped | #N/A | 1801 | XS | 1 | Kirby Taylor
TEMPEST | 1941 - TEMPEST Project Plan Deliverables | dropped | #N/A | 1801 | XS | 1 | Laura Smit
TEMPEST | 1942 - TEMPEST Project Plan Deliverables | dropped | #N/A | 1801 | XS | 1 | Bohao Zhu
TEMPEST | 1943 – TEMPEST Rough Schedule | accepted | 3 | 1801 | XS | 1 | Zachary Rotter
TEMPEST | 1944 - TEMPEST Workspace and Equipment Procurement | accepted | 3 | 1802 | XS | 1 | Christopher Lum
TEMPEST | 1945 - TEMPEST Unigraphics/NX First Steps | accepted | 3 | 1801 | XS | 1 | Laura Smit
General AFSL Lab | 1946 – Replace SSD for lab computer AFSL05 | accepted | 3 | 1801 | S | 2 | Joshua Brockschmidt
HIPPO | 1947 – HIPPO Safety Training | accepted | 3 | 1801 | XS | 1 | Alex Bernard
HIPPO | 1948 – HIPPO Safety Training | accepted | 3 | 1801 | XS | 1 | Samden Sherpa
HIPPO | 1949 – HIPPO Safety Training | accepted | 3 | 1802 | XS | 1 | Christopher Lynch
Collision Awareness | 195 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1401 | L | 5 | Taylor Campbell
HIPPO | 1950 – HIPPO Safety Training | accepted | 3 | 1801 | XS | 1 | Gabriella Sciuchetti
HIPPO | 1951 – Non-optical Sensor Trade Study | accepted | 3 | 1801 | L | 5 | Alex Bernard
HIPPO | 1952 – Non-optical Sensor Trade Study | accepted | 3 | 1801 | L | 5 | Samden Sherpa
HIPPO | 1953 – Non-optical Sensor Trade Study | accepted | 3 | 1801 | L | 5 | Christopher Lynch
HIPPO | 1954 – Non-optical Sensor Trade Study | accepted | 3 | 1801 | L | 5 | Gabriella Sciuchetti
HIPPO | 1955 – Admin Team Lead Duties | accepted | 3 | 1801 | S | 2 | Alex Bernard
HIPPO | 1956 – Budgeting Manager Duties | accepted | 3 | 1802 | XS | 1 | Christopher Lynch
HIPPO | 1957 – Fulfill Capstone Requirements | accepted | 3 | 1801 | M | 3 | Alex Bernard
HIPPO | 1958 – Fulfill Capstone Requirements | accepted | 3 | 1801 | S | 2 | Samden Sherpa
HIPPO | 1959 – Fulfill Capstone Requirements | accepted | 3 | 1801 | M | 3 | Christopher Lynch
Collision Awareness | 196 – Unit Testing Background Training (copy) | accepted | 3 | 1402 | M | 3 | Taylor Campbell
HIPPO | 1960 – Fulfill Capstone Requirements | accepted | 3 | 1801 | M | 3 | Gabriella Sciuchetti
LARAMID | 1961 – LARAMID Designing Docking Mechanism | accepted | 3 | 1802 | XL | 8 | Chung Choi |  | 80%
TRAPIS2 | 1962 – TRAPIS Payload Familiarization (copy) | accepted | 3 | 1802 | XL | 8 | Hannah Rotta
TRAPIS2 | 1963 – UASIPP Application | accepted | 3 | 1712 | XL | 8 | Hannah Rotta
TRAPIS2 | 1964 – UASIPP Application (copy) | accepted | 3 | 1712 | S | 2 | Hannah Rotta
General AFSL Lab | 1965 – Setup AFSL Server | accepted | 3 | 1801 | M | 3 | Joshua Brockschmidt
TRAPIS2 | 1966 – ArduPlane Customization for TRAPIS2 – WA_SMP (copy) | accepted | 3 | 1802 | L | 5 | Ravi Patel
Flight Operations | 1967 – Flight Ops Administration (1801) | accepted | 3 | 1801 | XL | 8 | Hannah Rotta
Flight Operations | 1968 – Flight Ops Administration (1802) | accepted | 3 | 1802 | XL | 8 | Hannah Rotta
Flight Operations | 1969 – Flight Ops Administration (1803) | accepted | 3 | 1803 | XL | 8 | Hannah Rotta
Collision Awareness | 197 – Simulation Test Plan Design and Documentation Part 2 | accepted | 3 | 1402 | M | 3 | Taylor Campbell |  |  | talk with chris on Monday
General AFSL Lab | 1970 – Perforce Visual Client (copy) | dropped | #N/A | 1812 | S | 2 | Shaunak Pandit
TRAPIS2 | 1971 – Generate custom Mavlink message (copy) | accepted | 3 | 1801 | XL | 8 | Jacob Longhurst
General AFSL Lab | 1972 – UWSDK Unit Testing | accepted | 3 | 1801 | S | 2 | Travis Clement
General AFSL Lab | 1973 – Perforce Visual Client (copy) | accepted | 3 | 1801 | S | 2 | Mason Guiste
General AFSL Lab | 1974 – Perforce Visual Client (copy) | accepted | 3 | 1904 | S | 2 | Mozes Jacobs
General AFSL Lab | 1975 – Perforce Visual Client (copy) | accepted | 3 | 1802 | S | 2 | Rostyk Svitelskyi
General AFSL Lab | 1976 – Perforce Visual Client (copy) | accepted | 3 | 1804 | S | 2 | Kelly Lee
General AFSL Lab | 1977 – Perforce Visual Client (copy) | accepted | 3 | 1804 | S | 2 | Veen Oung
General AFSL Lab | 1978 – Perforce Visual Client (copy) | accepted | 3 | 1804 | S | 2 | Joseph DePalma
General AFSL Lab | 1979 – Perforce Visual Client (copy) | accepted | 3 | 1805 | S | 2 | Jordan Sims
Collision Awareness | 198 – Conflict Calculator Feature Level Design | accepted | 3 | 1401 | L | 5 | Christopher Lum | yes
TRAPIS2 | 1980 – Finwing Roll Characteristics | accepted | 3 | 1802 | L | 5 | Christopher Lum
General AFSL Lab | 1981 – Sort LiPo Batteries | accepted | 3 | 1801 | S | 2 | Yao Dou
TRAPIS2 | 1982 – Finwing Roll Characteristics (copy) | accepted | 3 | 1802 | S | 2 | Hannah Rotta
Flight Operations | 1983 – Upgrade Flight Logs (Part 2) | accepted | 3 | 1802 | S | 2 | Yao Dou
Flight Operations | 1984 – Investigate Luke’s Receiver Problem | accepted | 3 | 1801 | XS | 1 | Mason Guiste
Swarm | 1985 – Swarm Research | accepted | 3 | 1801 | S | 2 | Nicholas Price
Swarm | 1986 – Swarm Research (Copy) | accepted | 3 | 1802 | XS | 1 | Tinnabhand Patana-anake
Swarm | 1986 – Swarm Research (Copy) | accepted | 3 | 1801 | S | 2 | Nikita Filippov
Swarm | 1987 – Swarm Research (Copy) | accepted | 3 | 1802 | XS | 1 | Dylan Hoff
Swarm | 1988 – Swarm Research (Copy) | accepted | 3 | 1802 | S | 2 | Griffin Klett
Swarm | 1989 – Swarm Research (Copy) | accepted | 3 | 1802 | S | 2 | Sid Raman
Collision Awareness | 199 – Risk Assessment Website Debugging | accepted | 3 | 1403 | L | 5 | Keisuke Tsujita |  |  | 100%
HIPPO | 1990 – Make HIPPO Gantt Chart | accepted | 3 | 1801 | XS | 1 | Gabriella Sciuchetti
HIPPO | 1991 – HIPPO Marketing and Outreach Duties | accepted | 3 | 1802 | XS | 1 | Gabriella Sciuchetti
HIPPO | 1992 – FAA Daylight Operations Waiver (for flying at night) | accepted | 3 | 1803 | S | 2 | Alex Bernard
TEMPEST | 1993 – TEMPEST Unigraphics / NX First Steps | accepted | 3 | 1801 | XS | 1 | Zachary Rotter
TEMPEST | 1994 – Secretary Lead Duties | accepted | 3 | 1801 | XS | 1 | Bohao Zhu
TEMPEST | 1995 - TEMPEST Communications / Marketing Lead Duties | accepted | 3 | 1805 | XS | 1 | Bohao Zhu
TEMPEST | 1996 - TEMPEST Administrative Lead Duties | accepted | 3 | 1801 | M | 3 | Zachary Rotter
TEMPEST | 1997 - TEMPEST Block Diagram First Draft | accepted | 3 | 1802 | S | 2 | Bohao Zhu
TEMPEST | 1998 - TEMPEST Safety Training | accepted | 3 | 1801 | XS | 1 | Zachary Rotter
TEMPEST | 1999 - TEMPEST Safety Training | accepted | 3 | 1805 | XS | 1 | Kirby Taylor
Collision Awareness | 200 – UWKML Refactor | accepted | 3 | 1402 | L | 5 | Christopher Lum
TEMPEST | 2000 - TEMPEST Safety Training | accepted | 3 | 1801 | XS | 1 | Laura Smit
TEMPEST | 2001 - TEMPEST Safety Training | accepted | 3 | 1801 | XS | 1 | Bohao Zhu
TEMPEST | 2002 - TEMPEST Schedule Update | dropped | #N/A | 1801 | XS | 1 | Zachary Rotter
TEMPEST | 2003 - TEMPEST Stability Researh | accepted | 3 | 1805 | S | 2 | Kirby Taylor
TEMPEST | 2004 - TEMPEST Materials Research | accepted | 3 | 1804 | M | 3 | Laura Smit
TEMPEST | 2005 - TEMPEST Regulations Research | accepted | 3 | 1802 | XS | 1 | Laura Smit
TEMPEST | 2006 - TEMPEST Electronics Research | accepted | 3 | 1802 | M | 4 | Bohao Zhu
TEMPEST | 2007 - TEMPEST Rough First Design Sketch | accepted | 3 | 1802 | S | 2 | Zachary Rotter
TEMPEST | 2008 - TEMPEST Rough First Design Sketch | accepted | 3 | 1802 | S | 2 | Kirby Taylor
TEMPEST | 2009 - TEMPEST Rough First Design Sketch | accepted | 3 | 1802 | S | 2 | Laura Smit
Collision Awareness | 201 – CAPlugin vs. TCAS Comparison | accepted | 3 | 1402 | M | 3 | Al Creigh | yes |  | 75%
TEMPEST | 2010 - TEMPEST Rough First Design Sketch | accepted | 3 | 1803 | S | 2 | Bohao Zhu
LARAMID | 2011 – Mini-Talon Build (Copy) | accepted | 3 | 1804 | M | 3 | Tao Jin
LARAMID | 2011 – Mini-Talon Build (Copy) | accepted | 3 | 1804 | M | 3 | Taehan Kook
Flight Operations | 2012 – Airspace Authorization Rules | accepted | 3 | 1801 | XS | 1 | Jaspreet Sidhu
Flight Operations | 2013 – Battery Warmer | accepted | 3 | 1802 | XS | 1 | Shaunak Pandit
TRAPIS2 | 2014 – Aileron Deflection Measurements for Wing Leveler | accepted | 3 | 1801 | XS | 1 | Nikita Filippov
TRAPIS2 | 2015 – Aileron Deflection Measurements for Wing Leveler (copy) | accepted | 3 | 1801 | XS | 1 | Helen Kuni
General AFSL Lab | 2016 – Propeller Lock 3D Print | accepted | 3 | 1802 | S | 2 | Sai Ranganathan
General AFSL Lab | 2017 – Plywood Cutting for Battery Charging Station | accepted | 3 | 1801 | XS | 1 | Dylan Hoff
JCATI 2016 | 2018 – SDR Database Front End | dropped | #N/A | 1906 | M | 3 | -
Flight Operations | 2019 – FAA DroneZone Account Creation | accepted | 3 | 1802 | XS | 1 | Christopher Lum
Collision Awareness | 202 – Entity Manager Feature Level Design | accepted | 3 | 1402 | M | 3 | Christopher Lum
General AFSL Lab | 2020 – UWSDK Unit Testing Copy | accepted | 3 | 1801 | S | 2 | Sita Manne
LiDAR | 2021 – GUI Development | accepted | 3 | 1806 | L | 5 | Travis Clement
HIPPO | 2022 – HIPPO DRR Preparation | accepted | 3 | 1801 | S | 2 | Alex Bernard
HIPPO | 2023 – HIPPO DRR Preparation | accepted | 3 | 1801 | S | 2 | Gabriella Sciuchetti
HIPPO | 2024 – HIPPO DRR Preparation | accepted | 3 | 1801 | XS | 1 | Christopher Lynch
HIPPO | 2025 – HIPPO DRR Preparation | accepted | 3 | 1801 | XS | 1 | Samden Sherpa
TEMPEST | 2026 - TEMPEST DRR Preparation | accepted | 3 | 1802 | S | 2 | Zachary Rotter
TEMPEST | 2027 - TEMPEST DRR Preparation | accepted | 3 | 1802 | S | 2 | Kirby Taylor
TEMPEST | 2028 - TEMPEST DRR Preparation | accepted | 3 | 1802 | S | 2 | Laura Smit
TEMPEST | 2029 - TEMPEST DRR Preparation | accepted | 3 | 1802 | S | 2 | Bohao Zhu
Collision Awareness | 203 – Entity Manager Implementation | accepted | 3 | 1402 | L | 5 | Christopher Lum | yes
TEMPEST | 2030 - TEMPEST January Meetings | accepted | 3 | 1801 | M | 3 | Zachary Rotter
TEMPEST | 2031 - TEMPEST January Meetings | accepted | 3 | 1801 | M | 3 | Kirby Taylor
TEMPEST | 2032 - TEMPEST January Meetings | accepted | 3 | 1801 | M | 3 | Laura Smit
TEMPEST | 2033 - TEMPEST January Meetings | accepted | 3 | 1801 | M | 3 | Bohao Zhu
TEMPEST | 2034 - TEMPEST Fiberglass Research | dropped | #N/A | 1802 | M | 3 | Laura Smit
TEMPEST | 2035 - TEMPEST Simple CAD Model | accepted | 3 | 1801 | XS | 1 | Zachary Rotter
TEMPEST | 2036 - TEMPEST Simple CFD Study | accepted | 3 | 1802 | L | 5 | Kirby Taylor
TEMPEST | 2037 - TEMPEST Reel System Research | accepted | 3 | 1805 | M | 3 | Zachary Rotter
TEMPEST | 2038 - TEMPEST Centralized System Design Matrix | accepted | 3 | 1802 | XS | 1 | Laura Smit
TEMPEST | 2039 - TEMPEST LaTex Paper Infrastructure | accepted | 3 | 1802 | XS | 1 | Zachary Rotter
Collision Awareness | 204 – Flight Path Class | accepted | 3 | 1402 | M | 3 | Matthew Davis
TEMPEST | 2040 - Planning for TEMPEST Prototype Truck Test Design | dropped | #N/A | 1803 | L | 5 | -
TEMPEST | 2041 - TEMPEST Full Model Truck Test | dropped | #N/A | 1805 | M | 3 | - |  |  | improve title to reflect spirit of story
TEMPEST | 2042 - TEMPEST Wind Tunnel Test Design | dropped | #N/A | 1803 | L | 5 | - |  |  | improve title to reflect spirit of story
TEMPEST | 2043 - TEMPEST SciTech Conference Registration | accepted | 3 | 1806 | XS | 1 | Zachary Rotter
TEMPEST | 2044 - TEMPEST Component CAD Modeling | dropped | #N/A | 1805 | M | 3 | Zachary Rotter
TEMPEST | 2045 - TEMPEST Component CAD Modeling | accepted | 3 | 1804 | L | 5 | Laura Smit
TEMPEST | 2046 - TEMPEST CAD Modeling Integration | accepted | 3 | 1804 | L | 5 | Laura Smit
TEMPEST | 2047 - Internal PDR Preparation | accepted | 3 | 1802 | S | 2 | Zachary Rotter
TEMPEST | 2048 - Internal PDR Preparation | accepted | 3 | 1802 | S | 2 | Kirby Taylor
TEMPEST | 2049 - Internal PDR Preparation | accepted | 3 | 1802 | S | 2 | Laura Smit
Collision Awareness | 205 – Sprint 1402 Administration | accepted | 3 | 1402 | M | 3 | Christopher Lum
TEMPEST | 2050 - Internal PDR Preparation | accepted | 3 | 1802 | S | 2 | Bohao Zhu
Mapping(New) | 2051 – Package and Migrate Project Code to Perforce | accepted | 3 | 1804 | M | 3 | Shida Xu |  | 100%
Mapping(New) | 2052 – Point Cloud Library (PCL) User Tutorial | accepted | 3 | 1805 | S | 2 | Shida Xu
AMFAV | 2053 – Correlation Study of UAV Data and Ground Truth Data | dropped | #N/A | 1809 | S | 2 | Shida Xu
TRAPIS2 | 2054 - Finwing Sabre Build (Pear) | accepted | 3 | 1804 | XL | 8 | Helen Kuni
TRAPIS2 | 2055 - Finwing Sabre Build (Pear) (copy) | accepted | 3 | 1804 | XS | 1 | Riley Turk
TRAPIS2 | 2055 - Finwing Sabre Build (Pear) (copy) | accepted | 3 | 1804 | XL | 8 | Taehan Kook
TRAPIS2 | 2056 - Finwing Sabre Build (Pear) (copy) | accepted | 3 | 1805 | S | 2 | Taehan Kook
TRAPIS2 | 2057 – Finwing Ballast | accepted | 3 | 1802 | M | 3 | Rostyk Svitelskyi
Flight Operations | 2058 – Plum Maintenance | accepted | 3 | 1802 | M | 3 | Rostyk Svitelskyi
Flight Operations | 2059 – ArduPilot Sofware Development Setup (Copy) | dropped | #N/A | 1902 | M | 3 | -
Collision Awareness | 206 – Software Quality Assurance for Sprint 1402 (Position 3) | accepted | 3 | 1405 | S | 2 | Brian Chang
HIPPO | 2060 – HIPPO Budgeting Duties | accepted | 3 | 1802 | XS | 1 | Christopher Lynch
HIPPO | 2061 – HIPPO Admin Duties | accepted | 3 | 1802 | L | 5 | Alex Bernard
HIPPO | 2062 – HIPPO Marketing and Outreach Duties | accepted | 3 | 1802 | XS | 1 | Gabriella Sciuchetti
HIPPO | 2063 – Communication with Microflown, Sensing Clues | accepted | 3 | 1802 | XS | 1 | Alex Bernard
HIPPO | 2064 – Sensor Choice | accepted | 3 | 1802 | XS | 1 | Alex Bernard
HIPPO | 2065 – Sensor Choice | accepted | 3 | 1802 | XS | 1 | Gabriella Sciuchetti
HIPPO | 2066 – Sensor Choice | accepted | 3 | 1802 | XS | 1 | Christopher Lynch
HIPPO | 2067 – Sensor Choice | accepted | 3 | 1802 | XS | 1 | Samden Sherpa
HIPPO | 2068 – V2 Model from Vulcan | accepted | 3 | 1802 | XS | 1 | Alex Bernard
HIPPO | 2069 – LiDAR Familiarization | dropped | #N/A | 1803 | S | 2 | -
Collision Awareness | 207 – Software Quality Assurance for Sprint 1402 (Position 4) | accepted | 3 | 1402 | S | 2 | Henry Qin |  |  | 95%
HIPPO | 2070 – Artificial Light Sensor Research | accepted | 3 | 1802 | S | 2 | Gabriella Sciuchetti
HIPPO | 2071 – Capstone Safety Matrix | accepted | 3 | 1802 | XS | 1 | Alex Bernard
HIPPO | 2072 – Sensor Support Research | accepted | 3 | 1802 | XS | 1 | Alex Bernard
HIPPO | 2073 – Sensor Support Research | accepted | 3 | 1802 | XS | 1 | Gabriella Sciuchetti
HIPPO | 2074 – Sensor Support Research | accepted | 3 | 1802 | XS | 1 | Samden Sherpa
HIPPO | 2075 – Paper Introduction | accepted | 3 | 1803 | S | 2 | Alex Bernard
HIPPO | 2075 – Sensor Support Research | accepted | 3 | 1802 | XS | 1 | Christopher Lynch
LARAMID | 2077 – Electromagnet Interference on UAV compass | accepted | 3 | 1803 | S | 2 | Sheershak Agarwal
LARAMID | 2078 – Electromagnet holding test on Styrofoam | accepted | 3 | 1802 | S | 2 | Blake Fletcher
LARAMID | 2079 – Accelerometer Research | dropped | #N/A | 1807 | S | 2 | Chung Choi
Collision Awareness | 208 – Software Quality Assurance for Sprint 1402 (Position 5) | accepted | 3 | 1403 | M | 3 | Madison Peck
LARAMID | 2080 – Research Proposal | accepted | 3 | 1802 | XS | 1 | Chung Choi |  | 100%
Flight Operations | 2081 – Fix Anakin's rudder | accepted | 3 | 1802 | XS | 1 | Taehan Kook
General AFSL Lab | 2082 – Component Description Document | accepted | 3 | 1802 | S | 2 | Taehan Kook
Flight Operations | 2083 – Reinstall Pixhawk on Cera | accepted | 3 | 1802 | M | 3 | Taehan Kook
LARAMID | 2084 – Stepper Motor Docking Design | accepted | 3 | 1802 | S | 2 | Tao Jin
LARAMID | 2085 – Sled Research | accepted | 3 | 1803 | S | 2 | Chung Choi |  | 100%
HIPPO | 2086 – Paper Formatting and Intro | accepted | 3 | 1802 | S | 2 | Gabriella Sciuchetti
HIPPO | 2087 – HIPPO February Meeting Preparation | accepted | 3 | 1802 | M | 3 | Alex Bernard
HIPPO | 2088 – HIPPO February Meeting Preparation | accepted | 3 | 1802 | M | 3 | Gabriella Sciuchetti
HIPPO | 2089 – HIPPO February Meeting Preparation | accepted | 3 | 1802 | M | 3 | Christopher Lynch
Collision Awareness | 209 – Software Quality Assurance Lead for Sprint 1402 | accepted | 3 | 1403 | M | 3 | Noel Kimber |  |  | talk with Chris about triaging unit tests. 75%
HIPPO | 2090 – HIPPO February Meeting Preparation | accepted | 3 | 1802 | M | 3 | Samden Sherpa
HIPPO | 2091 – HIPPO AERB 120 Workstation | accepted | 3 | 1802 | XS | 1 | Alex Bernard
HIPPO | 2092 – HIPPO Flight Test Participation | accepted | 3 | 1803 | L | 6 | Alex Bernard
HIPPO | 2093 – HIPPO Flight Test Familiarization | accepted | 3 | 1804 | XS | 1 | Gabriella Sciuchetti
HIPPO | 2094 – HIPPO Flight Test Familiarization | accepted | 3 | 1804 | XS | 1 | Christopher Lynch
HIPPO | 2095 – HIPPO Flight Test Familiarization | accepted | 3 | 1804 | XS | 1 | Samden Sherpa
HIPPO | 2096 – Plan HIPPO Flight Test Campaign | accepted | 3 | 1802 | S | 2 | Alex Bernard
HIPPO | 2097 – Microphone Investingation | accepted | 3 | 1802 | S | 2 | Alex Bernard
HIPPO | 2098 – HIPPO January Meetings | accepted | 3 | 1802 | M | 3 | Alex Bernard
HIPPO | 2099 – HIPPO January Meetings | accepted | 3 | 1802 | M | 3 | Gabriella Sciuchetti
Collision Awareness | 210 – Windows Presentation Foundation Controls Research for CAPlugin | accepted | 3 | 1402 | M | 3 | Dai Tsukada | yes |  | 75%
HIPPO | 2100 – HIPPO January Meetings | accepted | 3 | 1802 | M | 3 | Christopher Lynch
HIPPO | 2101 – HIPPO January Meetings | accepted | 3 | 1802 | M | 3 | Samden Sherpa
General AFSL Lab | 2102 – Purchase iPad | accepted | 3 | 1802 | XS | 1 | Taehan Kook
Flight Operations | 2103 – Finwing Decals | accepted | 3 | 1802 | S | 2 | Taehan Kook
HIPPO | 2104 – Botswana Familiarization | accepted | 3 | 1802 | S | 2 | Alex Bernard
HIPPO | 2105 – Camera Research | accepted | 3 | 1802 | S | 2 | Gabriella Sciuchetti
HIPPO | 2106 – Resolution Calculations | accepted | 3 | 1802 | XS | 1 | Samden Sherpa
HIPPO | 2107 – Shutter speed and Camera Research | accepted | 3 | 1802 | XS | 1 | Christopher Lynch
General AFSL Lab | 2108 – Battery Warmer Bag Documentation | accepted | 3 | 1802 | XS | 1 | Taehan Kook
General AFSL Lab | 2109 – New Battery Soldering | accepted | 3 | 1802 | S | 2 | Taehan Kook
General AFSL Lab | 211 – Research Inputs for Risk Assessment Tool | in backlog | 0 | - | M | 3 | -
LARAMID | 2110 – Mini-Talon Build (Copy) | accepted | 3 | 1804 | S | 2 | Blake Fletcher |  |  | No longer with the lab
TRAPIS2 | 2110 – TRAPIS Payload Familiarization (copy) | accepted | 3 | 1802 | XL | 8 | Karine Chen |  | 100%
TRAPIS2 | 2111 – TRAPIS Payload Familiarization (copy) | accepted | 3 | 1802 | M | 3 | Selina Lui
LiDAR | 2112 – STF 2017-39 Annual Report | accepted | 3 | 1802 | XS | 1 | Karine Chen |  | 100%
LARAMID | 2113 – Stepper Motor Docking Documentation | accepted | 2 | 1802 | XS | 1 | Tao Jin
HIPPO | 2114 – Plan HIPPO Flight Test Campaign | accepted | 3 | 1802 | S | 2 | Gabriella Sciuchetti
HIPPO | 2115 – HIPPO Project Vision Poster | accepted | 3 | 1802 | S | 2 | Gabriella Sciuchetti
HIPPO | 2116 – Continue Investigation into Artificial Light Detection | accepted | 3 | 1802 | M | 3 | Gabriella Sciuchetti
HIPPO | 2117 – Create Database of Test Images for Software Development | accepted | 3 | 1802 | M | 3 | Christopher Lynch
HIPPO | 2118 – Initiate Sensor Integration into AFSL UAS | accepted | 3 | 1803 | M | 3 | Alex Bernard
HIPPO | 2119 – Incorporate Completed Work into SciTech Paper | accepted | 3 | 1803 | M | 3 | Gabriella Sciuchetti
Collision Awareness | 212 – Google Earth KML Research | accepted | 3 | 1402 | M | 3 | Christopher Lum
HIPPO | 2120 – Sensor Integration and Camera Calculations | accepted | 3 | 1803 | M | 3 | Samden Sherpa
HIPPO | 2121 – Compile a Procurement List | accepted | 3 | 1802 | S | 2 | Christopher Lynch
TRAPIS2 | 2122 - TRAPIS-MAVLINK-ARDUPILOT Loop Verification | accepted | 3 | 1802 | L | 5 | Tinnabhand Patana-anake
TRAPIS2 | 2122 - TRAPIS-MAVLINK-ARDUPILOT Loop Verification | accepted | 3 | 1802 | L | 5 | Jacob Longhurst
TRAPIS2 | 2123 - UW_STEER Development (copy) | accepted | 3 | 1802 | M | 3 | Ryan Grimes
TRAPIS2 | 2124 - UW_STEER Development (copy) | accepted | 3 | 1802 | M | 3 | Hannah Rotta
General AFSL Lab | 2125 – Clean Soldering Iron | accepted | 3 | 1804 | S | 2 | Shaunak Pandit
LiDAR | 2126 – Infrared Testing | accepted | 3 | 1806 | XS | 1 | Shaunak Pandit
Flight Operations | 2127 - Checklist Updates | accepted | 3 | 1802 | XS | 1 | Helen Kuni
Flight Operations | 2128 - Anakin Servo Replacement | accepted | 3 | 1802 | XS | 1 | Helen Kuni
LARAMID | 2129 – LARAMID Docking Frame Design | accepted | 3 | 1804 | M | 3 | Chung Choi |  | 100%
Collision Awareness | 213 – Perforce Visual Client (copy) | accepted | 3 | 1402 | S | 2 | Justin Yantus
LARAMID | 2130– LARAMID Arduino Mega Installation | accepted | 3 | 1804 | M | 3 | Chung Choi |  | 100%
LARAMID | 2131 – LARAMID Electromagnets Mounting System | accepted | 3 | 1803 | S | 2 | Chung Choi
LARAMID | 2132 – LARAMID Sled Build | accepted | 3 | 1804 | L | 5 | Chung Choi
General AFSL Lab | 2133 – Battery Soldering | accepted | 3 | 1802 | XS | 1 | Tushar Lakhanpal
General AFSL Lab | 2133 – Battery Soldering | accepted | 3 | 1802 | XS | 1 | Tushar Lakhanpal
HIPPO | 2134 – Compile a Procurement List | accepted | 3 | 1802 | XS | 1 | Gabriella Sciuchetti
TEMPEST | 2135 - TEMPEST LaTeX Software Installation | accepted | 3 | 1802 | XS | 1 | Zachary Rotter
TEMPEST | 2136 - TEMPEST LaTeX Software Installation | accepted | 3 | 1802 | XS | 1 | Laura Smit
TEMPEST | 2137 - TEMPEST LaTeX Software Installation | accepted | 3 | 1805 | XS | 1 | Kirby Taylor
TEMPEST | 2138 - TEMPEST LaTeX Software Installation | accepted | 3 | 1802 | XS | 1 | Bohao Zhu
TEMPEST | 2139 - TEMPEST CAD Modeling Integration | accepted | 3 | 1805 | S | 2 | Zachary Rotter
Collision Awareness | 214 – Software Developer Background Training (Algorithm and Back End) | accepted | 3 | 1404 | L | 5 | Justin Yantus |  |  | lower priority
TEMPEST | 2140 - TEMPEST February Purchasing | accepted | 3 | 1802 | XS | 1 | Laura Smit
TEMPEST | 2141 - TEMPEST February Meetings | accepted | 3 | 1802 | M | 3 | Zachary Rotter
TEMPEST | 2142 - TEMPEST February Meetings | accepted | 3 | 1802 | M | 3 | Laura Smit
TEMPEST | 2143 - TEMPEST February Meetings | accepted | 3 | 1802 | M | 3 | Kirby Taylor
TEMPEST | 2144 - TEMPEST February Meetings | accepted | 3 | 1802 | M | 3 | Bohao Zhu
TEMPEST | 2145 - TEMPEST Contact with Runway | accepted | 3 | 1803 | XS | 1 | Zachary Rotter
TEMPEST | 2146 - TEMPEST Administrative Lead Duties | accepted | 3 | 1802 | M | 3 | Zachary Rotter
TEMPEST | 2147 - TEMPEST START CCM+ Tutorials | accepted | 3 | 1802 | XS | 1 | Kirby Taylor
TEMPEST | 2148 - TEMPEST NX Tutorials | accepted | 3 | 1802 | XS | 1 | Zachary Rotter
TEMPEST | 2149 - TEMPEST Make Vision Board | dropped | #N/A | 1805 | S | 2 | Bohao Zhu
Collision Awareness | 215 – JCATI Quarterly Progress Report | accepted | 3 | 1402 | S | 2 | Christopher Lum
General AFSL Lab | 2150 - Soldering GPS unit | accepted | 3 | 1802 | XS | 1 | Yao Dou
TRAPIS2 | 2151 – TRAPIS Payload Familiarization (copy) | accepted | 3 | 1802 | L | 5 | Hannah Rotta
HIPPO | 2152 – HIPPO March Admin Duties | accepted | 3 | 1803 | M | 4 | Alex Bernard
HIPPO | 2153 – HIPPO March Budgeting Duties | accepted | 3 | 1803 | S | 2 | Christopher Lynch
HIPPO | 2154 – HIPPO PDR Preparation and Sensitivity Calculations | accepted | 3 | 1803 | L | 5 | Alex Bernard
HIPPO | 2155 – HIPPO PDR Preparation and Code Development | accepted | 3 | 1803 | L | 5 | Gabriella Sciuchetti
HIPPO | 2156 – HIPPO PDR Preparation and Code Development | accepted | 3 | 1803 | L | 5 | Christopher Lynch
HIPPO | 2157 – HIPPO PDR Preparation and 3D Printing Support | accepted | 3 | 1803 | M | 4 | Samden Sherpa
HIPPO | 2158 – Revise and Resubmit Night Waiver | accepted | 3 | 1803 | S | 2 | Alex Bernard
General AFSL Lab | 2159 – Lab Members Status Check | accepted | 3 | 1804 | M | 3 | Taehan Kook
Collision Awareness | 216 – JCATI Symposium Research Poster 1 | accepted | 3 | 1405 | M | 3 | Taylor Campbell | 1 |  | high priority
LARAMID | 2160 – Mini-Talon Build (Copy) | accepted | 3 | 1804 | M | 3 | Sheershak Agarwal
LARAMID | 2161 – Mission Planner Familiarzation (Copy) | accepted | 3 | 1803 | XS | 1 | Sheershak Agarwal
Flight Operations | 2162 – 3D Printing Course (Copy) | accepted | 3 | 1803 | XS | 1 | Sheershak Agarwal
HIPPO | 2163 – HIPPO GigE/Pi Interface | accepted | 3 | 1804 | XL | 8 | Gabriella Sciuchetti
HIPPO | 2164 – HIPPO GigE/Pi Interface | accepted | 3 | 1804 | XL | 8 | Christopher Lynch
HIPPO | 2165 – Create Mission Document for HIPPO Test Plan | accepted | 3 | 1803 | S | 2 | Alex Bernard
General AFSL Lab | 2166 - Fix the destroyed part on Anakin | accepted | 1 | 1803 | XS | 1 | Yao Dou
LARAMID | 2167 – LARAMID Electromagnets Mounting System (Copy) | accepted | 3 | 1803 | S | 2 | Blake Fletcher
LARAMID | 2168 – Sled CAD Design | accepted | 3 | 1803 | XS | 1 | Tao Jin
LARAMID | 2169 – LARAMID Docking Frame Design (Copy) | accepted | 3 | 1804 | M | 3 | Tao Jin |  | 80%
Collision Awareness | 217 – JCATI Symposium Research Poster 2 | accepted | 3 | 1405 | M | 3 | Al Creigh | 1
LARAMID | 2170 – LARAMID Arduino Mega Installation (Copy) | accepted | 3 | 1804 | S | 2 | Sheershak Agarwal |  | 20%
General AFSL Lab | 2171 - Aircraft Construction Standards Manual | accepted | 3 | 1803 | M | 3 | Helen Kuni
LARAMID | 2172 – LARAMID Electromagnets Mounting System (Copy) | accepted | 1 | 1803 | S | 2 | Tao Jin
HIPPO | 2173 – Update Conference Paper with Feasibility Information | accepted | 3 | 1805 | M | 3 | Alex Bernard
HIPPO | 2174 – Update Conference Paper with Analytical Information | accepted | 3 | 1805 | M | 3 | Gabriella Sciuchetti
HIPPO | 2175 – Update Conference Paper with Analytical Information | accepted | 3 | 1805 | M | 3 | Christopher Lynch
HIPPO | 2176 – Update Conference Paper with Electrical Information | accepted | 3 | 1805 | M | 3 | Samden Sherpa
Flight Operations | 2177 - Flight Test FUNRA | accepted | 3 | 1811 | L | 5 | Dylan Hoff
Flight Operations | 2178 - Flight Test FUNRA (copy) | dropped | #N/A | 1906 | L | 5 | -
General AFSL Lab | 2179 – AeroStand | accepted | 3 | 1803 | XS | 1 | Karine Chen |  | 100%
General AFSL Lab | 218 – Unit Testing for Current Sprint | accepted | 3 | 1511 | XS | 1 | Shida Xu |  | 100%
General AFSL Lab | 2180 – Perforce Visual Client (copy) | accepted | 3 | 1803 | S | 2 | Cory Cantey
Flight Operations | 2181 – Skywalker Fleet Maintenance | accepted | 3 | 1803 | XS | 1 | Helen Kuni
TRAPIS2 | 2182 – Geofence Familiarization | accepted | 3 | 1804 | M | 3 | Zachary Williams
Flight Operations | 2183 – Update Aircraft AFMs | dropped | #N/A | 1902 | S | 2 | -
Flight Operations | 2184 – Flight Ops Administration (1804) | accepted | 3 | 1804 | XL | 8 | Hannah Rotta
Flight Operations | 2185 – Flight Ops Administration (1805) | accepted | 3 | 1805 | XL | 8 | Hannah Rotta
TRAPIS2 | 2186 – TRAPIS2 Box CAD Drawings | accepted | 3 | 1803 | XS | 1 | Karine Chen |  | 100%
LiDAR | 2187 – Raspberry Pi Box CAD Drawings | accepted | 3 | 1803 | XS | 1 | Karine Chen |  | 100%
LARAMID | 2188 – LARAMID EM receiver part2 | accepted | 1 | 1805 | M | 3 | Chung Choi
LARAMID | 2189 – LARAMID EM Polarity Control | accepted | 1 | 1804 | M | 3 | Chung Choi
Collision Awareness | 219 – Unit Testing for Sprint 1403 | accepted | 3 | 1405 | M | 3 | Brian Chang |  |  | this will be done today
LARAMID | 2190 – LARAMID Magnetic Interference on UAV compass | accepted | 1 | 1805 | S | 2 | Chung Choi
LARAMID | 2191 – LARAMID EM receiver part2 (Copy) | accepted | 1 | 1805 | M | 3 | Tao Jin
LARAMID | 2192 – LARAMID EM Polarity Control (Copy) | accepted | 1 | 1804 | S | 2 | Sheershak Agarwal
LARAMID | 2193 – LARAMID Magnetic Interference on UAV compass (Copy) | accepted | 1 | 1805 | S | 2 | Cory Cantey
HIPPO | 2194 – HIPPO Mission Document and Planning | dropped | 1 | 1803 | S | 2 | Alex Bernard
HIPPO | 2195 – Build electrical equipment for HIPPO | accepted | 3 | 1804 | XL | 8 | Samden Sherpa
HIPPO | 2196 – HIPPO Ground Testing | accepted | 3 | 1805 | L | 5 | Alex Bernard
HIPPO | 2197 – HIPPO Ground Testing | accepted | 3 | 1805 | L | 5 | Christopher Lynch
HIPPO | 2198 – HIPPO Ground Testing | accepted | 3 | 1805 | L | 5 | Gabriella Sciuchetti
HIPPO | 2199 – HIPPO Ground Testing | accepted | 3 | 1805 | L | 5 | Samden Sherpa
General AFSL Lab | 220 – Unit Testing for Current Sprint | accepted | 3 | 1608 | S | 2 | Zach Caratao |  | 25%
HIPPO | 2200 – HIPPO Flight Testing | accepted | 1 | 1804 | L | 5 | Alex Bernard
HIPPO | 2201 – HIPPO Flight Testing | accepted | 1 | 1804 | L | 5 | Gabriella Sciuchetti
HIPPO | 2202 – HIPPO Flight Testing | accepted | 1 | 1804 | L | 5 | Christopher Lynch
HIPPO | 2203 – HIPPO Flight Testing | accepted | 1 | 1804 | L | 5 | Samden Sherpa
HIPPO | 2204 – HIPPO April Meetings | accepted | 1 | 1804 | M | 3 | Alex Bernard
HIPPO | 2205 – HIPPO April Meetings | accepted | 1 | 1804 | M | 3 | Gabriella Sciuchetti
HIPPO | 2206 – HIPPO April Meetings | accepted | 1 | 1804 | M | 3 | Christopher Lynch
HIPPO | 2207 – HIPPO April Meetings | accepted | 1 | 1804 | M | 3 | Samden Sherpa
HIPPO | 2208 – HIPPO April Admin Duties | accepted | 1 | 1804 | L | 6 | Alex Bernard
HIPPO | 2209 – HIPPO April Budgeting Duties | accepted | 1 | 1804 | M | 3 | Christopher Lynch
General AFSL Lab | 221 – Unit Testing for Current Sprint | accepted | 3 | 1511 | M | 3 | Marissa Reid |  | 100%
HIPPO | 2210 – Develop Night Testing Training Program | accepted | 1 | 1804 | S | 2 | Alex Bernard
HIPPO | 2211 – HIPPO March Meetings | accepted | 1 | 1803 | S | 2 | Alex Bernard
HIPPO | 2212 – HIPPO March Meetings | accepted | 1 | 1803 | S | 2 | Christopher Lynch
HIPPO | 2213 – HIPPO March Meetings | accepted | 1 | 1803 | S | 2 | Gabriella Sciuchetti
HIPPO | 2214 – HIPPO March Meetings | accepted | 1 | 1803 | S | 2 | Samden Sherpa
HIPPO | 2215 – Dummy Payload for HIPPO | accepted | 1 | 1804 | XS | 1 | Alex Bernard
TEMPEST | 2216 - TEMPEST March Meetings | accepted | 0 | 1803 | M | 3 | Zachary Rotter
TEMPEST | 2217 - TEMPEST March Meetings | accepted | 0 | 1803 | M | 3 | Laura Smit
TEMPEST | 2218 - TEMPEST March Meetings | accepted | 0 | 1803 | M | 3 | Kirby Taylor
TEMPEST | 2219 - TEMPEST March Meetings | accepted | 0 | 1803 | M | 3 | Bohao Zhu
General AFSL Lab | 222 – Unit Testing for Current Sprint | accepted | 3 | 1511 | M | 3 | Emil Caga-anan |  | 100%
TEMPEST | 2220 - TEMPEST Administrative Lead Duties | accepted | 0 | 1803 | M | 3 | Zachary Rotter
TEMPEST | 2221 - TEMPEST Secretary Lead Duties | accepted | 0 | 1803 | S | 2 | Bohao Zhu
TEMPEST | 2222 - TEMPEST March Purchasing | accepted | 0 | 1803 | S | 2 | Laura Smit
TEMPEST | 2223 - TEMPEST Mockup Board | accepted | 0 | 1805 | XS | 1 | Bohao Zhu
TEMPEST | 2224 - TEMPEST Start on SciTech Paper | dropped | 0 | 1805 | S | 2 | Zachary Rotter
TEMPEST | 2225 - TEMPEST Start on SciTech Paper | dropped | 0 | 1805 | S | 2 | Laura Smit
TEMPEST | 2226 - TEMPEST Start on SciTech Paper | dropped | 0 | 1805 | S | 2 | Kirby Taylor
TEMPEST | 2227 - TEMPEST Start on SciTech Paper | dropped | 0 | 1805 | S | 2 | Bohao Zhu
TRAPIS2 | 2228 – TRAPIS2 Conference Paper (MAVLINK Section) | accepted | 3 | 1806 | S | 2 | Tinnabhand Patana-anake
TRAPIS2 | 2229 – TRAPIS2 Conference Paper (MAVLINK Section) (Copy) | accepted | 3 | 1806 | S | 2 | Jacob Longhurst
General AFSL Lab | 223 – Unit Testing for Current Sprint | accepted | 3 | 1510 | S | 2 | Alec Bueing |  | 40%
Flight Operations | 2230 – Finwing Traveler Build (Robin) | accepted | 3 | 1902 | L | 5 | Christopher Lum
Flight Operations | 2231 – Finwing Traveler Build (Robin) (copy) | accepted | 3 | 1902 | L | 5 | Christopher Lum
Flight Operations | 2232 – Finwing Sabre Build (Papaya) | accepted | 1 | 1806 | L | 5 | Kelly Lee
Flight Operations | 2233 – Finwing Sabre Build (Papaya) (copy) | accepted | 1 | 1806 | L | 5 | Veen Oung
Flight Operations | 2234 – Flight Training Program – Multi-Rotor (Copy) | dropped | #N/A | 1903 | L | 5 | Helen Kuni
TRAPIS2 | 2234 – Program Transponder ICAO | accepted | 1 | 1804 | XS | 1 | Hannah Rotta
Flight Operations | 2235 – Leia Maintenance (copy) | accepted | 3 | 1808 | L | 5 | Sarah Chu
LiDAR | 2236 – Dummy Payload CAD Drawings | accepted | 3 | 1804 | XS | 1 | Karine Chen |  | 100%
LARAMID | 2237 – LARAMID Sled manual documentation | accepted | 3 | 1804 | S | 2 | Chung Choi
LARAMID | 2238 – LARAMID Project Vision Documentation | accepted | 3 | 1809 | M | 3 | Chung Choi
LARAMID | 2239 – LARAMID System Illustration Documentation | dropped | #N/A | 1809 | M | 3 | Chung Choi |  |  | Integrated in other document
General AFSL Lab | 224 – Unit Testing for Current Sprint | accepted | 3 | 1512 | M | 3 | Emil Caga-anan
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Hannah Rotta
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Hannah Rotta
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Hannah Rotta
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Hannah Rotta
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Hannah Rotta
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Hannah Rotta
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Hannah Rotta
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | M | 3 | Hannah Rotta
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Helen Kuni
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Helen Kuni
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Helen Kuni
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Helen Kuni
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Helen Kuni
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Helen Kuni
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Helen Kuni
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Ryan Grimes
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Ryan Grimes
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Ryan Grimes
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Ryan Grimes
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Ryan Grimes
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Ryan Grimes
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Ryan Grimes
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Joshua Brockschmidt
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Joshua Brockschmidt
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Joshua Brockschmidt
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Ravi Patel
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Ravi Patel
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Ravi Patel
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Ravi Patel
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | L | 5 | Nicholas Price
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | L | 5 | Nicholas Price
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Nicholas Price
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Kelly Lee
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | L | 5 | Taehan Kook
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | L | 5 | Taehan Kook
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Jacob Longhurst
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Zachary Williams
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Cory Cantey
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Tinnabhand Patana-anake
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Tinnabhand Patana-anake
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Tinnabhand Patana-anake
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Tadej Kosel
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | L | 5 | Tadej Kosel
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Grant Bringham
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | M | 3 | Dylan Hoff
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Mason Guiste
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Karine Chen
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | L | 5 | Blake Fletcher
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Vivian Hua
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Selina Lui
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Varith Hong
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Firn Tieanklin
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | M | 3 | Chung Choi
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Sita Manne
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Deepanshu Gupta
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Connor Kafka
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Connor Kafka
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Carter Kraus
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | L | 5 | Rick Huang
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Andrew Redd
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | M | 3 | Nikita Filippov
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Christopher Lum
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Shida Xu
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Matthew Lemelin
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Tom Pflibsen
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Andrew Park
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | S | 2 | Eric Wang
Flight Operations | 2240 – Flight Test 06/01/17 - 03/31/18 | accepted | 3 | 1804 | M | 3 | Michael Brady
Flight Operations | 2241 – Data Tech 06/01/17 - 03/31/18 | accepted | 3 | 1804 | XL | 8 | Helen Kuni
Flight Operations | 2241 – Data Tech 06/01/17 - 03/31/18 | accepted | 3 | 1804 | M | 3 | Taehan Kook
Flight Operations | 2242 – Data Tech 04/21/18 | accepted | 3 | 1804 | XS | 1 | Helen Kuni
Flight Operations | 2243 – Data Tech 04/28/18 | accepted | 3 | 1804 | XS | 1 | Kelly Lee
Flight Operations | 2243 – Data Tech 05/05/18 | accepted | 3 | 1805 | XS | 1 | Hannah Rotta
General AFSL Lab | 2244 – Sprint Metrics (copy) | accepted | 3 | 1804 | XL | 8 | Taehan Kook
LARAMID | 2245 – LARAMID Sled Build (Copy) | accepted | 3 | 1804 | L | 5 | Taehan Kook
LARAMID | 2246 – LARAMID Sled build (Copy) | accepted | 3 | 1804 | L | 5 | Tao Jin
General AFSL Lab | 2247 – Solder Batteries | accepted | 3 | 1804 | XS | 1 | Rostyk Svitelskyi
General AFSL Lab | 2247 – Solder Batteries (copy) | accepted | 3 | 1804 | XS | 1 | Nicholas Price
Flight Operations | 2248 – Peach Battery Wire Replacement | accepted | 3 | 1804 | XS | 1 | Helen Kuni
Flight Operations | 2249 – FPV Transmitter Repair | accepted | 3 | 1804 | XS | 1 | Helen Kuni
Collision Awareness | 225 – Unit Testing for Sprint 1403 | accepted | 3 | 1406 | M | 3 | Justin Yantus
General AFSL Lab | 2250 – Security Audit and Hardening | accepted | 3 | 1902 | M | 3 | Joshua Brockschmidt
General AFSL Lab | 2251 – Security Audit and Hardening (Copy) | accepted | 3 | 1805 | XS | 1 | Hannah Rotta
LiDAR | 2252 – Stand-Alone GPS Integration, Part 2 | accepted | 3 | 1806 | XS | 1 | Sai Ranganathan
LiDAR | 2253 – Stand-Alone GPS Integration, Part 2 (Copy) | accepted | 3 | 1805 | M | 3 | Joshua Brockschmidt
General AFSL Lab | 2254 – Create Log for Static IPs | accepted | 3 | 1804 | XS | 1 | Joshua Brockschmidt
Flight Operations | 2255 – Data Tech 05/12/18 | accepted | 3 | 1805 | XS | 1 | Hannah Rotta
TRAPIS2 | 2255 - WSTR Waypoint Navigation Development | accepted | 3 | 1804 | L | 5 | Ravi Patel |  | 100% | WaypointNavigation works, see US_1910 for WSTR
Flight Operations | 2256 – Data Tech 05/19/18 | accepted | 3 | 1805 | XS | 1 | Helen Kuni
TRAPIS2 | 2256 - TRAPIS2 Documentation | accepted | 3 | 1804 | S | 2 | Ravi Patel
Flight Operations | 2257 – Data Tech 05/26/18 | accepted | 3 | 1805 | XS | 1 | Helen Kuni
TRAPIS2 | 2257 - JCATI Symposium Preparation | accepted | 3 | 1804 | XS | 1 | Ravi Patel
TRAPIS2 | 2258 - TRAPIS2 Conference Paper (Ardupilot Section) | accepted | 3 | 1811 | L | 5 | Ravi Patel
TRAPIS2 | 2259 - TRAPIS2 Software Clean-Up | accepted | 3 | 1805 | S | 2 | Ravi Patel
Collision Awareness | 226 – Unit Testing for Sprint 1403 | accepted | 3 | 1405 | M | 3 | Ryan Valach |  |  | get this checked in with Chris today or tomorrow
TRAPIS2 | 2260 - JCATI Symposium Attendance | accepted | 3 | 1804 | S | 2 | Ravi Patel |  |  | twas cool
TRAPIS2 | 2261 - JCATI Symposium Attendance | accepted | 1 | 1804 | S | 2 | Alex Banh
General AFSL Lab | 2262 - Standardize Mission Planners | dropped | #N/A | 1902 | S | 2 | -
General AFSL Lab | 2263 - Standardize Simulation and Build Process | dropped | #N/A | 1902 | M | 3 | Ravi Patel
General AFSL Lab | 2264 - Create Data Log Script | dropped | #N/A | 1902 | S | 2 | -
LARAMID | 2265 – LARAMID System integration for Samwise | accepted | 3 | 1805 | M | 3 | Chung Choi
LARAMID | 2266 – LARAMID System integration for Samwise (Copy) | accepted | 3 | 1805 | M | 3 | Cory Cantey
General AFSL Lab | 2266 – Solar Plane Trade Study | accepted | 3 | 1806 | M | 3 | Nicholas Price
Collision Awareness | 227 – Unit Testing for Sprint 1402 | accepted | 3 | 1402 | M | 3 | Madison Peck |  |  | 0%
HIPPO | 2270 – HIPPO CDR Preparation | accepted | 1 | 1804 | M | 3 | Alex Bernard
HIPPO | 2271 – HIPPO CDR Preparation | accepted | 1 | 1804 | M | 3 | Christopher Lynch
HIPPO | 2272 – HIPPO CDR Preparation | accepted | 1 | 1804 | M | 3 | Gabriella Sciuchetti
HIPPO | 2273 – HIPPO CDR Preparation | accepted | 1 | 1804 | M | 3 | Samden Sherpa
Flight Operations | 2274 - Plum Battery Maintenace | accepted | 3 | 1804 | XS | 1 | Rostyk Svitelskyi
LARAMID | 2275 – LARAMID 3D-Print Docking Frame | accepted | 3 | 1805 | S | 2 | Tao Jin
General AFSL Lab | 2276 – Diagnose Monitors for AFSL04 | accepted | 3 | 1804 | XS | 1 | Joshua Brockschmidt
TRAPIS2 | 2277 – Develop Method for Forwarding LAMS Transmission | accepted | 3 | 1805 | S | 2 | Joshua Brockschmidt
General AFSL Lab | 2278 – Install PhoenixRC on Lab Computers | accepted | 3 | 1804 | S | 2 | Mason Guiste
TRAPIS2 | 2279 – Clean up custom ardupilot code | accepted | 3 | 1805 | M | 3 | Connor Kafka
General AFSL Lab | 228 – Unit Testing for Current Sprint | accepted | 3 | 1512 | M | 3 | Shida Xu
TRAPIS2 | 2280 – Fix trapis payload | accepted | 3 | 1804 | M | 3 | Connor Kafka
Visual Anchoring | 2281 - Visual Anchoring Thesis | accepted | 3 | 1805 | XL | 8 | Ryan Grimes
Visual Anchoring | 2282 - Finalize Vision System | accepted | 3 | 1804 | XL | 8 | Ryan Grimes
TEMPEST | 2283 - TEMPEST April Meetings | accepted | 0 | 1804 | M | 3 | Zachary Rotter
TEMPEST | 2284 - TEMPEST April Meetings | accepted | 0 | 1804 | M | 3 | Laura Smit
TEMPEST | 2285 - TEMPEST April Meetings | accepted | 0 | 1804 | M | 3 | Kirby Taylor
TEMPEST | 2286 - TEMPEST April Meetings | accepted | 0 | 1804 | M | 3 | Bohao Zhu
TEMPEST | 2287 - TEMPEST Administrative Lead Duties | accepted | 0 | 1804 | M | 3 | Zachary Rotter
TEMPEST | 2288 - TEMPEST Purchasing / Budgeting | accepted | 0 | 1804 | M | 3 | Laura Smit
TEMPEST | 2289 - TEMPEST CDR Preparation | accepted | 0 | 1804 | S | 2 | Zachary Rotter
General AFSL Lab | 229 – Unit Testing for Current Sprint | accepted | 3 | 1602 | M | 3 | Anupam Gupta |  | 50%
TEMPEST | 2290 - TEMPEST CDR Preparation | accepted | 0 | 1804 | S | 2 | Laura Smit
TEMPEST | 2291 - TEMPEST CDR Preparation | accepted | 0 | 1804 | S | 2 | Kirby Taylor
TEMPEST | 2292 - TEMPEST CDR Preparation | accepted | 0 | 1804 | S | 2 | Bohao Zhu
TEMPEST | 2293 - TEMPEST CDR Presentation | accepted | 0 | 1804 | XS | 1 | Kirby Taylor
TEMPEST | 2294 - TEMPEST CDR Presentation | accepted | 0 | 1804 | XS | 1 | Bohao Zhu
TEMPEST | 2295 - TEMPEST Truck Test Prep | accepted | 0 | 1804 | M | 3 | Zachary Rotter
TEMPEST | 2296 - TEMPEST Truck Test Prep | accepted | 0 | 1804 | M | 3 | Laura Smit
TEMPEST | 2297 - TEMPEST Truck Test Prep | accepted | 0 | 1804 | M | 3 | Kirby Taylor
TEMPEST | 2298 - TEMPEST Truck Test Prep | accepted | 0 | 1804 | M | 3 | Bohao Zhu
TEMPEST | 2299 - TEMPEST Truck Test | accepted | 0 | 1804 | M | 3 | Zachary Rotter
General AFSL Lab | 230 – Unit Testing for Current Sprint | accepted | 3 | 1609 | S | 2 | Zach Caratao |  | 50%
TEMPEST | 2300 - TEMPEST Truck Test | accepted | 0 | 1804 | M | 3 | Laura Smit
TEMPEST | 2301 - TEMPEST Truck Test | accepted | 0 | 1804 | M | 3 | Kirby Taylor
TEMPEST | 2303 - TEMPEST Truck Test | accepted | 0 | 1804 | M | 3 | Bohao Zhu
TEMPEST | 2304 - TEMPEST Truck Test Data Analysis | accepted | 0 | 1804 | S | 2 | Laura Smit
TEMPEST | 2305 - TEMPEST Truck Test Data Compiling | accepted | 0 | 1804 | XS | 1 | Zachary Rotter
TEMPEST | 2306 - TEMPEST Drogue Ground Stability Test | accepted | 0 | 1804 | S | 2 | Zachary Rotter
TEMPEST | 2307 - TEMPEST Drogue Ground Stability Test | accepted | 0 | 1804 | S | 2 | Kirby Taylor
TEMPEST | 2308 - TEMPEST Winch Final Design | accepted | 0 | 1804 | M | 3 | Zachary Rotter
TEMPEST | 2309 - TEMPEST Winch CAD | accepted | 0 | 1804 | XS | 1 | Zachary Rotter
General AFSL Lab | 231 – Unit Testing for Current Sprint | accepted | 3 | 1712 | M | 3 | Sita Manne
TEMPEST | 2310 - TEMPEST Lab Inspection Prep | accepted | 0 | 1804 | XS | 1 | Zachary Rotter
TEMPEST | 2311 - TEMPEST May Meetings | accepted | 0 | 1805 | M | 3 | Zachary Rotter
TEMPEST | 2312 - TEMPEST May Meetings | accepted | 0 | 1805 | M | 3 | Laura Smit
TEMPEST | 2313 - TEMPEST May Meetings | accepted | 0 | 1805 | M | 3 | Kirby Taylor
TEMPEST | 2314 - TEMPEST May Meetings | accepted | 0 | 1805 | M | 3 | Bohao Zhu
TEMPEST | 2315 - TEMPEST Administrative Lead Duties | accepted | 0 | 1805 | M | 3 | Zachary Rotter
TEMPEST | 2316 - TEMPEST Purchasing / Budgeting | accepted | 0 | 1805 | M | 3 | Laura Smit
TEMPEST | 2317 - TEMPEST FDR Preparation | accepted | 0 | 1805 | M | 3 | Zachary Rotter
TEMPEST | 2318 - TEMPEST FDR Preparation | accepted | 0 | 1805 | M | 3 | Laura Smit
TEMPEST | 2319 - TEMPEST FDR Preparation | accepted | 0 | 1805 | M | 3 | Kirby Taylor
Collision Awareness | 232 – Test Case for Multiple Entities | accepted | 3 | 1403 | L | 5 | Taylor Campbell | yes |  | high priority
TEMPEST | 2320 - TEMPEST FDR Preparation | accepted | 0 | 1805 | M | 3 | Bohao Zhu
TEMPEST | 2321 - TEMPEST FDR Presentation | accepted | 0 | 1806 | S | 2 | Zachary Rotter
TEMPEST | 2322 - TEMPEST FDR Presentation | accepted | 0 | 1806 | XS | 1 | Laura Smit
TEMPEST | 2323 - TEMPEST FDR Presentation | accepted | 0 | 1806 | XS | 1 | Kirby Taylor
TEMPEST | 2324 - TEMPEST FDR Presentation | accepted | 0 | 1806 | XS | 1 | Bohao Zhu
TEMPEST | 2325 - TEMPEST Write Sections of Department Paper | accepted | 0 | 1805 | XL | 8 | Zachary Rotter
TEMPEST | 2326 - TEMPEST Write Sections of Department Paper | accepted | 0 | 1805 | XL | 8 | Laura Smit
TEMPEST | 2327 - TEMPEST Write Sections of Department Paper | accepted | 0 | 1805 | XL | 8 | Kirby Taylor
TEMPEST | 2328 - TEMPEST Write Sections of Department Paper | accepted | 0 | 1805 | XL | 8 | Bohao Zhu
TEMPEST | 2329 - TEMPEST Edit Department Paper | dropped | 0 | 1806 | M | 3 | Zachary Rotter
Collision Awareness | 233 – Sprint 1403 Simulation Project | accepted | 3 | 1403 | XL | 8 | Christopher Lum | yes
TEMPEST | 2330 - TEMPEST Edit Department Paper | dropped | 0 | 1806 | M | 3 | Laura Smit
TEMPEST | 2331 - TEMPEST Edit Department Paper | dropped | 0 | 1806 | M | 3 | Kirby Taylor
TEMPEST | 2332 - TEMPEST Edit Department Paper | dropped | 0 | 1806 | M | 3 | Bohao Zhu
TEMPEST | 2333 - TEMPEST Final Line Selection | dropped | 0 | 1805 | XS | 1 | Laura Smit
TEMPEST | 2334 - TEMPEST Design Line Spooling Control | dropped | 0 | 1805 | S | 2 | Zachary Rotter
TEMPEST | 2335 - TEMPEST Full System FEA | accepted | 0 | 1805 | M | 3 | Zachary Rotter
TEMPEST | 2336 - TEMPEST Spool/Motor Mount Manufacturing | accepted | 0 | 1805 | L | 5 | Zachary Rotter
TEMPEST | 2337 - TEMPEST Coordinate Plane Body Signal Penetration Test | accepted | 0 | 1805 | XS | 1 | Zachary Rotter
TEMPEST | 2338 - TEMPEST Organize Final Flight Test | dropped | 0 | 1805 | M | 3 | Zachary Rotter
TEMPEST | 2339 - TEMPEST Systems Integration | accepted | 0 | 1805 | XS | 1 | Zachary Rotter
Collision Awareness | 234 – Forward State Estimator Free Flight Simulation | accepted | 3 | 1403 | M | 3 | Kevin Ueunten
TEMPEST | 2340 - TEMPEST Final CAD Model | accepted | 0 | 1805 | L | 5 | Laura Smit
TEMPEST | 2341 - TEMPEST Facilitate Body Thickness Reduction | accepted | 0 | 1805 | S | 2 | Zachary Rotter
TEMPEST | 2342 - TEMPEST Facilitate Nose/Tail Cone Printing | accepted | 0 | 1805 | S | 2 | Zachary Rotter
TEMPEST | 2343 - TEMPEST C-Channel Modifications | dropped | 0 | 1805 | S | 2 | Laura Smit
TEMPEST | 2344 - TEMPEST Board Manufacturing | accepted | 0 | 1805 | M | 3 | Laura Smit
TEMPEST | 2345 - TEMPEST Systems Integration | accepted | 0 | 1805 | S | 2 | Laura Smit
TEMPEST | 2346 - TEMPEST Final CFD Analysis | accepted | 0 | 1805 | L | 5 | Kirby Taylor
TEMPEST | 2347 - TEMPEST Final Plane Attachment Design | accepted | 0 | 1805 | M | 3 | Kirby Taylor
TEMPEST | 2348 - TEMPEST Build Air Routing System | accepted | 0 | 1805 | S | 2 | Kirby Taylor
TEMPEST | 2349 - TEMPEST Systems Integration | accepted | 0 | 1805 | S | 2 | Kirby Taylor
Collision Awareness | 235 – Forward State Estimator Flight Path Simulation | accepted | 3 | 1403 | M | 3 | Bao Le | yes
TEMPEST | 2350 - TEMPEST GPS Integration | accepted | 0 | 1805 | XS | 1 | Bohao Zhu
TEMPEST | 2351 - TEMPEST Build Complete Sensor Circuit | accepted | 0 | 1805 | L | 5 | Bohao Zhu
TEMPEST | 2352 - TEMPEST Build Complete Winch Control Circuit | accepted | 0 | 1805 | S | 2 | Bohao Zhu
TEMPEST | 2353 - TEMPEST Write Software to Read Sensor Data | accepted | 0 | 1805 | XL | 8 | Bohao Zhu
TEMPEST | 2354 - TEMPEST Plane Body Signal Penetration Test | dropped | 0 | 1805 | S | 2 | Bohao Zhu
TEMPEST | 2355 - TEMPEST Systems Integration | accepted | 0 | 1805 | S | 2 | Bohao Zhu
TEMPEST | 2356 - TEMPEST Full System Ground Test | accepted | 0 | 1805 | L | 5 | Zachary Rotter
TEMPEST | 2357 - TEMPEST Full System Ground Test | accepted | 0 | 1805 | M | 3 | Laura Smit
TEMPEST | 2358 - TEMPEST Full System Ground Test | accepted | 0 | 1805 | L | 5 | Kirby Taylor
TEMPEST | 2359 - TEMPEST Full System Ground Test | accepted | 0 | 1805 | S | 2 | Bohao Zhu
Collision Awareness | 236 – FlightPathLLA Creation | accepted | 3 | 1403 | S | 2 | Christopher Lum
TEMPEST | 2360 - TEMPEST Final Flight Test | dropped | 0 | 1805 | M | 3 | Zachary Rotter
TEMPEST | 2361 - TEMPEST Final Flight Test | dropped | 0 | 1805 | M | 3 | Laura Smit
TEMPEST | 2362 - TEMPEST Final Flight Test | dropped | 0 | 1805 | M | 3 | Kirby Taylor
TEMPEST | 2363 - TEMPEST Final Flight Test | dropped | 0 | 1805 | M | 3 | Bohao Zhu
TEMPEST | 2364 - TEMPEST Secretary Lead Duties | accepted | 0 | 1804 | XS | 1 | Bohao Zhu
TEMPEST | 2365 - TEMPEST Secretary Lead Duties | accepted | 0 | 1805 | XS | 1 | Bohao Zhu
General AFSL Lab | 2367 - Add pin on magnetic battery | accepted | 2 | 1804 | XS | 1 | Yao Dou
Mapping | 2368 - Add close button and improve open button on the interface | accepted | 2 | 1804 | S | 2 | Yao Dou
Mapping | 2369 - Improve Mapping graph | accepted | 2 | 1804 | S | 2 | Yao Dou
Collision Awareness | 237 – FlightPathLLA Visualizer | accepted | 3 | 1403 | S | 2 | Christopher Lum
TRAPIS2 | 2370 – TRAPIS Payload Reliability | accepted | 2 | 1805 | M | 3 | Ryan Grimes
TRAPIS2 | 2371 – TRAPIS Payload Reliability (copy) | accepted | 2 | 1805 | L | 5 | Helen Kuni
TRAPIS2 | 2372 – TRAPIS Payload Reliability (copy) | accepted | 2 | 1805 | L | 5 | Hannah Rotta
TRAPIS2 | 2373 – TRAPIS Payload Reliability (copy) | accepted | 2 | 1805 | XS | 1 | Cory Cantey
Flight Operations | 2374 – Flight Test Attendance 04/21/18 | accepted | 2 | 1804 | S | 2 | Hannah Rotta
Flight Operations | 2374 – Flight Test Attendance 04/21/18 | accepted | 2 | 1804 | S | 2 | Cory Cantey
Flight Operations | 2374 – Flight Test Attendance 04/21/18 | accepted | 2 | 1804 | S | 2 | Taehan Kook
Flight Operations | 2374 – Flight Test Attendance 04/21/18 | accepted | 2 | 1804 | S | 2 | Joshua Brockschmidt
Flight Operations | 2374 – Flight Test Attendance 04/21/18 | accepted | 2 | 1804 | S | 2 | Helen Kuni
Flight Operations | 2374 – Flight Test Attendance 04/21/18 | accepted | 2 | 1804 | S | 2 | Rostyk Svitelskyi
Flight Operations | 2374 – Flight Test Attendance 04/21/18 | accepted | 2 | 1804 | S | 2 | Ravi Patel
Flight Operations | 2374 – Flight Test Attendance 04/28/18 | accepted | 2 | 1804 | S | 2 | Hannah Rotta
Flight Operations | 2374 – Flight Test Attendance 04/28/18 | accepted | 2 | 1804 | S | 2 | Helen Kuni
Flight Operations | 2374 – Flight Test Attendance 04/28/18 | accepted | 2 | 1804 | S | 2 | Kelly Lee
Flight Operations | 2374 – Flight Test Attendance 04/28/18 | accepted | 3 | 1804 | S | 2 | Tinnabhand Patana-anake
Flight Operations | 2374 – Flight Test Attendance 04/28/18 | accepted | 2 | 1804 | S | 2 | Ryan Grimes
Flight Operations | 2374 – Flight Test Attendance 04/28/18 | accepted | 2 | 1804 | S | 2 | Rostyk Svitelskyi
Flight Operations | 2374 – Flight Test Attendance 04/28/18 | accepted | 2 | 1804 | S | 2 | Veen Oung
Flight Operations | 2375 – Aircraft CG Labeling | accepted | 2 | 1804 | XS | 1 | Frederick Chandra
Flight Operations | 2376 – Telemetry and Transmitter ID Labeling | accepted | 2 | 1804 | XS | 1 | Frederick Chandra
TRAPIS2 | 2377 – Map Geofence to Transmitters | dropped | #N/A | 1812 | XS | 1 | Frederick Chandra
TRAPIS2 | 2378 – TRAPIS2 Conference Paper | accepted | 2 | 1806 | M | 3 | Hannah Rotta
TRAPIS2 | 2378 – TRAPIS2 Conference Paper (copy) | accepted | 3 | 1811 | XL | 8 | Helen Kuni
Collision Awareness | 238 – Sprint 1403 Unity Visualizer (Position 1) | accepted | 3 | 1403 | L | 5 | Madison Peck
HIPPO | 2380 – HIPPO May Admin Duties | accepted | 3 | 1805 | L | 5 | Alex Bernard
HIPPO | 2381 – HIPPO May Meetings | accepted | 3 | 1805 | M | 3 | Alex Bernard
HIPPO | 2382 – HIPPO May Meetings | accepted | 3 | 1805 | M | 3 | Gabriella Sciuchetti
HIPPO | 2383 – HIPPO May Meetings | accepted | 3 | 1805 | M | 3 | Christopher Lynch
HIPPO | 2384 – HIPPO May Meetings | accepted | 3 | 1805 | M | 3 | Samden Sherpa
HIPPO | 2385 – HIPPO May Budgeting Duties | accepted | 3 | 1805 | S | 2 | Christopher Lynch
HIPPO | 2386 – HIPPO FDR Preparation | accepted | 3 | 1805 | L | 5 | Alex Bernard
HIPPO | 2387 – HIPPO FDR Preparation | accepted | 3 | 1805 | M | 3 | Christopher Lynch
HIPPO | 2388 – HIPPO FDR Preparation | accepted | 3 | 1805 | L | 5 | Gabriella Sciuchetti
HIPPO | 2389 – HIPPO FDR Preparation | accepted | 3 | 1805 | S | 2 | Samden Sherpa
Collision Awareness | 239 – Sprint 1403 Unity Visualizer (Position 2) | accepted | 3 | 1403 | M | 3 | Richard Fukutome
HIPPO | 2390 – HIPPO Additional Flight Test Support | accepted | 3 | 1805 | L | 5 | Alex Bernard
HIPPO | 2391 – HIPPO Additional Flight Test Support | accepted | 3 | 1805 | L | 5 | Christopher Lynch
HIPPO | 2392 – HIPPO Additional Flight Test Support | accepted | 3 | 1805 | L | 5 | Gabriella Sciuchetti
HIPPO | 2393 – HIPPO Additional Flight Test Support | accepted | 3 | 1805 | L | 5 | Samden Sherpa
HIPPO | 2394 – HIPPO Final Paper Completion | accepted | 3 | 1805 | XL | 8 | Alex Bernard
HIPPO | 2395 – HIPPO Final Paper Completion | accepted | 3 | 1805 | L | 5 | Christopher Lynch
HIPPO | 2396 – HIPPO Final Paper Completion | accepted | 3 | 1805 | XL | 8 | Gabriella Sciuchetti
HIPPO | 2397 – HIPPO Final Paper Completion | accepted | 3 | 1805 | S | 2 | Samden Sherpa
HIPPO | 2398 – HIPPO Data/Image Analysis | accepted | 3 | 1805 | L | 5 | Gabriella Sciuchetti
HIPPO | 2399 – HIPPO Data/Image Analysis & Documentation | accepted | 3 | 1805 | M | 3 | Christopher Lynch
Collision Awareness | 240 – Insitu Trip Logistics | accepted | 3 | 1403 | M | 3 | Christopher Lum
HIPPO | 2400 – HIPPO April/May Weekly Reports | accepted | 3 | 1805 | XS | 1 | Alex Bernard
HIPPO | 2401 – HIPPO April/May Weekly Reports | accepted | 3 | 1805 | XS | 1 | Christopher Lynch
HIPPO | 2402 – HIPPO April/May Weekly Reports | accepted | 3 | 1805 | XS | 1 | Gabriella Sciuchetti
HIPPO | 2403 – HIPPO April/May Weekly Reports | accepted | 3 | 1805 | XS | 1 | Samden Sherpa
LARAMID | 2404 – GUI for controlling multiple UAV | dropped | #N/A | 1806 | XL | 8 | Tinnabhand Patana-anake
LARAMID | 2405 – LARAMID Electromagnet Optimization Testing | accepted | 3 | 1805 | M | 3 | Chung Choi
LARAMID | 2406 – LARAMID Electromagnet Receiver Mounting | accepted | 3 | 1806 | L | 5 | Chung Choi
LARAMID | 2407 – Mini-Talon Build part 2 (Merry) | accepted | 3 | 1809 | L | 5 | Chung Choi |  |  | waiting for flight test
LARAMID | 2408 – LARAMID Samwise Dummy Payload Testing | accepted | 3 | 1807 | M | 3 | Cory Cantey
LARAMID | 2409 – LARAMID Samwise Dummy Payload Testing (Copy) | accepted | 3 | 1809 | M | 3 | Chung Choi
Collision Awareness | 241 – Gaussian Random Number Generator | accepted | 3 | 1405 | L | 5 | Henry Qin | 1 |  | 100%
LARAMID | 2410 - Mini-Talon Build part 2 (Merry) (copy) | accepted | 3 | 1807 | L | 5 | Taehan Kook
General AFSL Lab | 2411 - Track Components | accepted | 2 | 1806 | L | 5 | Taehan Kook
General AFSL Lab | 2412 - Transmitter Organizing | accepted | 2 | 1805 | XS | 1 | Taehan Kook
Flight Operations | 2413 - CONDOR To-Do items | accepted | 2 | 1805 | M | 3 | Taehan Kook
Flight Operations | 2414 – Flight Test Attendance 05/01/18 | accepted | 2 | 1805 | S | 2 | Ryan Grimes
Flight Operations | 2414 – Flight Test Attendance 05/01/18 | accepted | 2 | 1805 | S | 2 | Cory Cantey
Flight Operations | 2414 – Flight Test Attendance 05/01/18 | accepted | 3 | 1805 | S | 2 | Zachary Williams
Flight Operations | 2414 – Flight Test Attendance 05/01/18 | accepted | 3 | 1805 | S | 2 | Dylan Hoff
Flight Operations | 2414 – Flight Test Attendance 05/01/18 | accepted | 2 | 1805 | S | 2 | Hannah Rotta
Flight Operations | 2414 – Flight Test Attendance 05/03/18 | accepted | 2 | 1805 | S | 2 | Taehan Kook
Flight Operations | 2414 – Flight Test Attendance 05/03/18 | accepted | 3 | 1805 | S | 2 | Nicholas Price
Flight Operations | 2414 – Flight Test Attendance 05/03/18 | accepted | 2 | 1805 | S | 2 | Helen Kuni
Flight Operations | 2414 – Flight Test Attendance 05/03/18 | accepted | 2 | 1805 | S | 2 | Hannah Rotta
Flight Operations | 2414 – Flight Test Attendance 05/03/18 | accepted | 2 | 1805 | S | 2 | Cory Cantey
Flight Operations | 2414 – Flight Test Attendance 05/05/18 | accepted | 2 | 1805 | S | 2 | Hannah Rotta
Flight Operations | 2414 – Flight Test Attendance 05/05/18 | accepted | 3 | 1805 | S | 2 | Rostyk Svitelskyi
Flight Operations | 2414 – Flight Test Attendance 05/05/18 | accepted | 2 | 1805 | S | 2 | Joshua Brockschmidt
Flight Operations | 2414 – Flight Test Attendance 05/05/18 | accepted | 2 | 1805 | S | 2 | Tinnabhand Patana-anake
Flight Operations | 2414 – Flight Test Attendance 05/05/18 | accepted | 3 | 1805 | S | 2 | Ravi Patel
Flight Operations | 2414 – Flight Test Attendance 05/05/18 | accepted | 2 | 1805 | S | 2 | Ryan Grimes
Flight Operations | 2414 – Flight Test Attendance 05/05/18 | accepted | 2 | 1805 | S | 2 | Helen Kuni
Flight Operations | 2415 – Switch Repair | dropped | #N/A | 1902 | XS | 1 | -
Flight Operations | 2416 – Secure Finwing Canopies | accepted | 3 | 1807 | XS | 1 | Annyn Howle
Flight Operations | 2417 – Make Finwing Spares Box | accepted | 3 | 1807 | XS | 1 | Sarah Chu
Flight Operations | 2418 – Update Aircraft Parameters for Geofence | dropped | #N/A | 1902 | XS | 1 | -
Flight Operations | 2419 – FPV Charging Cable | dropped | #N/A | 1808 | XS | 1 | Rostyk Svitelskyi
Collision Awareness | 242 – ADS-B Literature Review and Assessment | accepted | 3 | 1403 | M | 3 | Al Creigh | yes
Flight Operations | 2420 – XT60 Extension Cable | accepted | 3 | 1805 | XS | 1 | Tinnabhand Patana-anake
Flight Operations | 2421 – Checklist Updates | accepted | 3 | 1806 | XS | 1 | Helen Kuni
Flight Operations | 2422 – Increase Wingnut Visibility | accepted | 3 | 1806 | XS | 1 | Taehan Kook
Flight Operations | 2423 – Standardize Construction & Maintenance Logs | dropped | #N/A | 1902 | XS | 1 | -
Flight Operations | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Christopher Lum
Flight Operations | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Connor Kafka
Flight Operations | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Hannah Rotta
Flight Operations | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Ryan Grimes
Flight Operations | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Taehan Kook
Flight Operations | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Helen Kuni
Flight Operations | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Tinnabhand Patana-anake
Flight Operations | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Ravi Patel
Flight Operations | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Joshua Brockschmidt
HIPPO | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Alex Bernard
HIPPO | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Gabriella Sciuchetti
HIPPO | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Ang Samden Sherpa
Flight Operations | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Rostyk Svitelskyi
Flight Operations | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Kelly Lee
Flight Operations | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Cory Cantey
Flight Operations | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Veen Oung
HIPPO | 2424 – Night Training | accepted | 3 | 1805 | XS | 1 | Christopher Lynch
AMFAV | 2425 – Mapping Initialization Startup | accepted | 3 | 1806 | XS | 1 | Bryson Bruno
AMFAV | 2426 – Mapping Excursion 1 | dropped | #N/A | 1812 | M | 3 | TBD
AMFAV | 2427 – Familiarize with Pix4D | dropped | #N/A | 1906 | M | 3 | TBD
AMFAV | 2428 – Mapping Initialization Startup (Copy) | accepted | 3 | 1806 | M | 3 | Bryson Bruno
AMFAV | 2429 – Mapping Excursion 1 (Copy) | accepted | 3 | 1806 | M | 3 | Bryson Bruno
Collision Awareness | 243 – Sprint 1403 Administration | accepted | 3 | 1403 | M | 3 | Christopher Lum
AMFAV | 2430 – Familiarize with Pix4D (Copy) | accepted | 3 | 1806 | M | 3 | Bryson Bruno
General AFSL Lab | 2431 – SFTE NW Symposium Preparation | accepted | 3 | 1805 | M | 3 | Karine Chen |  | 100%
General AFSL Lab | 2432 – SFTE NW Symposium Attendance | accepted | 3 | 1806 | S | 2 | Karine Chen |  | 100%
General AFSL Lab | 2433 – SFTE NW Symposium Preparation (copy) | accepted | 3 | 1806 | M | 3 | Hannah Rotta
General AFSL Lab | 2434 – SFTE NW Symposium Attendance (copy) | accepted | 3 | 1806 | S | 2 | Hannah Rotta
General AFSL Lab | 2435 – AeroStand Copies | accepted | 3 | 1805 | S | 2 | Karine Chen |  | 100%
Flight Operations | 2437 – Rebuild TEDD | accepted | 3 | 1806 | XL | 8 | Taehan Kook
Flight Operations | 2438 – Excelsior Maintenance | accepted | 3 | 1806 | M | 3 | Taehan Kook
Team India | 2439 – Assist Team India with LiDAR Project | accepted | 3 | 1805 | S | 2 | Joshua Brockschmidt
Collision Awareness | 244 – Sprint 1403 Simulation Project Helper 1 | accepted | 3 | 1403 | M | 3 | Brian Chang
Team India | 2440 – Assist Team India with LiDAR Project (COPY) | accepted | 3 | 1805 | M | 3 | Travis Clement
HIPPO | 2441 – HIPPO Payload Check | dropped | #N/A | 1808 | S | 2 | Joshua Brockschmidt
HIPPO | 2442 – HIPPO Payload Check (COPY) | dropped | #N/A | 1808 | S | 2 | Mason Guiste
General AFSL Lab | 2443 – Reattach Wheel to Lab Chair | accepted | 3 | 1805 | XS | 1 | Joshua Brockschmidt
General AFSL Lab | 2444 - Put sticker on the lab box | accepted | 3 | 1805 | XS | 1 | Yao Dou
Flight Operations | 2445 - Format maintenance files of all drones | accepted | 3 | 1805 | S | 2 | Yao Dou
LARAMID | 2446 – LARAMID Samwise Dummy Payload Testing (Copy) | accepted | 3 | 1808 | XS | 1 | Taehan Kook
Flight Operations | 2447 – Glue/Tape Aircraft Stands | accepted | 3 | 1807 | XS | 1 | Annyn Howle
Flight Operations | 2448 – Repair FPV Transmitter | dropped | #N/A | 1812 | S | 2 | Grant Bringham
Flight Operations | 2449 – Equip Finwings with FPV Cameras | accepted | 3 | 1807 | S | 2 | Kelly Lee
Collision Awareness | 245 – Sprint 1403 Simulation Project Helper 2 | accepted | 3 | 1403 | M | 3 | Taylor Campbell | yes |  | high priority
Flight Operations | 2450 – Equip Finwings with FPV Cameras (copy) | accepted | 3 | 1808 | S | 2 | Sarah Chu
Flight Operations | 2451 – Auto Calculate Flight Time on the Flight Logs | dropped | #N/A | 1902 | XS | 1 | -
General AFSL Lab | 2452 - AFSL Action Items 1 | accepted | 3 | 1806 | M | 3 | Taehan Kook
General AFSL Lab | 2452 - AFSL Action Items 2 | accepted | 3 | 1806 | S | 2 | Taehan Kook
Flight Operations | 2452 – Flight Test Attendance 05/12/18 | accepted | 2 | 1805 | S | 2 | Hannah Rotta
Flight Operations | 2452 – Flight Test Attendance 05/12/18 | accepted | 3 | 1805 | S | 2 | Ravi Patel
Flight Operations | 2452 – Flight Test Attendance 05/12/18 | accepted | 2 | 1805 | S | 2 | Cory Cantey
Flight Operations | 2452 – Flight Test Attendance 05/12/18 | accepted | 3 | 1805 | S | 2 | Rostyk Svitelskyi
Flight Operations | 2452 – Flight Test Attendance 05/12/18 | accepted | 2 | 1805 | S | 2 | Ryan Grimes
Flight Operations | 2452 – Flight Test Attendance 05/12/18 | accepted | 2 | 1805 | S | 2 | Joshua Brockschmidt
Flight Operations | 2452 – Flight Test Attendance 05/12/18 | accepted | 3 | 1805 | S | 2 | Nicholas Price
Flight Operations | 2452 – Flight Test Attendance 05/12/18 | accepted | 3 | 1805 | S | 2 | Jordan Sims
Flight Operations | 2452 – Flight Test Attendance 05/12/18 | accepted | 2 | 1805 | S | 2 | Tinnabhand Patana-anake
Flight Operations | 2453 – Flight Test Attendance 05/19/18 | accepted | 2 | 1805 | S | 2 | Hannah Rotta
Flight Operations | 2453 – Flight Test Attendance 05/19/18 | accepted | 3 | 1805 | S | 2 | Joseph DePalma
Flight Operations | 2453 – Flight Test Attendance 05/19/18 | accepted | 3 | 1805 | S | 2 | Nicholas Price
Flight Operations | 2453 – Flight Test Attendance 05/19/18 | accepted | 3 | 1805 | S | 2 | Yao Dou
Flight Operations | 2453 – Flight Test Attendance 05/19/18 | accepted | 3 | 1805 | S | 2 | Ravi Patel
Flight Operations | 2453 – Flight Test Attendance 05/19/18 | accepted | 2 | 1805 | S | 2 | Helen Kuni
Flight Operations | 2453 – Flight Test Attendance 05/19/18 | accepted | 3 | 1805 | S | 2 | Rostyk Svitelskyi
TRAPIS2 | 2454 – Flight Test Attendance 05/26/18 - TRAPIS Dress Rehearsal | accepted | 2 | 1805 | S | 2 | Hannah Rotta
TRAPIS2 | 2454 – Flight Test Attendance 05/26/18 - TRAPIS Dress Rehearsal | accepted | 2 | 1805 | S | 2 | Helen Kuni
TRAPIS2 | 2454 – Flight Test Attendance 05/26/18 - TRAPIS Dress Rehearsal | accepted | 3 | 1805 | S | 2 | Christopher Lum
TRAPIS2 | 2454 – Flight Test Attendance 05/26/18 - TRAPIS Dress Rehearsal | accepted | 2 | 1805 | S | 2 | Kelly Lee
TRAPIS2 | 2454 – Flight Test Attendance 05/26/18 - TRAPIS Dress Rehearsal | accepted | 3 | 1805 | S | 2 | Ravi Patel
TRAPIS2 | 2454 – Flight Test Attendance 05/26/18 - TRAPIS Dress Rehearsal | accepted | 2 | 1805 | S | 2 | Cory Cantey
TRAPIS2 | 2454 - TRAPIS Payload Interference Testing | accepted | 3 | 1806 | M | 3 | Helen Kuni
TRAPIS2 | 2455 - TRAPIS Payload Interference Testing - Copy | accepted | 3 | 1806 | M | 3 | Hannah Rotta
Flight Operations | 2456 - Finwing latches and TRAPIS antenna fixture | accepted | 3 | 1806 | XS | 1 | Rostyk Svitelskyi
Flight Operations | 2457 – Finwing Decals (copy) | accepted | 3 | 1806 | S | 2 | Taehan Kook
Flight Operations | 2458 – Component Wiring Modification | accepted | 3 | 1806 | S | 2 | Taehan Kook
TEMPEST | 2459 - Poster prep | accepted | 0 | 1805 | XS | 1 | Bohao Zhu
TEMPEST | 2459 - Poster prep | accepted | 0 | 1805 | XS | 1 | Kirby Taylor
TEMPEST | 2459 - Poster prep | accepted | 0 | 1805 | XS | 1 | Zachary Rotter
TEMPEST | 2459 - Poster prep | accepted | 0 | 1805 | XS | 1 | Laura Smit
General AFSL Lab | 246 – Sprint 1403 Unit Test Triage 1 | accepted | 3 | 1511 | M | 3 | Alec Bueing |  | 25%
TEMPEST | 2463 - Validation Test Data Analysis | accepted | 0 | 1805 | XS | 1 | Bohao Zhu
TEMPEST | 2463 - Validation Test Data Analysis | accepted | 0 | 1805 | XS | 1 | Kirby Taylor
TEMPEST | 2463 - Validation Test Data Analysis | accepted | 0 | 1805 | S | 2 | Zachary Rotter
TEMPEST | 2463 - Validation Test Data Analysis | accepted | 0 | 1805 | S | 2 | Laura Smit
TEMPEST | 2467 - Final Prototype Manufacturing | accepted | 0 | 1805 | L | 5 | Laura Smit
General AFSL Lab | 2468 - Finwing Box Construction | accepted | 0 | 1805 | L | 5 | Joseph DePalma
General AFSL Lab | 2468 - Perforce Visual Client (copy) | accepted | 0 | 1806 | S | 2 | Boda Li
General AFSL Lab | 2469 - Perforce Visual Client (copy) | dropped | #N/A | 1902 | S | 2 | -
General AFSL Lab | 247 – Sprint 1403 Unit Test Triage 2 | dropped | #N/A | 1609 | M | 3 | -
General AFSL Lab | 2470 - Drill out propellers | accepted | 0 | 1806 | XS | 1 | Boda Li
Flight Operations | 2471 – Flight Test Attendance 06/02/18 | accepted | 3 | 1806 | S | 2 | Hannah Rotta
Flight Operations | 2471 – Flight Test Attendance 06/02/18 | accepted | 3 | 1806 | S | 2 | Yao Dou
Flight Operations | 2471 – Flight Test Attendance 06/02/18 | accepted | 3 | 1806 | S | 2 | Helen Kuni
Flight Operations | 2471 – Flight Test Attendance 06/02/18 | accepted | 3 | 1806 | S | 2 | Ryan Grimes
Flight Operations | 2471 – Flight Test Attendance 06/02/18 | accepted | 3 | 1806 | S | 2 | Cory Cantey
Flight Operations | 2471 – Flight Test Attendance 06/02/18 | accepted | 3 | 1806 | S | 2 | Shida Xu
TRAPIS2 | 2472 – Flight Test Attendance 06/08/18 - TRAPIS2 Dress Rehearsal | accepted | 3 | 1806 | S | 2 | Hannah Rotta
TRAPIS2 | 2472 – Flight Test Attendance 06/08/18 - TRAPIS2 Dress Rehearsal | accepted | 3 | 1806 | S | 2 | Helen Kuni
TRAPIS2 | 2472 – Flight Test Attendance 06/08/18 - TRAPIS2 Dress Rehearsal | accepted | 3 | 1806 | S | 2 | Kelly Lee
TRAPIS2 | 2472 – Flight Test Attendance 06/08/18 - TRAPIS2 Dress Rehearsal | accepted | 3 | 1806 | S | 2 | Karine Chen
TRAPIS2 | 2472 – Flight Test Attendance 06/08/18 - TRAPIS2 Dress Rehearsal | accepted | 3 | 1806 | S | 2 | Cory Cantey
TRAPIS2 | 2473 – Flight Test Attendance KDLS TRAPIS2 Flight Test | accepted | 3 | 1806 | L | 5 | Christopher Lum
TRAPIS2 | 2473 – Flight Test Attendance KDLS TRAPIS2 Flight Test | accepted | 3 | 1806 | L | 5 | Hannah Rotta
TRAPIS2 | 2473 – Flight Test Attendance KDLS TRAPIS2 Flight Test | accepted | 3 | 1806 | L | 5 | Helen Kuni
TRAPIS2 | 2473 – Flight Test Attendance KDLS TRAPIS2 Flight Test | accepted | 3 | 1806 | L | 5 | Cory Cantey
TRAPIS2 | 2473 – Flight Test Attendance KDLS TRAPIS2 Flight Test | accepted | 3 | 1806 | L | 5 | Joshua Brockschmidt
TRAPIS2 | 2473 – Flight Test Attendance KDLS TRAPIS2 Flight Test | accepted | 3 | 1806 | L | 5 | Karine Chen
TRAPIS2 | 2473 – Flight Test Attendance KDLS TRAPIS2 Flight Test | accepted | 3 | 1806 | L | 5 | Kelly Lee
TRAPIS2 | 2473 – Flight Test Attendance KDLS TRAPIS2 Flight Test | accepted | 3 | 1806 | L | 5 | Ravi Patel
Flight Operations | 2474 – Data Tech 06/02/18 | accepted | 3 | 1806 | XS | 1 | Hannah Rotta
TRAPIS2 | 2475 – Data Tech KDLS Flight Test | accepted | 3 | 1806 | XS | 1 | Helen Kuni
General AFSL Lab | 2476 – Luke Rebuild | accepted | 3 | 1808 | L | 5 | Sarah Chu
General AFSL Lab | 2477 – Troubleshoot Finwings | accepted | 3 | 1806 | S | 2 | Kelly Lee
General AFSL Lab | 2478 – Troubleshoot Finwings (copy) | accepted | 3 | 1806 | S | 2 | Sarah Chu
General AFSL Lab | 2479 - Construction & Maintenance Items | accepted | 3 | 1806 | XS | 1 | Sarah Chu
Collision Awareness | 248 – 3D Volumes C# Research | accepted | 3 | 1403 | S | 2 | Matthew Davis | yes
General AFSL Lab | 2480 - Perforce Visual Client (copy) | accepted | 0 | 1806 | S | 2 | Sarah Chu
General AFSL Lab | 2481 - Perforce Visual Client (copy) | accepted | 0 | 1807 | S | 2 | Aditi Chauhan
General AFSL Lab | 2482 - Perforce Visual Client (copy) | accepted | 0 | 1806 | S | 2 | DB Nguyen
General AFSL Lab | 2483 - Perforce Visual Client (copy) | accepted | 0 | 1806 | S | 2 | Wendy Liu
General AFSL Lab | 2484 - Assess Component Status | accepted | 0 | 1806 | XS | 1 | Veen Oung
AMFAV | 2485 - Investigate MicaSense camera and Pix4Dfields | dropped | #N/A | 1906 | XS | 1 | -
Flight Operations | 2486 - Build flight team power station | accepted | 0 | 1806 | XS | 1 | Leo Zhu
General AFSL Lab | 2487 - Assess 3DRSoloSTF | accepted | 0 | 1806 | XS | 1 | Sarah Chu
LARAMID | 2488 - Frodo Rebuild | accepted | 0 | 1806 | L | 5 | Taehan Kook
Flight Operations | 2489 – Flight Test Attendance 06/19/18 | accepted | 3 | 1806 | S | 2 | Helen Kuni
Collision Awareness | 249 – Insitu Trip Logistics Helper | accepted | 3 | 1403 | M | 3 | Justin Yantus |  |  | highest priority
Flight Operations | 2490 – Flight Test Attendance 06/19/18 | accepted | 3 | 1806 | S | 2 | Cory Cantey
Flight Operations | 2491 – Flight Test Attendance 06/19/18 | accepted | 3 | 1806 | S | 2 | Norman Lei
Flight Operations | 2492 – Flight Test Attendance 06/19/18 | accepted | 3 | 1806 | S | 2 | Chung Choi
Flight Operations | 2493 – Flight Test Attendance 06/19/18 | accepted | 3 | 1806 | S | 2 | Boda Li
Flight Operations | 2494 – Flight Test Attendance 06/19/18 | accepted | 3 | 1806 | S | 2 | Leo Zhu
Flight Operations | 2495 – Flight Test Attendance 06/19/18 | accepted | 3 | 1806 | S | 2 | Sarah Chu
Flight Operations | 2496 – Flight Test Attendance 06/19/18 | accepted | 3 | 1806 | S | 2 | Wendy Liu
General AFSL Lab | 2497 - Perforce Visual Client (copy) | finished | 0 | 1806 | S | 2 | Gerald Collom
General AFSL Lab | 2498 – Sprint Metrics (copy) | accepted | 3 | 1806 | XS | 1 | Taehan Kook
AMFAV | 2499 - Mapping Initialiation Startup (copy) | accepted | 3 | 1807 | XS | 1 | Helen Kuni
Collision Awareness | 250 – Sprint 1403 Unity Visualizer (Position 3) | accepted | 3 | 1403 | L | 5 | Robert McSwain
General AFSL Lab | 2500 - Perforce Visual Client (copy) | accepted | 0 | 1806 | S | 2 | Stephanie Huerta-Ramirez
General AFSL Lab | 2501 - Perforce Visual Client (copy) | accepted | 0 | 1806 | S | 2 | Reuel Abad
AMFAV | 2502 - Mapping Initialiation Startup (copy) | accepted | 3 | 1806 | XS | 1 | Wendy Liu
AMFAV | 2503 - Mapping Initialiation Startup (copy) | accepted | 3 | 1806 | XS | 1 | Gerald Collom
AMFAV | 2504 - Mapping Initialiation Startup (copy) | accepted | 3 | 1806 | XS | 1 | Jaspreet Sidhu
Flight Operations | 2505 – Flight Training Program – Multi-Rotor (Copy) | dropped | #N/A | 1812 | L | 5 | Bryson Bruno
LARI | 2506 - LARI Initialization/Startup | accepted | 3 | 1809 | M | 3 | Joshua Brockschmidt |  |  | Need dev guide
General AFSL Lab | 2507 - Investigate Precision laptop chargers | accepted | 3 | 1806 | XS | 1 | Stephanie Huerta-Ramirez
Flight Operations | 2508 – Flight Ops Administration (1806) | accepted | 3 | 1806 | L | 5 | Hannah Rotta
Flight Operations | 2509 – Flight Ops Administration (1806) (copy) | accepted | 3 | 1806 | L | 5 | Helen Kuni
Collision Awareness | 251 – Refactor Simulator | in backlog | 0 | - | M | 3 | -
Flight Operations | 2510 -- Finwing Maintenance | accepted | 3 | 1807 | XS | 1 | Sarah Chu
LARI | 2511 - Generate wireframe of UI | dropped | #N/A | 1811 | M | 3 | Aditi Chauhan
LARI | 2512 - Clarify Internet Connectivity in the MFOC | accepted | 3 | 1807 | XS | 1 | Leo Zhu
LARI | 2513 - Understand the systems component list and checklist | dropped | #N/A | 1811 | XS | 1 | Valdi Widanta
LARI | 2514 - Look into Database Layers | accepted | 3 | 1807 | S | 2 | Gerald Collom
LARI | 2515 - Build a Mockup LARI Example | dropped | #N/A | 1811 | M | 3 | Bryson Bruno
LARI | 2516 - Build a Mockup LARI Example (Copy) | dropped | #N/A | 1811 | M | 3 | Valdi Widanta
LARI | 2517 - Build a Mockup LARI Example (Copy) | dropped | #N/A | 1811 | M | 3 | Aditi Chauhan
LARI | 2518 - Build a Mockup LARI Example (Copy) | dropped | #N/A | 1809 | M | 3 | -
LARI | 2519 - Build a Mockup LARI Example (Copy) | accepted | 3 | 1807 | XS | 1 | Gerald Collom
Collision Awareness | 252 – Test Cases for 3D Volume Restricted Airspaces | accepted | 3 | 1406 | L | 5 | Brian Chang
LARI | 2520 - Build a Mockup LARI Example (Copy) | dropped | #N/A | 1809 | M | 3 | Erin Arthur
General AFSL Lab | 2521 – Luke Rebuild (copy) | accepted | 3 | 1807 | S | 2 | Stephanie Huerta-Ramirez
TRAPIS2 | 2522 - JCATI Final Report | accepted | 3 | 1806 | S | 2 | Helen Kuni
LARAMID | 2523 - Frodo Rebuild (copy) | accepted | 0 | 1806 | L | 5 | Norman Lei
LARAMID | 2524 – LARAMID Electromagnet Receiver Mounting (copy) | accepted | 3 | 1806 | L | 5 | Taehan Kook
LARAMID | 2525 – LARAMID Samwise Weight Optimization | accepted | 3 | 1807 | L | 5 | Chung Choi
LARAMID | 2526 – LARAMID Samwise Weight Optimization (copy) | accepted | 3 | 1807 | L | 5 | Taehan Kook
LARAMID | 2527 – LARAMID Motor Thrust Testing | accepted | 3 | 1807 | M | 3 | Chung Choi
LARAMID | 2528 – LARAMID Motor Thrust Testing (copy) | accepted | 3 | 1807 | M | 3 | Taehan Kook
LARAMID | 2529 – LARAMID Docking Frame Design (part2) | accepted | 3 | 1807 | M | 3 | Chung Choi
Collision Awareness | 253 – 3D Volume Restricted Airspaces Implementation (Method 1) | accepted | 3 | 1405 | M | 3 | Christopher Lum | 1 |  | 75%
LARAMID | 2530 – LARAMID Docking Frame Design (part2) (copy) | accepted | 3 | 1807 | M | 3 | Norman Lei
LARAMID | 2531 – LARAMID Aerodynamics Simulation | dropped | #N/A | 1901 | M | 3 | -
LARAMID | 2532 – LARAMID Aircraft CAD Design | accepted | 3 | 1807 | L | 5 | Chung Choi
LARAMID | 2533 – LARAMID Aircraft CAD Design (copy) | accepted | 3 | 1807 | L | 5 | Boda Li
LARAMID | 2534 – LARAMID Detachment Process Pre-Ground Test | accepted | 3 | 1809 | XL | 8 | Chung Choi
LARAMID | 2534 – LARAMID Detachment Process Pre-Ground Test (copy) | accepted | 3 | 1807 | XL | 8 | Taehan Kook
LARAMID | 2536 – LARAMID Docking Frame Design (part3) | accepted | 3 | 1807 | L | 5 | Chung Choi
LARAMID | 2537 – LARAMID Docking Frame Design (part3) (copy) | accepted | 3 | 1807 | L | 5 | Norman Lei
LARAMID | 2538 – LARAMID Motor Thrust Testing (copy) | accepted | 3 | 1807 | M | 3 | Norman Lei
LARAMID | 2539 - Frodo Rebuild (copy) | accepted | 3 | 1806 | L | 5 | Boda Li
Collision Awareness | 254 – 3D Volume Restricted Airspaces Implementation (Method 2) | in backlog | 0 | - | M | 3 | -
Flight Operations | 2540 – Flight Test Attendance 06/29/18 | accepted | 3 | 1806 | S | 2 | Helen Kuni
Flight Operations | 2541 – Flight Test Attendance 06/29/18 | accepted | 3 | 1806 | S | 2 | Christopher Lum
Flight Operations | 2542 – Flight Test Attendance 06/29/18 | accepted | 3 | 1806 | S | 2 | Bryson Bruno
Flight Operations | 2543 – Flight Test Attendance 06/29/18 | accepted | 3 | 1806 | S | 2 | Cory Cantey
Flight Operations | 2544 – Flight Test Attendance 06/29/18 | finished | 2 | 1806 | S | 2 | Gerald Collom
Flight Operations | 2545 – Flight Test Attendance 06/29/18 | accepted | 3 | 1806 | S | 2 | Brian Harr
Flight Operations | 2546 – Flight Test Attendance 06/29/18 | accepted | 3 | 1806 | S | 2 | Jaspreet Sidhu
Flight Operations | 2547 – Flight Test Attendance 06/29/18 | accepted | 3 | 1806 | S | 2 | Leo Zhu
TRAPIS2 | 2548 - KDLS Compilation Video | accepted | 3 | 1808 | M | 3 | Sarah Chu
AMFAV | 2549 - Investigate Cloud Compare | accepted | 3 | 1807 | XS | 1 | Jaspreet Sidhu
Collision Awareness | 255 – Integration of Position Probabilities Over An Arbitrary Volume | accepted | 3 | 1407 | L | 5 | Kevin Ueunten |  |  | 75% writing unit tests
Flight Operations | 2550 – Data Tech 06/19/18 | accepted | 3 | 1806 | XS | 1 | Boda Li
Flight Operations | 2551 – Data Tech 06/29/18 | accepted | 3 | 1806 | XS | 1 | Bryson Bruno
General AFSL Lab | 2552 - FPV Transmitter Repair | accepted | 3 | 1806 | XS | 1 | Reuel Abad
TRAPIS2 | 2553 - LAMS Documentation | dropped | #N/A | 1902 | XS | 1 | -
TRAPIS2 | 2554 - TRAPIS2 Writeup | accepted | 3 | 1807 | XS | 1 | Helen Kuni
LARI | 2555 - Find Software for Managing User Stories | dropped | #N/A | 1902 | M | 3 | Ravi Patel |  |  | I do not think taiga.io will be a sufficient replacement for our lab… time investment for this is not worth our time in my opinion.
General AFSL Lab | 2556 - Convert Lab's GitHub Account Into an Organization | accepted | 3 | 1807 | S | 2 | Joshua Brockschmidt
General AFSL Lab | 2557 - Assess 3DRSoloSTF (copy) | accepted | 0 | 1806 | XS | 1 | Stephanie Huerta-Ramirez
Flight Operations | 2558 - Flight Test Attendance (07/07/18) | accepted | 0 | 1807 | S | 2 | Helen Kuni
AMFAV | 2558 - Pix4D Analysis, 6/29/18 | accepted | 3 | 1807 | M | 3 | Bryson Bruno
Flight Operations | 2559 - Flight Test Attendance (07/07/18) | accepted | 0 | 1807 | S | 2 | Cory Cantey
AMFAV | 2559 - Pix4D Analysis, 6/29/18 (copy) | accepted | 3 | 1807 | XS | 1 | Stephanie Huerta-Ramirez
Collision Awareness | 256 – Augment Forward State Estimator with Environmental Factors | in backlog | 0 | - |  | #N/A | -
Flight Operations | 2560 - Flight Test Attendance (07/07/18) | accepted | 3 | 1807 | S | 2 | Rostyk Svitelskyi
General AFSL Lab | 2560 - Repair silver 4s battery connector | accepted | 3 | 1807 | XS | 1 | Sarah Chu
Flight Operations | 2561 - Flight Test Attendance (07/07/18) | accepted | 0 | 1807 | S | 2 | Nicholas Price
General AFSL Lab | 2561 - General fleet maintanence tasks | accepted | 3 | 1807 | XS | 1 | Sarah Chu
Flight Operations | 2562 - Flight Test Attendance (07/07/18) | accepted | 0 | 1807 | S | 2 | Kelly Lee
General AFSL Lab | 2562 - Perforce Visual Client (copy) | accepted | 0 | 1807 | S | 2 | Annyn Howle
Flight Operations | 2563 - Flight Test Attendance (07/07/18) | accepted | 0 | 1807 | S | 2 | Joshua Brockschmidt
General AFSL Lab | 2563 - Perforce Visual Client (copy) | accepted | 0 | 1807 | S | 2 | Hadi Al_Naji
Flight Operations | 2564 - Flight Test Attendance (07/07/18) | accepted | 3 | 1807 | S | 2 | Ravi Patel
Flight Operations | 2564 – Flight Test Attendance 07/13/18 | accepted | 3 | 1807 | S | 2 | Helen Kuni
Flight Operations | 2565 - Flight Test Attendance (07/07/18) | accepted | 0 | 1807 | S | 2 | Chung Choi
Flight Operations | 2565 – Flight Test Attendance 07/13/18 | accepted | 3 | 1807 | S | 2 | Cory Cantey
Flight Operations | 2566 - Flight Test Attendance (07/07/18) | accepted | 0 | 1807 | S | 2 | Taehan Kook
Flight Operations | 2566 – Flight Test Attendance 07/13/18 | accepted | 3 | 1807 | S | 2 | Bryson Bruno
Flight Operations | 2567 - Flight Test Attendance (07/07/18) | accepted | 0 | 1807 | S | 2 | Boda Li
Flight Operations | 2567 – Flight Test Attendance 07/13/18 | accepted | 3 | 1807 | S | 2 | Annyn Howle
Flight Operations | 2568 - Data Tech 07/07/18 | accepted | 0 | 1807 | S | 2 | Taehan Kook
Flight Operations | 2568 – Flight Test Attendance 07/13/18 | accepted | 3 | 1807 | S | 2 | Jaspreet Sidhu
Flight Operations | 2569 – Flight Test Attendance 07/13/18 | accepted | 3 | 1807 | S | 2 | Stephanie Huerta-Ramirez
Collision Awareness | 257 – Insitu Trip Wrap-Up | accepted | 3 | 1405 | S | 2 | Justin Yantus |  |  | 100%
Flight Operations | 2570 – Flight Test Attendance 07/13/18 | accepted | 3 | 1807 | S | 2 | Wendy Liu
Flight Operations | 2571 – Flight Test Attendance 07/13/18 | accepted | 3 | 1807 | S | 2 | Taehan Kook
Visual Anchoring | 2572 – Visual Anchoring vision system study | accepted | 3 | 1808 | XL | 8 | Rostyk Svitelskyi
Visual Anchoring | 2573 – Visual Anchoring gimbal study | accepted | 3 | 1807 | XL | 8 | Rostyk Svitelskyi
General AFSL Lab | 2574 – HiL Airworthiness (copy) | accepted | 3 | 1807 | L | 5 | Taehan Kook
General AFSL Lab | 2575 - Perforce Visual Client (copy) | accepted | 0 | 1808 | S | 2 | Emily Drozynski
General AFSL Lab | 2576 - Repair TEDD | accepted | 3 | 1807 | XS | 1 | Sarah Chu
AMFAV | 2577 - Pix4D Analysis, 7/13/18 | accepted | 3 | 1808 | L | 5 | Bryson Bruno
AMFAV | 2578 - Pix4D Analysis, 7/13/18 (copy) | accepted | 3 | 1808 | L | 5 | Annyn Howle
AMFAV | 2579 - Pix4D Analysis, 7/13/18 (copy) | accepted | 3 | 1807 | M | 3 | Stephanie Huerta-Ramirez
Collision Awareness | 258 –Critical Code Path Identification | in backlog | 0 | - | L | 5 | Noel Kimber
AMFAV | 2580 - Point cloud Matlab analysis | accepted | 3 | 1808 | L | 5 | Jaspreet Sidhu
AMFAV | 2581 - Point cloud Matlab analysis (copy) | accepted | 3 | 1807 | XS | 1 | Gerald Collom
Flight Operations | 2582 - Data tech 07/13/18 | accepted | 0 | 1807 | XS | 1 | Taehan Kook
LARI | 2583 - Write Component class | accepted | 0 | 1807 | S | 2 | Wendy Liu
LARI | 2584 - Write unit tests for Component class | accepted | 0 | 1807 | S | 2 | Gerald Collom
AMFAV | 2585 - 3D Print from Pix4D Models | accepted | 3 | 1807 | S | 2 | Annyn Howle
Flight Operations | 2586 – Flight Test Attendance 07/21/18 | accepted | 3 | 1807 | S | 2 | Helen Kuni
Flight Operations | 2587 – Flight Test Attendance 07/21/18 | accepted | 3 | 1807 | S | 2 | Ravi Patel
Flight Operations | 2588 – Flight Test Attendance 07/21/18 | accepted | 3 | 1807 | S | 2 | Sarah Chu
Flight Operations | 2589 – Flight Test Attendance 07/21/18 | accepted | 3 | 1807 | S | 2 | Rostyk Svitelskyi
Collision Awareness | 259 – Master’s Thesis 1 | accepted | 3 | 1404 | XL | 8 | Bao Le
Flight Operations | 2590 – Flight Test Attendance 07/21/18 | accepted | 3 | 1807 | S | 2 | Nicholas Price
Flight Operations | 2591 – Flight Test Attendance 07/21/18 | accepted | 3 | 1807 | S | 2 | Hadi Al_Naji
Flight Operations | 2592 - Data tech 07/21/18 | accepted | 0 | 1807 | XS | 1 | Nicholas Price
General AFSL Lab | 2593 - SolarUAS Rebuild | accepted | 0 | 1807 | XL | 8 | Nicholas Price
General AFSL Lab | 2594 - Fix broken/loose pitot tubes | accepted | 0 | 1807 | XS | 1 | Annyn Howle
General AFSL Lab | 2595 - TEDD Postmortem | accepted | 0 | 1807 | M | 3 | Taehan Kook
AMFAV | 2596 - Blakely Elemetary Data Analysis | accepted | 3 | 1807 | XL | 8 | Stephanie Huerta-Ramirez
LARAMID | 2597 – Frodo Rebuild 2 | accepted | 1 | 1807 | M | 3 | Chung Choi
LARAMID | 2598 – Frodo Rebuild 2 (copy) | accepted | 1 | 1807 | M | 3 | Taehan Kook
LARAMID | 2598 – Frodo Rebuild 2 (copy) | accepted | 1 | 1807 | M | 3 | Boda Li
LARAMID | 2599 – LARAMID Wireless Network Setup | accepted | 3 | 1809 | XL | 8 | Chung Choi
Collision Awareness | 260 – 3D Volumes C# Research (Part 2) | in backlog | 0 | - | M | 3 | -
LARAMID | 2600 – LARAMID Electromagnet Control with Raspberry Pi | accepted | 1 | 1807 | M | 3 | Taehan Kook
LARAMID | 2601 – LARAMID EM Receiver Mounting 2 | accepted | 3 | 1809 | S | 2 | Chung Choi
LARAMID | 2602 – LARAMID EM Receiver Mounting 2 (copy) | accepted | 3 | 1809 | S | 2 | Boda Li
LARAMID | 2602 – LARAMID EM Receiver Mounting 2 (copy) | accepted | 3 | 1809 | S | 2 | Norman Lei
LARAMID | 2603 – LARAMID Autonomous Mission Operation | dropped | #N/A | 1809 | L | 5 | Chung Choi
LARAMID | 2604 – LARAMID Mating System Options | dropped | #N/A | 1811 | L | 5 | Chung Choi |  |  | Integrated with Rendezvous Control
Visual Anchoring | 2605 – Clean Up VA Ardupilot Code | dropped | #N/A | 1902 | M | 3 | -
LARI | 2606 – AFSLSystem and EquippageController methods and unit tests | accepted | 3 | 1811 | L | 5 | Gerald Collom
LARI | 2607 - C# GUI Tutorial | accepted | 3 | 1810 | S | 2 | Ravi Patel
LARI | 2608 - C# GUI Tutorial (copy) | accepted | 3 | 1810 | S | 2 | Sidharth Lakshmanan
LARI | 2609 - C# GUI Tutorial (copy) | accepted | 3 | 1811 | M | 3 | Veen Oung
Collision Awareness | 261 – JCATI Symposium Trip Logistics | accepted | 3 | 1405 | M | 3 | John Marshall | 1 |  | high priority, deadline is 4/21
LARI | 2610 - C# GUI Tutorial (copy) | dropped | #N/A | 1903 | S | 2 | -
LARI | 2611 - C# GUI Tutorial (copy) | accepted | 3 | 1902 | M | 3 | Tina Li |  | 100% | Verified by Ravi Patel
LARI | 2612 - UWXML Serialize/Deserialize Doubles Test | dropped | #N/A | 1811 | S | 2 | Valdi Widanta
Flight Operations | 2614 – Flight Test Attendance 07/28/18 | accepted | 3 | 1807 | S | 2 | Helen Kuni
Flight Operations | 2615 – Flight Test Attendance 07/28/18 | accepted | 3 | 1807 | S | 2 | Ravi Patel
Flight Operations | 2616 – Flight Test Attendance 07/28/18 | accepted | 3 | 1807 | S | 2 | Rostyk Svitelskyi
Flight Operations | 2617 – Flight Test Attendance 07/28/18 | accepted | 3 | 1807 | S | 2 | Nicholas Price
Flight Operations | 2618 – Flight Test Attendance 07/28/18 | accepted | 3 | 1807 | S | 2 | Joshua Brockschmidt
Flight Operations | 2619 – Flight Test Attendance 07/28/18 | accepted | 3 | 1807 | S | 2 | Annyn Howle
Collision Awareness | 262 – WPF User Control for ConflictEntity | accepted | 3 | 1406 | M | 3 | Dai Tsukada |  |  | 60%
General AFSL Lab | 2620 - General Fleet Maintenance | accepted | 3 | 1807 | XS | 1 | Hadi Al_Naji
TRAPIS2 | 2621 - KDLS Data Analysis | accepted | 3 | 1810 | XL | 8 | Helen Kuni
TRAPIS2 | 2622 - KDLS Data Analysis (copy) | accepted | 3 | 1808 | M | 3 | Tinnabhand Patana-anake
TRAPIS2 | 2623 - KDLS Compilation Video (copy) | accepted | 3 | 1807 | XS | 1 | Tinnabhand Patana-anake
General AFSL Lab | 2624 - TEDD Postmortem (copy) | accepted | 0 | 1807 | XS | 1 | Kelly Lee
General AFSL Lab | 2625 - TEDD Postmortem (copy) | accepted | 3 | 1807 | XS | 1 | Sarah Chu
General AFSL Lab | 2626 - Anakin Repairs | accepted | 0 | 1807 | S | 2 | Stephanie Huerta-Ramirez
General AFSL Lab | 2627 - Repair CONDOR's wings | accepted | 0 | 1807 | XS | 1 | Hadi Al_Naji
Flight Operations | 2628 - Flight Ops Administration (1807) | accepted | 0 | 1807 | XL | 8 | Helen Kuni
Flight Operations | 2629 - Data Tech 07/28/18 | accepted | 0 | 1807 | XS | 1 | Annyn Howle
Collision Awareness | 263 – Unity 3D Polygons and Hit Detection (position 1) | accepted | 3 | 1404 | M | 3 | Richard Fukutome
General AFSL Lab | 2630 - Evaluate Transmitter K | accepted | 3 | 1807 | XS | 1 | Sarah Chu
General AFSL Lab | 2631 - Evaluate Transmitter K (copy) | accepted | 0 | 1807 | XS | 1 | Annyn Howle
AMFAV | 2632 - Pix4D Analysis, 7/13/18 (copy) | accepted | 3 | 1807 | M | 3 | Jaspreet Sidhu
General AFSL Lab | 2633-X-Plane setup | accepted | 0 | 1807 | S | 2 | Rostyk Svitelskyi
Flight Operations | 2634 – Flight Test Attendance 08/03/18 | accepted | 3 | 1808 | S | 2 | Annyn Howle
Flight Operations | 2635 – Flight Test Attendance 08/03/18 | accepted | 3 | 1808 | S | 2 | Chung Choi
Flight Operations | 2636 – Flight Test Attendance 08/03/18 | accepted | 3 | 1808 | S | 2 | Zachary Williams
Flight Operations | 2637 – Flight Test Attendance 08/03/18 | accepted | 3 | 1808 | S | 2 | Helen Kuni
Flight Operations | 2638 – Flight Test Attendance 08/03/18 | accepted | 3 | 1808 | S | 2 | Norman Lei
Flight Operations | 2639 – Flight Test Attendance 08/03/18 | accepted | 3 | 1808 | S | 2 | Taehan Kook
Collision Awareness | 264 – Unity 3D Polygons and Hit Detection (position 2) | accepted | 3 | 1404 | M | 3 | Robert McSwain
Flight Operations | 2640 - Data Tech 08/03/18 | accepted | 3 | 1808 | XS | 1 | Annyn Howle
Flight Operations | 2641 – Flight Test Attendance 08/11/18 | accepted | 3 | 1808 | XS | 1 | Zachary Williams
Flight Operations | 2642 – Flight Test Attendance 08/11/18 | accepted | 3 | 1808 | XS | 1 | Helen Kuni
Flight Operations | 2643 - Data Tech 08/11/18 | accepted | 3 | 1808 | XS | 1 | Helen Kuni
Flight Operations | 2644 - Flight Test Attendance 08/18/18 | accepted | 3 | 1808 | S | 2 | Helen Kuni
Flight Operations | 2645 - Flight Test Attendance 08/18/18 | accepted | 3 | 1808 | S | 2 | Rostyk Svitelskyi
Flight Operations | 2646 - Flight Test Attendance 08/18/18 | accepted | 3 | 1808 | S | 2 | Bryson Bruno
Flight Operations | 2647 - Flight Test Attendance 08/18/18 | accepted | 3 | 1808 | S | 2 | Nicholas Price
Flight Operations | 2648 - Data Tech 08/18/18 | accepted | 3 | 1808 | XS | 1 | Nicholas Price
AMFAV | 2649 - Flight Test Attendance 08/20/18 | accepted | 3 | 1808 | S | 2 | Bryson Bruno
Collision Awareness | 265 – Perforce Visual Client (copy) | accepted | 3 | 1404 | S | 2 | Aleksandr Tereshchenkov
AMFAV | 2650 - Flight Test Attendance 08/20/18 | accepted | 3 | 1808 | S | 2 | Jaspreet Sidhu
AMFAV | 2651 - Flight Test Attendance 08/20/18 | accepted | 3 | 1808 | S | 2 | Helen Kuni
Flight Operations | 2652 - Data Tech 08/20/18 | accepted | 3 | 1808 | XS | 1 | Helen Kuni
Flight Operations | 2653 – Flight Training Program – Fixed Wing (Copy) | accepted | 3 | 1809 | L | 5 | Rostyk Svitelskyi
Visual Anchoring | 2654 – Visual Anchoring code integration | accepted | 3 | 1808 | XL | 8 | Rostyk Svitelskyi
Visual Anchoring | 2655 – Visual Anchoring Rectification algorithm ground test | accepted | 3 | 1808 | L | 5 | Rostyk Svitelskyi
Flight Operations | 2656 -- Flight Test Attendance 08/25/18 | accepted | 3 | 1808 | S | 2 | Helen Kuni
Flight Operations | 2657 -- Flight Test Attendance 08/25/18 | accepted | 3 | 1808 | S | 2 | Rostyk Svitelskyi
Flight Operations | 2658 -- Flight Test Attendance 08/25/18 | accepted | 3 | 1808 | S | 2 | Ravi Patel
Flight Operations | 2659 -- Flight Test Attendance 08/25/18 | accepted | 3 | 1808 | S | 2 | Dylan Hoff
Collision Awareness | 266 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1404 | L | 5 | Aleksandr Tereshchenkov
Flight Operations | 2660 - Data Tech 08/25/18 | accepted | 3 | 1808 | XS | 1 | Helen Kuni
LARAMID | 2661 - Samwise repairs | accepted | 3 | 1808 | S | 2 | Norman Lei
AMFAV | 2662 - Pix4D Analysis, 8/20/18 | accepted | 3 | 1811 | S | 2 | Jaspreet Sidhu
AMFAV | 2663 - Pix4D Analysis, 8/20/18 (copy) | dropped | #N/A | 1811 | XS | 1 | Bryson Bruno
Flight Operations | 2664 - Flight Ops Administration (1808) | accepted | 3 | 1808 | XL | 8 | Helen Kuni
AMFAV | 2665 - Matlab analysis, 8/20/18 | accepted | 3 | 1811 | M | 3 | Jaspreet Sidhu
General AFSL Lab | 2666 - Setup Static Analysis Tool | accepted | 3 | 1810 | XS | 1 | Ravi Patel
General AFSL Lab | 2667 - Setup Continuous Integration Tool | accepted | 3 | 1810 | XS | 1 | Ravi Patel
TRAPIS2 | 2668 - Ardupilot Software Development Setup | accepted | 3 | 1811 | M | 3 | Dylan Hoff
TRAPIS2 | 2669 - Advanced TRAPIS Flight Mode | accepted | 3 | 1811 | S | 2 | Dylan Hoff
Collision Awareness | 267 – Developer WebEx Account Setup (Group 16) | accepted | 3 | 1405 | XS | 1 | Aleksandr Tereshchenkov
TRAPIS2 | 2670 - Advanced TRAPIS Flight Mode (copy) | dropped | #N/A | 1901 | XL | 8 | -
Flight Operations | 2671 - Carnation Test Site Radio Identification Script | accepted | 3 | 1809 | XS | 1 | Nicholas Price |  | 100%
Flight Operations | 2672 -- Flight Test Attendance 09/08/18 | finished | 2 | 1808 | S | 2 | Helen Kuni
Flight Operations | 2673 -- Flight Test Attendance 09/08/18 | finished | 2 | 1808 | S | 2 | Rostyk Svitelskyi
Flight Operations | 2674 -- Flight Test Attendance 09/08/18 | finished | 2 | 1808 | S | 2 | Joshua Brockschmidt
Flight Operations | 2675 -- Flight Test Attendance 09/08/18 | finished | 2 | 1808 | S | 2 | Gerald Collom
Flight Operations | 2676 -- Flight Test Attendance 09/08/18 | finished | 2 | 1808 | S | 2 | Norman Lei
Flight Operations | 2677 - Data Tech 09/08/18 | finished | 2 | 1808 | XS | 1 | Joshua Brockschmidt
General AFSL Lab | 2678 - Perforce Visual Client (copy) | accepted | 3 | 1809 | S | 2 | Sidharth Lakshmanan
General AFSL Lab | 2679 - Perforce Visual Client (copy) | accepted | 3 | 1809 | S | 2 | Nathan White
Collision Awareness | 268 – Unit Testing Background Training (copy) | accepted | 3 | 1405 | M | 3 | Aleksandr Tereshchenkov
General AFSL Lab | 2680 - Lab Moving | accepted | 3 | 1809 | L | 5 | Helen Kuni
General AFSL Lab | 2681 - Lab Moving (copy) | accepted | 3 | 1809 | M | 3 | Ravi Patel
General AFSL Lab | 2682 - Lab Moving (copy) | accepted | 3 | 1809 | M | 3 | Joshua Brockschmidt
General AFSL Lab | 2683 - Lab Moving (copy) | accepted | 3 | 1809 | S | 2 | Shawn Stanley
General AFSL Lab | 2684 - Lab Moving (copy) | accepted | 3 | 1809 | M | 3 | Josh Lee
General AFSL Lab | 2685 - Lab Moving (copy) | accepted | 3 | 1809 | S | 2 | Karine Chen
General AFSL Lab | 2686 - Lab Moving (copy) | accepted | 3 | 1809 | S | 2 | Norman Lei
General AFSL Lab | 2687 - Lab Moving (copy) | accepted | 3 | 1809 | L | 5 | Christopher Lum
General AFSL Lab | 2688 - Perforce Visual Client (copy) | accepted | 3 | 1902 | S | 2 | Shawn Stanley
General AFSL Lab | 2689 - Perforce Visual Client (copy) | accepted | 3 | 1809 | S | 2 | Josh Lee
Collision Awareness | 269 – Perforce Visual Client (copy) | accepted | 3 | 1404 | S | 2 | Ryan Valach
LARAMID | 2690 – LARAMID Electromagnet Control Programming | accepted | 3 | 1809 | S | 2 | Chung Choi
LARAMID | 2691 – LARAMID Mating System 3D Sensor Option | dropped | #N/A | 1810 | M | 3 | Chung Choi
LARAMID | 2692 – LARAMID Intel Realsense 3D Camera and Drone Integration | dropped | #N/A | 1810 | M | 3 | Chung Choi
LARAMID | 2693 – LARAMID Docking Frame Design (part4) | accepted | 3 | 1809 | L | 5 | Norman Lei
LARAMID | 2694 – Samwise Inspection and Repaired | accepted | 3 | 1810 | XS | 1 | Norman Lei
LARAMID | 2695 – LARAMID Mating System 3D Sensor Option (copy) | dropped | #N/A | 1810 | M | 3 | Norman Lei
CellNav | 2696 – CellNav Project Acronym Brainstorm | accepted | 3 | 1902 | XS | 1 | Matthew Davis
CellNav | 2697 – CellNav Populate backlog | accepted | 3 | 1811 | S | 2 | Matthew Davis
CellNav | 2698 – CellNav Onboarding Automation Investigation | dropped | #N/A | 1902 | M | 3 | -
LARAMID | 2699 – LARAMID Docking Frame Design (part4) (copy) | accepted | 3 | 1809 | L | 5 | Chung Choi
Collision Awareness | 270 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1404 | L | 5 | Ryan Valach
LARI | 2700 – Refactor Project Structure | accepted | 3 | 1810 | XL | 8 | Joshua Brockschmidt
LARI | 2701 – Develop Basic Components/Systems Viewer and Editor | accepted | 3 | 1809 | M | 3 | Gerald Collom
LARI | 2702 – Implement Skeleton GUI for Components | accepted | 3 | 1811 | S | 2 | Aditi Chauhan
LARI | 2703 – Implement Skeleton GUI for Systems | accepted | 3 | 1811 | S | 2 | Wendy Liu
LARI | 2704 – Implement Skeleton GUI for Adding and Editing Components | accepted | 3 | 1810 | L | 5 | Sidharth Lakshmanan
Flight Operations | 2705 -- Flight Test Attendance 09/30/18 | accepted | 3 | 1809 | S | 2 | Helen Kuni
Flight Operations | 2706 -- Flight Test Attendance 09/30/18 | accepted | 3 | 1809 | S | 2 | Ravi Patel
Flight Operations | 2707 -- Flight Test Attendance 09/30/18 | accepted | 3 | 1809 | S | 2 | Rostyk Svitelskyi
Flight Operations | 2708 -- Flight Test Attendance 09/30/18 | accepted | 3 | 1809 | S | 2 | Dylan Hoff
Flight Operations | 2709 -- Flight Test Attendance 09/30/18 | accepted | 3 | 1809 | S | 2 | Nicholas Price
Collision Awareness | 271 – Developer WebEx Account Setup (Group 16) | accepted | 3 | 1404 | XS | 1 | Ryan Valach
Flight Operations | 2710 -- Flight Test Attendance 09/30/18 | accepted | 3 | 1809 | S | 2 | Norman Lei
Flight Operations | 2711 -- Flight Test Attendance 09/30/18 | accepted | 3 | 1809 | S | 2 | Chung Choi
Flight Operations | 2712 -- Flight Test Attendance 09/30/18 | accepted | 3 | 1809 | S | 2 | Josh Lee
General AFSL Lab | 2713 - Perforce Visual Client (copy) | dropped | #N/A | 1905 | S | 2 | -
General AFSL Lab | 2714 - Perforce Visual Client (copy) | accepted | 3 | 1811 | S | 2 | Pranav Natarajan
General AFSL Lab | 2715 - Troubleshoot Excelsior | accepted | 3 | 1809 | XS | 1 | Josh Lee
Flight Operations | 2716 - Flight Ops Administration (1809) | accepted | 3 | 1809 | XL | 8 | Helen Kuni
Flight Operations | 2717 - Data Tech 09/30/18 | accepted | 3 | 1810 | XS | 1 | Nicholas Price |  |  | 100%
Flight Operations | 2718 - BVLOS CONOPS Document | accepted | 3 | 1809 | S | 2 | Helen Kuni
LARI | 2719 - C# GUI Tutorial (copy) | accepted | 3 | 1811 | M | 3 | Emelia Hughes
Collision Awareness | 272 – Unit Testing Background Training (copy) | accepted | 3 | 1405 | M | 3 | Ryan Valach
LARI | 2720 – Implement Saving and Loading for User Settings | dropped | #N/A | 1810 | M | 3 | Sita Manne
LARI | 2721 – Design GUI for Checklists | dropped | #N/A | 1903 | M | 3 | -
LARI | 2722 – Implement Data Structures for Checklists | accepted | 3 | 1811 | XL | 8 | Veen Oung
LARI | 2723 – Add Unit Testing for LARI | dropped | #N/A | 1903 | M | 3 | -
LARI | 2724 – Add Functionality to the Add Systems Window | accepted | 3 | 1811 | L | 5 | Sita Manne
LARI | 2725 – Add Functionality to the Add Components Window | dropped | #N/A | 1903 | L | 5 | Sidharth Lakshmanan
LARI | 2726 – Explore Excel Integration | accepted | 3 | 1811 | XS | 1 | Joshua Brockschmidt
LARI | 2727 – Add Fields to the Components Class | accepted | 3 | 1811 | M | 3 | Wendy Liu
LARI | 2728 – Refactor Equipage Data | accepted | 3 | 1811 | M | 3 | Joshua Brockschmidt
LARAMID | 2729 – LARAMID Pre-Ground Test part2 | accepted | 3 | 1810 | S | 2 | Chung Choi
Collision Awareness | 273 – Sprint 1404 Administration | accepted | 3 | 1404 | M | 3 | Christopher Lum
LARAMID | 2730 – LARAMID Thesis Preparation | accepted | 3 | 1901 | S | 2 | Chung Choi
LARAMID | 2731 – LARAMID Samwise Inspection and Repair part2 | accepted | 3 | 1810 | XS | 1 | Chung Choi |  | 80% | Landing gear problem
LARAMID | 2732 – LARAMID Samwise Inspection and Repair part2 (copy) | accepted | 3 | 1810 | XS | 1 | Josh Lee |  | 80% | Landing gear problem
LARAMID | 2733 – LARAMID Aerodynamics Simulation (copy) | accepted | 3 | 1902 | M | 3 | Austin Park
LARAMID | 2734 – LARAMID Pre-Ground Test part2 (copy) | accepted | 3 | 1810 | S | 2 | Yubin Kim
LARAMID | 2734 – LARAMID Pre-Ground Test part2 (copy) | accepted | 3 | 1810 | S | 2 | Austin Park
LARAMID | 2734 – LARAMID Pre-Ground Test part2 (copy) | accepted | 3 | 1810 | S | 2 | Cameron Tavakoli
LARAMID | 2734 – LARAMID Pre-Ground Test part2 (copy) | accepted | 3 | 1810 | S | 2 | Cathy Lee
LARAMID | 2734 – LARAMID Pre-Ground Test part2 (copy) | accepted | 3 | 1810 | S | 2 | Boda Li
LARAMID | 2734 – LARAMID Pre-Ground Test part2 (copy) | accepted | 3 | 1810 | S | 2 | Peyton Wells
General AFSL Lab | 2735 - Lab Safety Survey Checklist | accepted | 3 | 1810 | XS | 1 | Kelly Lee
General AFSL Lab | 2736 - Lab Safety Survey Checklist (copy) | accepted | 3 | 1811 | XS | 1 | Emelia Hughes
General AFSL Lab | 2737 - Perforce Visual Client (copy) | accepted | 0 | 1811 | S | 2 | Emelia Hughes
TRAPIS2 | 2738 - Waypoint Heading Calculations | accepted | 0 | 1810 | XS | 1 | Kelly Lee
General AFSL Lab | 2739 - Repair Anakin | accepted | 0 | 1810 | S | 2 | Josh Lee
General AFSL Lab | 2739 - Repair Anakin (copy) | accepted | 0 | 1810 | S | 2 | Liam Mortell
Collision Awareness | 274 – Sprint 1405 Administration | accepted | 3 | 1405 | M | 3 | Christopher Lum
General AFSL Lab | 2740 - Perforce Visual Client (copy) | accepted | 0 | 1811 | S | 2 | Liam Mortell
Flight Operations | 2741 -- Flight Test Attendance 10/06/19 | accepted | 3 | 1810 | S | 2 | Helen Kuni
Flight Operations | 2742 -- Flight Test Attendance 10/06/19 | accepted | 3 | 1810 | S | 2 | Rostyk Svitelskyi
Flight Operations | 2743 -- Flight Test Attendance 10/06/19 | accepted | 3 | 1810 | S | 2 | Nicholas Price
Flight Operations | 2744 -- Flight Test Attendance 10/06/19 | accepted | 3 | 1810 | S | 2 | Veen Oung
Flight Operations | 2745 -- Flight Test Attendance 10/06/19 | accepted | 3 | 1810 | S | 2 | Cameron Tavakoli
Flight Operations | 2746 - Data Tech 10/06/18 | accepted | 3 | 1810 | XS | 1 | Nicholas Price
General AFSL Lab | 2747 - Perforce Visual Client (copy) | accepted | 3 | 1810 | S | 2 | Cameron Tavakoli
General AFSL Lab | 2748 - Update control panel software | accepted | 3 | 1810 | M | 3 | Connor Kafka
General AFSL Lab | 2749 - Setup workflow for ArduPlane 3.9 update | accepted | 3 | 1810 | M | 3 | Connor Kafka
Collision Awareness | 275 – Australia: Research LaTeX Environment | accepted | 3 | 1406 | L | 5 | Richard Fukutome
LARAMID | 2750 – LARAMID Samwise Inspection and Repair part2 (copy) | accepted | 3 | 1810 | XS | 1 | Cameron Tavakoli |  | 80% | Landing gear problem
General AFSL Lab | 2751 – LARAMID Mini-Talon Safety Measurement Implementation | accepted | 3 | 1811 | XS | 1 | Peyton Wells
LARAMID | 2752 – LARAMID Technical Video for Project Presentation | dropped | #N/A | 1904 | L | 5 | Chung Choi
LARAMID | 2753 – LARAMID Mobius Camera Implementation | accepted | 3 | 1810 | S | 2 | Cathy Lee
LARAMID | 2754 – LARAMID Docking Frame Design (part5) | dropped | #N/A | 1904 | M | 3 | Chung Choi
General AFSL Lab | 2755 -- Security Camera System Integration | in backlog | 0 | 1908 | L | 5 | -
LARAMID | 2756 – LARAMID Mobius Camera Implementation (copy) | accepted | 3 | 1810 | XS | 1 | Kelly Lee
LARAMID | 2757 – LARAMID Dronekit-SITL Practice | accepted | 3 | 1811 | M | 3 | Sam Lee
LARAMID | 2758 – LARAMID Dronekit-SITL Practice (copy) | finished | 2 | 1810 | M | 3 | Nathan White
Visual Anchoring | 2759 – Choosing gimbal for visual Anchoring | accepted | 0 | 1810 | M | 3 | Rostyk Svitelskyi
Collision Awareness | 276 – Australia: Explore Forest Fire-Line Management Systems | accepted | 3 | 1406 | M | 3 | Daniel Ablog |  |  | move to sprint 1406
Visual Anchoring | 2760 – Visual Anchoring thesis | accepted | 0 | 1810 | M | 3 | Rostyk Svitelskyi
General AFSL Lab | 2761 – Perforce Visual Client (copy) | accepted | 3 | 1811 | S | 2 | Austin Park
General AFSL Lab | 2762 – Perforce Visual Client (copy) | accepted | 3 | 1810 | S | 2 | John Choi
General AFSL Lab | 2763 – Perforce Visual Client (copy) | accepted | 3 | 1810 | S | 2 | Cathy Lee
General AFSL Lab | 2764 – Perforce Visual Client (copy) | dropped | #N/A | 1905 | S | 2 | -
General AFSL Lab | 2765 – Perforce Visual Client (copy) | accepted | 3 | 1811 | S | 2 | Peyton Wells
General AFSL Lab | 2766 – Perforce Visual Client (copy) | accepted | 3 | 1811 | S | 2 | Yubin Kim
General AFSL Lab | 2767 – Perforce Visual Client (copy) | dropped | #N/A | 1905 | S | 2 | -
General AFSL Lab | 2768 – Perforce Visual Client (copy) | dropped | #N/A | 1905 | S | 2 | -
LARAMID | 2769– LARAMID Plane Rendezvous Control Algorithms | dropped | #N/A | 1906 | L | 5 | -
Collision Awareness | 277 – Australia: Prototype Forest Fire-Line Identification System | accepted | 3 | 1405 | L | 5 | Keisuke Tsujita |  |  | will finish today
LARAMID | 2772– LARAMID Frodo Inspection and Repair | accepted | 3 | 1810 | XS | 1 | Norman Lei
LARAMID | 2773– LARAMID Frodo Inspection and Repair (copy) | accepted | 3 | 1810 | XS | 1 | Cameron Tavakoli
LARAMID | 2774– LARAMID Flight Data Plotting | accepted | 3 | 1811 | S | 2 | Chung Choi
LARAMID | 2775– LARAMID Ground Test Structure Build | accepted | 3 | 1811 | XS | 1 | Chung Choi
LARAMID | 2776– LARAMID Electromagnet Testing and Replacement | accepted | 3 | 1810 | XS | 1 | Chung Choi
LARAMID | 2777– LARAMID Flight Data Plotting (copy) | accepted | 3 | 1811 | S | 2 | Yubin Kim
LARAMID | 2777– LARAMID Flight Data Plotting (copy) | accepted | 3 | 1811 | S | 2 | Peyton Wells
Flight Operations | 2778 -- Flight Test Attendance 10/13/18 | accepted | 3 | 1810 | S | 2 | Helen Kuni
LARAMID | 2778– LARAMID Ground Test Structure Build (copy) | accepted | 3 | 1810 | S | 2 | Austin Park
Flight Operations | 2779 -- Flight Test Attendance 10/13/18 | accepted | 3 | 1810 | S | 2 | Rostyk Svitelskyi
Australia Bushfire Monitoring | 278 – Australia: Prototype Forest Fire Propagation Model | dropped | #N/A | 1411 | XL | 8 | -
Flight Operations | 2780 -- Flight Test Attendance 10/13/18 | accepted | 3 | 1810 | S | 2 | Liam Mortell
Flight Operations | 2781- Flight Test Attendance 10/13/18 | accepted | 3 | 1810 | S | 2 | Zech Latimer
Flight Operations | 2782 -- Flight Test Attendance 10/13/18 | accepted | 3 | 1810 | S | 2 | Kelly Lee
Flight Operations | 2783 -- Flight Test Attendance 10/13/18 | accepted | 3 | 1810 | S | 2 | Stephanie Huerta-Ramirez
Flight Operations | 2784 -- Flight Test Attendance 10/13/18 | accepted | 3 | 1810 | S | 2 | Nicholas Price
Flight Operations | 2785 - Data Tech 10/13/18 | accepted | 3 | 1810 | XS | 1 | Kelly Lee
General AFSL Lab | 2786 - Battery Soldering | accepted | 3 | 1811 | XS | 1 | Dylan Hoff
General AFSL Lab | 2787 - Pegboard Installation | accepted | 3 | 1902 | M | 3 | Sean Carda
Flight Operations | 2788 - Anakin Postmortem | dropped | #N/A | 1903 | M | 3 | Nicholas Price
Flight Operations | 2789 - Fixed Wing Landing Gear – Initial Research & Design | accepted | 3 | 1811 | S | 2 | Josh Lee
Collision Awareness | 279 – Australia: Research Swinglet UAS | accepted | 3 | 1406 | M | 3 | Aleksandr Tereshchenkov
Flight Operations | 2790 - Fixed Wing Landing Gear – Initial Research & Design (copy) | accepted | 3 | 1811 | S | 2 | Liam Mortell
Flight Operations | 2791 - Anakin Repairs | accepted | 3 | 1810 | XS | 1 | Kelly Lee
Flight Operations | 2792 - Anakin Repairs (copy) | accepted | 3 | 1810 | XS | 1 | Stephanie Huerta-Ramirez
General AFSL Lab | 2793 - Lab Safety Survey Checklist (copy) | accepted | 3 | 1903 | XS | 1 | Christopher Lum
General AFSL Lab | 2794 - Lab Safety Survey Checklist (copy) | accepted | 3 | 1903 | XS | 1 | Helen Kuni
CellNav | 2795 - CellNav Conops | accepted | 3 | 1810 | M | 3 | Matthew Davis
CellNav | 2796 - CellNav T-Mobile Presentation Slides | accepted | 3 | 1810 | S | 2 | Matthew Davis
CellNav | 2797 - CellNav System Signal Path Diagram | accepted | 3 | 1810 | S | 2 | Matthew Davis
Visual Anchoring | 2798 - Repair Gimbals | accepted | 3 | 1810 | S | 2 | Nicholas Price
Visual Anchoring | 2799 - Camera/Gimbal Protection V.1 | accepted | 3 | 1810 | S | 2 | Nicholas Price |  |  | 50% as of 10/16
Collision Awareness | 280 – Australia: Research Swinglet Software | dropped | #N/A | 1408 | M | 3 | Noel Kimber |  |  | 75%
General AFSL Lab | 2800 - Solar Plane Part 2 | stretch goal | 4 | 1908 | XL | 8 | Nicholas Price
Flight Operations | 2801 - FUNRA Flight Testing and Troubleshooting | dropped | #N/A | 1811 | L | 5 | Dylan Hoff
Flight Operations | 2802 - Anakin Postmortem (Copy) | dropped | #N/A | 1811 | M | 3 | Kelly Lee
Flight Operations | 2803 - Anakin Postmortem (Copy) | dropped | #N/A | 1811 | M | 3 | Liam Mortell
Flight Operations | 2804 - Anakin Repairs (copy) | dropped | #N/A | 1903 | XS | 1 | -
Flight Operations | 2804- Flight Test Attendance 10/20/18 | accepted | 3 | 1810 | S | 2 | Helen Kuni
Flight Operations | 2805- Flight Test Attendance 10/20/18 | accepted | 3 | 1810 | S | 2 | Rostyk Svitelskyi
LARAMID | 2805– LARAMID Frodo Inspection and Repair (copy) | accepted | 3 | 1810 | XS | 1 | Josh Lee
Flight Operations | 2806- Flight Test Attendance 10/20/18 | accepted | 3 | 1810 | S | 2 | Nicholas Price
LARAMID | 2806– LARAMID Electromagnet Testing and Replacement (copy) | accepted | 3 | 1810 | XS | 1 | Cameron Tavakoli
Flight Operations | 2807- Flight Test Attendance 10/20/18 | accepted | 3 | 1810 | S | 2 | Josh Lee
LARAMID | 2807– LARAMID Ultrasonic Sensor Testing and Control | accepted | 3 | 1903 | M | 3 | Cathy Lee
Flight Operations | 2808- Flight Test Attendance 10/20/18 | accepted | 3 | 1810 | S | 2 | Liam Mortell
LARAMID | 2808– LARAMID Ultrasonic Sensor Testing and Control (copy) | dropped | #N/A | 1811 | M | 3
Flight Operations | 2809- Flight Test Attendance 10/20/18 | accepted | 3 | 1810 | S | 2 | Houyu Dong
LARAMID | 2809– LARAMID CAD Modeling | accepted | 3 | 1811 | S | 2 | John Choi
Australia Bushfire Monitoring | 281 – Australia: Fake Fire-Line Generation | dropped | #N/A | 1411 | L | 5 | Justin Yantus
Flight Operations | 2810 - Data Tech 10/20/18 | accepted | 3 | 1810 | XS | 1 | Nicholas Price
LARAMID | 2811– LARAMID Ground Test Structure Build (copy) | accepted | 3 | 1810 | XS | 1 | Yubin Kim
LARAMID | 2811– LARAMID Ground Test Structure Build (copy) | accepted | 3 | 1810 | XS | 1 | Norman Lei
LARAMID | 2811– LARAMID Ground Test Structure Build (copy) | accepted | 3 | 1810 | XS | 1 | Chung Choi
General AFSL Lab | 2812– Perforce Visual Client (copy) | dropped | #N/A | 1905 | S | 2 | -
General AFSL Lab | 2813– Perforce Visual Client (copy) | accepted | 3 | 1811 | S | 2 | Sean Carda
General AFSL Lab | 2814 – Perforce Visual Client (copy) | dropped | #N/A | 1905 | S | 2 | -
LARAMID | 2815 – LARAMID Pre-Ground Test part3 | accepted | 3 | 1810 | S | 2 | Chung Choi
LARAMID | 2816 – LARAMID Pre-Ground Test part3 (copy) | accepted | 3 | 1810 | S | 2 | Yubin Kim
LARAMID | 2816 – LARAMID Pre-Ground Test part3 (copy) | accepted | 3 | 1810 | S | 2 | Cathy Lee
LARAMID | 2816 – LARAMID Pre-Ground Test part3 (copy) | accepted | 3 | 1810 | S | 2 | Cameron Tavakoli
LARAMID | 2816 – LARAMID Pre-Ground Test part3 (copy) | accepted | 3 | 1810 | S | 2 | Sean Carda
LARAMID | 2816 – LARAMID Pre-Ground Test part3 (copy) | accepted | 3 | 1810 | S | 2 | John Choi
LARAMID | 2816 – LARAMID Pre-Ground Test part3 (copy) | accepted | 3 | 1810 | S | 2 | Norman Lei
LARAMID | 2816 – LARAMID Pre-Ground Test part3 (copy) | accepted | 3 | 1810 | S | 2 | Boda Li
LARAMID | 2817 – LARAMID Autonomous Vehicle Software Troubleshooting Manual | dropped | #N/A | 1905 | S | 2 | -
LARAMID | 2818 – LARAMID Autonomous Vehicle Software Troubleshooting Manual (copy) | dropped | #N/A | 1905 | S | 2 | -
LARAMID | 2819 – LARAMID Ultrasonic Sensor Test | dropped | #N/A | 1811 | M | 3
Collision Awareness | 282 – Perforce Shelf Sets | accepted | 3 | 1405 | S | 2 | Christopher Lum
LARAMID | 2820 – LARAMID Ultrasonic Sensor Test (copy) | dropped | #N/A | 1811 | M | 3
LARAMID | 2821– LARAMID Frodo Carbon Fiber Installed Under Metal Plates | accepted | 3 | 1810 | XS | 1 | Josh Lee
LARAMID | 2822– LARAMID Frodo Carbon Fiber Installed Under Metal Plates (Copy) | accepted | 3 | 1810 | XS | 1 | Norman Lei
General AFSL Lab | 2824 - Custom arduplane flight mode 3.9 updates | accepted | 3 | 1811 | S | 2 | Connor Kafka
Visual Anchoring | 2825 – Investigate feasibility of using guided mode for visual anchoring | accepted | 3 | 1811 | M | 3 | Connor Kafka
LARI | 2826 - Add Preliminary Component Tracker Functionality | accepted | 3 | 1810 | M | 3 | Sita Manne
LARI | 2826 – Add Preliminary Systems View Functionality | accepted | 3 | 1811 | S | 2 | Sita Manne
LARI | 2827 – Populate Components Table | accepted | 3 | 1904 | M | 3 | Veen Oung
LARI | 2828 – Add Preliminary Systems View Functionality (copy) | accepted | 3 | 1811 | M | 3 | Joshua Brockschmidt
LARI | 2829 – Add Component View Button Functionality | accepted | 3 | 1905 | L | 5 | Tina Li
Visual Anchoring | 283 – ScanEagle Simulator: System Architecture | accepted | 3 | 1406 | M | 3 | Taylor Campbell
LARAMID | 2830 – LARAMID Electromagnet Control with Transmitter | dropped | #N/A | 1905 | S | 2 | -
LARAMID | 2831 – LARAMID Updating Aircraft Manual | accepted | 3 | 1812 | XS | 1 | Norman Lei
LARAMID | 2832 – LARAMID Coupled Aircraft Modeling | accepted | 3 | 1902 | M | 3 | Chung Choi
LARAMID | 2833– LARAMID Ground Test Structure Build part2 | accepted | 3 | 1811 | S | 2 | Chung Choi
LARAMID | 2834 LARAMID Ground Test Structure Build part2 (copy) | accepted | 3 | 1811 | S | 2 | Yubin Kim
LARAMID | 2835 LARAMID Ground Test Structure Build part2 (copy) | accepted | 3 | 1811 | S | 2 | Austin Park
Flight Operations | 2836 -- Flight Test Attendance 11/18/18 | accepted | 3 | 1811 | S | 2 | Helen Kuni
LARAMID | 2836– LARAMID Frodo repair | accepted | 3 | 1811 | XS | 1 | Cameron Tavakoli
Flight Operations | 2837 -- Flight Test Attendance 11/18/18 | accepted | 3 | 1811 | S | 2 | Chung Choi
LARAMID | 2837– LARAMID Flight preparation | accepted | 3 | 1811 | S | 2 | Norman Lei
Flight Operations | 2838 -- Flight Test Attendance 11/18/18 | accepted | 3 | 1811 | S | 2 | Nicholas Price
LARAMID | 2838 LARAMID Flight preparation (copy) | accepted | 3 | 1811 | S | 2 | Boda Li
Flight Operations | 2839 -- Flight Test Attendance 11/18/18 | accepted | 3 | 1811 | S | 2 | Veen Oung
LARAMID | 2839– LARAMID Electromagnet manual | accepted | 3 | 1811 | XS | 1 | Sean Carda
Visual Anchoring | 284 – ScanEagle Simulator: Plant Model | accepted | 3 | 1504 | M | 3 | Daniel Ablog | 1 | 100%
Flight Operations | 2840 -- Flight Test Attendance 11/18/18 | accepted | 3 | 1811 | S | 2 | Dylan Hoff
LARAMID | 2840– LARAMID Flight test plan | accepted | 3 | 1811 | XS | 1 | Chung Choi
Flight Operations | 2841 - Data Tech 11/18/18 | accepted | 3 | 1811 | XS | 1 | Nicholas Price
Visual Anchoring | 2841 – Visual Anchoring move onto Tedd | accepted | 3 | 1811 | S | 1 | Rostyk Svitelskyi
Visual Anchoring | 2842 – Visual Anchoring thesis (copy) | accepted | 3 | 1811 | M | 3 | Rostyk Svitelskyi
Visual Anchoring | 2843 – Visual Anchoring Condor setup | accepted | 3 | 1811 | XS | 1 | Rostyk Svitelskyi
Visual Anchoring | 2844 – Visual Anchoring Tedd PID tuning | dropped | #N/A | 1811 | XS | 1 | Rostyk Svitelskyi
LARAMID | 2845 – LARAMID flight test setup | accepted | 3 | 1811 | XS | 1 | Rostyk Svitelskyi
General AFSL Lab | 2846 – Perforce Visual Client (copy) | accepted | 3 | 1812 | S | 2 | Yixin Xu
CellNav | 2847 - CellNav- LTE bands research | accepted | 3 | 1811 | M | 3 | Kelly Lee
CellNav | 2847 - CellNav- LTE bands research(copy) | accepted | 3 | 1811 | M | 3 | Firn Tieanklin
Flight Operations | 2847 -- Flight Test Attendance 11/25/18 | accepted | 3 | 1811 | S | 2 | Helen Kuni
Flight Operations | 2848 - Data Tech documentation | accepted | 3 | 1811 | XS | 1 | Kelly Lee
Flight Operations | 2848 -- Flight Test Attendance 11/25/18 | accepted | 3 | 1811 | S | 2 | Nicholas Price
LARI | 2849 – Add Method for Removing Systems from Equipage | in backlog | 0 | 1908 | S | 2 | -
Flight Operations | 2849 -- Flight Test Attendance 11/25/18 | accepted | 3 | 1811 | S | 2 | Rostyk Svitelskyi
Visual Anchoring | 285 – ScanEagle Simulator: Joystick Interface | accepted | 3 | 1406 | M | 3 | Taylor Campbell
Flight Operations | 2850 -- Flight Test Attendance 11/25/18 | accepted | 3 | 1811 | S | 2 | Chung Choi
Flight Operations | 2851 -- Flight Test Attendance 11/25/18 | accepted | 3 | 1811 | S | 2 | Norman Lei
Flight Operations | 2852 -- Flight Test Attendance 11/25/18 | accepted | 3 | 1811 | S | 2 | Boda Li
Flight Operations | 2853 -- Flight Test Attendance 11/25/18 | accepted | 3 | 1811 | S | 2 | Josh Lee
Flight Operations | 2854 -- Flight Test Attendance 11/25/18 | accepted | 3 | 1811 | S | 2 | Veen Oung
Flight Operations | 2855 - Data Tech 11/25/18 | accepted | 3 | 1811 | XS | 1 | Kelly Lee
CellNav | 2856 - Look into block edit for Trello | accepted | 3 | 1811 | XS | 1 | Pranav Natarajan
CellNav | 2857 - Look into templates for Trello cards | accepted | 3 | 1811 | M | 3 | Pranav Natarajan
General AFSL Lab | 2858 – Tool Peg Board | accepted | 3 | 1811 | M | 3 | Sean Carda
General AFSL Lab | 2859 – Tool Peg Board (Copy) | accepted | 3 | 1811 | S | 2 | Nicholas Price
Visual Anchoring | 286 – ScanEagle Simulator: X-Plane Interface | accepted | 3 | 1504 | L | 5 | Noel Kimber
Flight Operations | 2860 -- Flight Test Attendance 12/01/18 | accepted | 3 | 1812 | S | 2 | Helen Kuni
Flight Operations | 2861 -- Flight Test Attendance 12/01/18 | accepted | 3 | 1812 | S | 2 | Rostyk Svitelskyi
Flight Operations | 2862 -- Flight Test Attendance 12/01/18 | accepted | 3 | 1812 | S | 2 | Boda Li
Flight Operations | 2863 -- Flight Test Attendance 12/01/18 | accepted | 3 | 1812 | S | 2 | Nicholas Price
Flight Operations | 2864 - Data Tech 12/01/18 | accepted | 3 | 1812 | XS | 1 | Kelly Lee
Flight Operations | 2865 - Flight Ops Administration (1811) | accepted | 3 | 1811 | L | 5 | Helen Kuni
CellNav | 2866 – CellNav Trello Tasks(Matt,5) | accepted | 2 | 1811 | XL | 8 | Matthew Davis
CellNav | 2867 – CellNav Trello Tasks(Connor,5) | accepted | 2 | 1811 | L | 5 | Connor Kafka
CellNav | 2868 – CellNav Trello Tasks(Connor,1) | accepted | 2 | 1811 | XS | 1 | Connor Kafka
CellNav | 2869 – CellNav Trello Tasks(Sita,2) | accepted | 2 | 1811 | S | 2 | Sita Manne
Collision Awareness | 287 – Australia: Forest Fire-Line Identification System Homework | accepted | 3 | 1406 | M | 3 | Keisuke Tsujita
General AFSL Lab | 2870 – Perforce Visual Client (copy) | dropped | #N/A | 1905 | S | 2 | -
General AFSL Lab | 2871 - Robust Research Platform Proposal Budgeting | accepted | 3 | 1811 | S | 2 | Houyu Dong
FUNRA | 2872 - FUNRA Hardware Troubleshooting | accepted | 3 | 1811 | XS | 1 | Zech Latimer
General AFSL Lab | 2873 – Perforce Visual Client (copy) | accepted | 3 | 1812 | S | 2 | Zech Latimer
Flight Operations | 2874 - Fixed Wing Landing Gear – Initial Research & Design (copy) | accepted | 3 | 1811 | S | 2 | Zech Latimer
General AFSL Lab | 2875 - Research alternative aircraft repair methods | accepted | 3 | 1811 | S | 2 | Liam Mortell
LARI | 2876 — Write Unit Tests for Checklist Data Structures | dropped | #N/A | 1902 | L | 5 | -
General AFSL Lab | 2877 — Security Camera System Integration | accepted | 3 | 1902 | S | 2 | Joshua Brockschmidt
General AFSL Lab | 2877 — Security Camera System Integration (Copy) | dropped | #N/A | 1903 | M | 3 | -
LARI | 2878 — Create Data Structure for Timestamped Data (LARI) | dropped | #N/A | 1904 | L | 5 | - |  |  | Not sure if this is necessary, do not pickup
LARI | 2879 — Design GUI for Viewing and Editing Timestamped Data | dropped | #N/A | 1904 | M | 3 | - |  |  | Not sure if this is necessary, do not pickup
Collision Awareness | 288 – Numerical Validation of Integration of Position Probabilities Over An Arbitrary Volume | accepted | 3 | 1406 | L | 5 | Henry Qin |  |  | 90% Need to fix directory issues and code review
General AFSL Lab | 2881 – Organize Misc. Box of Parts | accepted | 3 | 1902 | XS | 1 | Helen Kuni
LARI | 2882 — Setup Continuous Integration Tool (copy) | accepted | 3 | 1903 | L | 5 | Wasif Siddique
General AFSL Lab | 2883 – Organize/Modify Charging Station | accepted | 3 | 1903 | S | 2 | Jaspreet Sidhu
General AFSL Lab | 2884 – Wing Rack Build 2 | in backlog | 0 | 1908 | M | 3 | -
General AFSL Lab | 2885 – Skywalker 1900 Storage Rack Build | dropped | #N/A | 1901 | M | 3 | -
General AFSL Lab | 2886 – Perforce Visual Client (copy) | accepted | 3 | 1812 | S | 2 | Wasif Siddique
Collision Awareness | 289 – Airspace Conflict Calculator Test Case Generation | accepted | 3 | 1406 | M | 3 | Ryan Valach
General AFSL Lab | 290 – UW UAS Use Case Document | accepted | 3 | 1408 | M | 3 | Aleksandr Tereshchenkov
Collision Awareness | 291 – Software Best Practices Poster and Presentations (Session 5) | accepted | 3 | 1406 | M | 3 | Keisuke Tsujita |  |  | tell the group about your finding with the Matlab image processing toolbox. Plan on (4/24)
Collision Awareness | 292 – Sprint 1406 Administration | accepted | 3 | 1406 | M | 3 | Christopher Lum
Collision Awareness | 293 – WPF User Control for ConflictEntity (Integration into UW Solution) | in backlog | 0 | - | M | 3 | Dai Tsukada
Collision Awareness | 294 – Sprint 1407 Administration | accepted | 3 | 1407 | M | 3 | Christopher Lum
Collision Awareness | 295 – Error Propagation Bug | accepted | 3 | 1410 | L | 5 | Kevin Ueunten |  | 100%
Collision Awareness | 296 – IEEE Aerospace Conference Paper Writeup | accepted | 3 | 1410 | XL | 8 | Kevin Ueunten |  | 100%
Collision Awareness | 297 – IEEE Aerospace Conference Presentation and Logistics | accepted | 3 | 1502 | XL | 8 | Kevin Ueunten |  | 90%
Collision Awareness | 298 – Master’s Thesis 2 | accepted | 3 | 1410 | XL | 8 | Kevin Ueunten |  | 85%
General AFSL Lab | 299 – Migrate Perforce Server | accepted | 3 | 1408 | L | 5 | Dai Tsukada
General AFSL Lab | 300 – Perforce Visual Client | accepted | 3 | 1407 | S | 2 | Angel Rodriguez
General AFSL Lab | 301 – Perforce Visual Client (copy) | accepted | 3 | 1407 | S | 2 | Melanie Clark
General AFSL Lab | 302 – Perforce Visual Client (copy) | accepted | 3 | 1407 | S | 2 | Justin Taft
General AFSL Lab | 303 – Laboratory Setup | accepted | 3 | 1407 | M | 3 | Christopher Lum
Visual Anchoring | 304 – Autopilot Familiarization (position 1) | accepted | 3 | 1407 | M | 3 | Angel Rodriguez |  |  | 100%
Visual Anchoring | 305 – Autopilot Familiarization (position 2) | accepted | 3 | 1407 | M | 3 | Melanie Clark |  |  | 100%
Visual Anchoring | 306 – Autopilot Familiarization (position 3) | accepted | 3 | 1407 | M | 3 | Justin Taft |  |  | 70%
Visual Anchoring | 307 – Autopilot Documentation | in backlog | 0 | - | M | 3 | -
Visual Anchoring | 308 – Autopilot Simple Demonstration | accepted | 3 | 1410 | L | 5 | Alec Bueing | 1 | 80%
Visual Anchoring | 309 – Simple Camera System Familiarization (position 1) | accepted | 3 | 1407 | M | 3 | Keisuke Tsujita
Visual Anchoring | 310 – Simple Camera System Familiarization (position 2) | accepted | 3 | 1407 | M | 3 | Noel Kimber
Visual Anchoring | 311 – Simple Camera System Documentation | accepted | 3 | 1410 | L | 5 | Keisuke Tsujita |  | 90%
Visual Anchoring | 312 – Simple Camera System Simple Demonstration | dropped | #N/A | 1502 | M | 3 | - |  | 20%
Visual Anchoring | 313 – Autopilot Familiarization (Advanced) (position 1) | dropped | #N/A | 1502 | S | 2 | - |  | 70%
Visual Anchoring | 314 – Simple Camera System Familiarization (Advanced) | accepted | 3 | 1410 | M | 3 | Keisuke Tsujita |  | 90% | extension chort
Visual Anchoring | 315 – FoxTech Camera System Familiarization | accepted | 3 | 1501 | M | 3 | Keisuke Tsujita |  | 30%
General AFSL Lab | 316 – Airframe Selection | accepted | 3 | 1407 | L | 5 | Aleksandr Tereshchenkov
General AFSL Lab | 317 – AFSL Website Control | dropped | #N/A | 1410 | M | 3 | Justin Yantus |  | 10%
General AFSL Lab | 318 – Sprint 1407 Administration | accepted | 3 | 1407 | M | 3 | Christopher Lum
General AFSL Lab | 319 – Sprint 1408 Administration | accepted | 3 | 1408 | M | 3 | Christopher Lum
Australia Bushfire Monitoring | 320 – eMotion 2 Ground Station Familiarization | accepted | 3 | 1408 | M | 3 | Angel Rodriguez |  |  | 85%
Visual Anchoring | 321 – Pan/Tilt Gimbal System Creation | accepted | 3 | 1410 | L | 5 | Brendan Doyle Wade | 1 | 90%
Visual Anchoring | 322 – Camera Ground Station Software Setup and Proof of Concept | accepted | 3 | 1408 | L | 5 | Keisuke Tsujita
Visual Anchoring | 323 – Aircraft Construction (RC Configuration) | accepted | 3 | 1409 | L | 5 | Aleksandr Tereshchenkov |  |  | get clamps
Flight Operations | 324 – Aircraft Flight Testing Preparation and Legalities (RC Configuration) | accepted | 3 | 1410 | XL | 8 | Melanie Clark |  | 90% | talk to professor livne
Flight Operations | 325 – Aircraft Flight Testing (RC Configuration) | accepted | 3 | 1411 | M | 3 | Al Creigh |  | 85%
General AFSL Lab | 326 – Laboratory Setup (Part 2) | accepted | 3 | 1410 | M | 3 | Christopher Lum |  | 100%
Visual Anchoring | 327 – Autopilot Familiarization (Advanced) (position 2) | accepted | 3 | 1501 | S | 2 | Melanie Clark |  | 90%
Visual Anchoring | 328 – Autopilot Familiarization (Advanced) (position 3) | accepted | 3 | 1502 | M | 3 | Bryan Ghahremani |  | 95%
Flight Operations | 329 – Establish RC Pilot Training Course | in backlog | 0 | - | L | 5 | - |  | 80%
Visual Anchoring | 330 – Visual Anchoring: System Architecture | accepted | 3 | 1410 | S | 2 | Christopher Lum |  | 100%
Visual Anchoring | 331 – Visual Anchoring: RCAM Plant Model | accepted | 3 | 1410 | M | 3 | Christopher Lum | 1 | 100%
Visual Anchoring | 332 – Visual Anchoring: Joystick Interface | accepted | 3 | 1410 | M | 3 | Christopher Lum | 1 | 100%
Visual Anchoring | 333 – Visual Anchoring: X-Plane Interface | dropped | #N/A | 1410 | L | 5 | - |  | 50%
General AFSL Lab | 334 – Laboratory Safety | accepted | 3 | 1410 | M | 3 | Aleksandr Tereshchenkov |  | 100%
Mapping | 335 – Coordinate with Earth and Space Sciences | accepted | 3 | 1410 | M | 3 | Christopher Lum |  | 100%
General AFSL Lab | 336 – Sprint 1409 Administration | accepted | 3 | 1409 | M | 3 | Christopher Lum
General AFSL Lab | 337 – Sprint 1410 Administration | accepted | 3 | 1410 | L | 5 | Christopher Lum |  | 100%
General AFSL Lab | 338 – Project Branding | accepted | 3 | 1501 | S | 2 | Maxine Tan |  | 85%
Australia Bushfire Monitoring | 339 – Australia Results Consolidation | accepted | 3 | 1410 | M | 3 | Angel Rodriguez |  | 70%
Australia Bushfire Monitoring | 340 – Australia Ortho-Rectified Image | accepted | 3 | 1501 | L | 5 | Brian Carpenter |  | 100% | Alex S will present this
Australia Bushfire Monitoring | 341 – Orientation and Setup | accepted | 3 | 1409 | XS | 1 | Angel Rodriguez
Australia Bushfire Monitoring | 342 – Literature Review | accepted | 3 | 1409 | XS | 1 | Angel Rodriguez
Australia Bushfire Monitoring | 343 – Swinglet Familiarization | accepted | 3 | 1409 | XS | 1 | Angel Rodriguez
Australia Bushfire Monitoring | 344 – Swinglet Software Familiarization | accepted | 3 | 1409 | S | 2 | Angel Rodriguez
Australia Bushfire Monitoring | 345 – Design Flight Test Experiment | accepted | 3 | 1409 | S | 2 | Angel Rodriguez
Australia Bushfire Monitoring | 346 – Flight Test Experiment Execution | accepted | 3 | 1409 | XS | 1 | Angel Rodriguez
Australia Bushfire Monitoring | 347 – Flight Test Data Reduction and Analysis | accepted | 3 | 1409 | XS | 1 | Angel Rodriguez
Australia Bushfire Monitoring | 348 – Matlab Image Processing Toolbox Familiarization | accepted | 3 | 1409 | S | 2 | Angel Rodriguez
Australia Bushfire Monitoring | 349 – Computer Vision Fire Line Detection | accepted | 3 | 1409 | XS | 1 | Angel Rodriguez
Australia Bushfire Monitoring | 350 – Fire Propagation Model | accepted | 3 | 1409 | S | 2 | Angel Rodriguez
Australia Bushfire Monitoring | 351 – Fire Simulation and Analysis | accepted | 3 | 1409 | S | 2 | Angel Rodriguez
Australia Bushfire Monitoring | 352 – Results Dissemination (Paper Publication) | accepted | 3 | 1409 | S | 2 | Angel Rodriguez
Australia Bushfire Monitoring | 353 – Results Dissemination (Project Presentation) | accepted | 3 | 1409 | XS | 1 | Angel Rodriguez
Australia Bushfire Monitoring | 354 – Orientation and Setup | accepted | 3 | 1409 | XS | 1 | Brian Carpenter
Australia Bushfire Monitoring | 355 – Literature Review | accepted | 3 | 1409 | XS | 1 | Brian Carpenter
Australia Bushfire Monitoring | 356 – Swinglet Familiarization | accepted | 3 | 1409 | XS | 1 | Brian Carpenter
Australia Bushfire Monitoring | 357 – Swinglet Software Familiarization | accepted | 3 | 1409 | S | 2 | Brian Carpenter
Australia Bushfire Monitoring | 358 – Design Flight Test Experiment | accepted | 3 | 1409 | S | 2 | Brian Carpenter
Australia Bushfire Monitoring | 359 – Flight Test Experiment Execution | accepted | 3 | 1409 | XS | 1 | Brian Carpenter
Australia Bushfire Monitoring | 360 – Flight Test Data Reduction and Analysis | accepted | 3 | 1409 | XS | 1 | Brian Carpenter
Australia Bushfire Monitoring | 361 – Matlab Image Processing Toolbox Familiarization | accepted | 3 | 1409 | S | 2 | Brian Carpenter
Australia Bushfire Monitoring | 362 – Computer Vision Fire Line Detection | accepted | 3 | 1409 | XS | 1 | Brian Carpenter
Australia Bushfire Monitoring | 363 – Fire Propagation Model | accepted | 3 | 1409 | S | 2 | Brian Carpenter
Australia Bushfire Monitoring | 364 – Fire Simulation and Analysis | accepted | 3 | 1409 | S | 2 | Brian Carpenter
Australia Bushfire Monitoring | 365 – Results Dissemination (Paper Publication) | accepted | 3 | 1409 | S | 2 | Brian Carpenter
Australia Bushfire Monitoring | 366 – Results Dissemination (Project Presentation) | accepted | 3 | 1409 | XS | 1 | Brian Carpenter
Australia Bushfire Monitoring | 367 – Orientation and Setup | accepted | 3 | 1409 | XS | 1 | Alexander Summers
Australia Bushfire Monitoring | 368 – Literature Review | accepted | 3 | 1409 | XS | 1 | Alexander Summers
Australia Bushfire Monitoring | 369 – Swinglet Familiarization | accepted | 3 | 1409 | XS | 1 | Alexander Summers
Australia Bushfire Monitoring | 370 – Swinglet Software Familiarization | accepted | 3 | 1409 | S | 2 | Alexander Summers
Australia Bushfire Monitoring | 371 – Design Flight Test Experiment | accepted | 3 | 1409 | S | 2 | Alexander Summers
Australia Bushfire Monitoring | 372 – Flight Test Experiment Execution | accepted | 3 | 1409 | XS | 1 | Alexander Summers
Australia Bushfire Monitoring | 373 – Flight Test Data Reduction and Analysis | accepted | 3 | 1409 | XS | 1 | Alexander Summers
Australia Bushfire Monitoring | 374 – Matlab Image Processing Toolbox Familiarization | accepted | 3 | 1409 | S | 2 | Alexander Summers
Australia Bushfire Monitoring | 375 – Computer Vision Fire Line Detection | accepted | 3 | 1409 | XS | 1 | Alexander Summers
Australia Bushfire Monitoring | 376 – Fire Propagation Model | accepted | 3 | 1409 | S | 2 | Alexander Summers
Australia Bushfire Monitoring | 377 – Fire Simulation and Analysis | accepted | 3 | 1409 | S | 2 | Alexander Summers
Australia Bushfire Monitoring | 378 – Results Dissemination (Paper Publication) | accepted | 3 | 1409 | S | 2 | Alexander Summers
Australia Bushfire Monitoring | 379 – Results Dissemination (Project Presentation) | accepted | 3 | 1409 | XS | 1 | Alexander Summers
General AFSL Lab | 380 – Sprint Metrics | accepted | 3 | 1802 | XL | 8 | Taehan Kook
General AFSL Lab | 381 – UW Engineering Societies Fair | accepted | 3 | 1410 | XS | 1 | Christopher Lum |  | 100%
General AFSL Lab | 382 – Apply BSD Software License | in backlog | 0 | - | XS | 1 | -
General AFSL Lab | 383 – Clean Up User Stories | accepted | 3 | 1411 | S | 2 | Christopher Lum |  | 100%
Visual Anchoring | 384 – APM Firmware Preparation/Installation | accepted | 3 | 1410 | M | 3 | Alec Bueing |  | 100%
Visual Anchoring | 385 – APM Editing/Building Code Via Visual Studio 2008-2013 | accepted | 3 | 1411 | XL | 8 | Erli Sheng |  | 70% | Dan Ablog tried this but got stuck.
General AFSL Lab | 386 – Update Laboratory Computing Infrastructure | accepted | 3 | 1411 | S | 2 | Christopher Lum |  | 100%
General AFSL Lab | 387 – Purchase Laboratory Computing Infrastructure | accepted | 3 | 1502 | XL | 8 | Alec Bueing |  | 100%
Australia Bushfire Monitoring | 388 – Australia Conference Paper (Position 1) | accepted | 3 | 1503 | XL | 8 | Angel Rodriguez |  | 20%
General AFSL Lab | 389 – TVW Movie/TV Piece | accepted | 3 | 1411 | XS | 1 | Jeremy Brenner |  | 30%
General AFSL Lab | 390 – AFSL YouTube Channel | accepted | 3 | 1412 | S | 2 | Jeremy Brenner |  | 10%
General AFSL Lab | 390 – AFSL YouTube Channel | accepted | 3 | 1612 | M | 3 | Karine Chen |  | 100%
Collision Awareness | 391 – IEEE Paper Review and Write Introduction | accepted | 3 | 1410 | M | 3 | Al Creigh |  | 100%
Collision Awareness | 392 – IEEE Paper Review | accepted | 3 | 1410 | M | 3 | Keisuke Tsujita |  | 100%
General AFSL Lab | 393 – Research Sensors for UAS Measurement of Snowpack and Ecology | dropped | #N/A | 1504 | L | 5 | Cory Hage |  | 85%
General AFSL Lab | 394 – Research Student Technology Fund (STF) Resources Pertinent to UAS Research | in backlog | 0 | - | S | 2 | - |  | 5%
Visual Anchoring | 395 – Visual Anchoring Literature Review | accepted | 3 | 1410 | M | 3 | Henry Qin |  | 80% | Presenting on November 20th
General AFSL Lab | 396 – Matlab Unit Testing Initial Research | in backlog | 0 | - | L | 5 | Matthew Jones
General AFSL Lab | 397 – LaTeX Environment Setup | accepted | 3 | 1410 | M | 3 | Brian Chang |  | 100%
General AFSL Lab | 398 – LaTeX References/Bibliography Research | in backlog | 0 | - | M | 3 | - |  | 75%
General AFSL Lab | 399 – Perforce Visual Client (copy) | accepted | 3 | 1601 | XS | 1 | Madison Mackenzie |  | 90%
Visual Anchoring | 400 – Visual Anchoring: RCAM Trim Solution for Orbit | in backlog | 0 | - | L | 5 | Hao Ruan
Visual Anchoring | 401 – Visual Anchoring: RCAM Linear Orbit Model | in backlog | 0 | - | L | 5 | Hao Ruan
Visual Anchoring | 402 – Visual Anchoring Literature Review (copy) | accepted | 3 | 1410 | M | 3 | Ryan Valach |  | 100%
Visual Anchoring | 403 – UW UAS Wind Tunnel Test Feasibility Study | accepted | 3 | 1410 | M | 3 | Aleksandr Tereshchenkov |  | 100%
Visual Anchoring | 404 – UW UAS Wind Tunnel Test Model Preparation | in backlog | 0 | - | XL | 8 | - |  | 65%
Visual Anchoring | 405 – UW UAS Wind Tunnel Test Plan Preparation | in backlog | 0 | - | XL | 8 | -
Visual Anchoring | 406 – UW UAS Wind Tunnel Test Execution | in backlog | 0 | - | XL | 8 | -
Visual Anchoring | 407 – UW UAS Wind Tunnel Test Data Reduction | in backlog | 0 | - |  | #N/A | -
Visual Anchoring | 408 – UW UAS Wind Tunnel Test Documentation | in backlog | 0 | - |  | #N/A | -
Flight Operations | 409 – FAA Certificate of Authorization (COA) for CONDOR | accepted | 3 | 1603 | XL | 8 | Christopher Lum |  | 75%
General AFSL Lab | 410 – Tabulate UW Course Evaluation Data | accepted | 3 | 1410 | S | 2 | Dana Fraij |  | 70%
General AFSL Lab | 411 – Reorganize UWUAS Depot | accepted | 3 | 1411 | S | 2 | Christopher Lum |  | 100%
General AFSL Lab | 412 – Document UWMatlab Install Procedure | accepted | 3 | 1411 | S | 2 | Christopher Lum |  | 100%
General AFSL Lab | 413 – Perforce Educational License Addition | accepted | 3 | 1501 | M | 3 | Jason Hung |  | 100%
Mapping | 414 – Backup Airframe Procurement and Construction | accepted | 3 | 1410 | M | 3 | Justin Yantus |  | 90%
General AFSL Lab | 415– UWMatlab Unit Testing Spreadsheet Creation and Population | in backlog | 0 | - | M | 3 | -
General AFSL Lab | 416– UW UAS Systems Audit | accepted | 3 | 1410 | M | 3 | Brendan Doyle Wade |  | 100%
Flight Operations | 417 – Aircraft Flight Testing (RC Configuration) (Position 2) | accepted | 3 | 1411 | M | 3 | Mason Steinbrueck |  | 50%
Mapping | 418 – Backup Airframe Procurement and Construction (Position 2) | accepted | 3 | 1410 | M | 3 | Maxine Tan |  | 80%
Australia Bushfire Monitoring | 419 – Australia Matlab Simulation Environment | accepted | 3 | 1501 | M | 3 | Alexander Summers |  | 75%
General AFSL Lab | 420 – Software Developer Background Training (Algorithm and Back End) (copy) | in backlog | 0 | - | L | 5 | - |  | 30%
General AFSL Lab | 421 – Aircraft Flight Testing Preparation and Legalities (RC Configuration) Helper | in backlog | 0 | - | M | 3 | -
Visual Anchoring | 422 – Matlab Image Processing Toolbox Familiarization | accepted | 3 | 1501 | L | 5 | Alec Bueing |  | 100%
General AFSL Lab | 423 – Perforce Server Security | in backlog | 0 | - | L | 5 | -
Visual Anchoring | 424 – OpenCV Familiarization | in backlog | 0 | - | L | 5 | - |  | 10% | strech goal??
Visual Anchoring | 425 – APM Data Logging | accepted | 3 | 1410 | L | 5 | Justin Taft |  | 90%
Mapping | 426 – Pixhawk Trigger Still Camera and Log GPS Position and Orientation | accepted | 3 | 1504 | XL | 8 | Aleksandr Tereshchenkov |  | 100%
General AFSL Lab | 427 – Research Sensors for UAS Measurement of Snowpack and Ecology (Position 2) | in backlog | 0 | - | M | 3 | -
General AFSL Lab | 428 – UWAA Fall Poster Session (2014) | accepted | 3 | 1411 | S | 2 | Christopher Lum |  | 100%
Visual Anchoring | 429 – Image Processing Algorithm Feature Level Design | accepted | 3 | 1411 | M | 3 | Ben Landes |  | 50%
General AFSL Lab | 430 – UAS Flight Path Planning for Visual Line Of Sight Operations for Snowpack Monitoring | accepted | 3 | 1411 | L | 5 | Robert Soo |  | 60%
Visual Anchoring | 431 – Visual Anchoring Literature Review (copy) | accepted | 3 | 1410 | M | 3 | Ben Landes |  | 60%
Visual Anchoring | 432 – Visual Anchoring: RCAM Plant Model Augment with Disturbances | accepted | 3 | 1501 | L | 5 | Christopher Lum |  | 100%
General AFSL Lab | 433 – Piper J-3 Training RC Aircraft Setup | accepted | 3 | 1410 | M | 3 | Mason Steinbrueck |  | 100%
General AFSL Lab | 434 – Aircraft Storage and Display | accepted | 3 | 1410 | XS | 1 | Christopher Lum |  | 100%
General AFSL Lab | 435 – New Team Member Orientation Document Creation | accepted | 3 | 1501 | M | 3 | Christopher Lum |  | 10%
General AFSL Lab | 436 – Perforce Visual Client (copy) | accepted | 3 | 1410 | XS | 1 | Alec Bueing |  | 100%
General AFSL Lab | 437 – Perforce Visual Client (copy) | accepted | 3 | 1411 | XS | 1 | Alexander Summers
General AFSL Lab | 438 – Perforce Visual Client (copy) | accepted | 3 | 1410 | XS | 1 | Ben Landes |  | 70%
General AFSL Lab | 439 – Perforce Visual Client (copy) | accepted | 3 | 1411 | XS | 1 | Brendan Doyle Wade |  | 100%
General AFSL Lab | 440 – Perforce Visual Client (copy) | accepted | 3 | 1410 | XS | 1 | Brian Carpenter |  | 100%
General AFSL Lab | 441 – Perforce Visual Client (copy) | accepted | 3 | 1410 | XS | 1 | Bryan Ghahremani |  | 100%
General AFSL Lab | 442 – Perforce Visual Client (copy) | accepted | 3 | 1410 | XS | 1 | Cory Hage |  | 10%
General AFSL Lab | 443 – Perforce Visual Client (copy) | accepted | 3 | 1410 | XS | 1 | Dana Fraij |  | 0%
General AFSL Lab | 444 – Perforce Visual Client (copy) | accepted | 3 | 1511 | XS | 1 | Carter Beamish |  | 100%
General AFSL Lab | 445 – Perforce Visual Client (copy) | accepted | 3 | 1410 | XS | 1 | Erli Sheng
General AFSL Lab | 446 – Perforce Visual Client (copy) | accepted | 3 | 1410 | XS | 1 | Hao Ruan
General AFSL Lab | 447 – Perforce Visual Client (copy) | accepted | 3 | 1410 | XS | 1 | Maxine Tan |  | 100%
General AFSL Lab | 448 – Perforce Visual Client (copy) | accepted | 3 | 1501 | XS | 1 | Sanjit Samra |  | 100%
General AFSL Lab | 449 – Perforce Visual Client (copy) | accepted | 3 | 1410 | XS | 1 | Randy Lirano |  | 100%
General AFSL Lab | 450 – Perforce Visual Client (copy) | accepted | 3 | 1410 | XS | 1 | Robert Soo |  | 100%
Australia Bushfire Monitoring | 451 – Bushfire Detection Depot Creation | accepted | 3 | 1411 | S | 2 | Christopher Lum |  | 100%
General AFSL Lab | 452 – Developer WebEx Account Setup (Copy) | accepted | 3 | 1410 | XS | 1 | Hao Ruan
Visual Anchoring | 453 – Visual Anchoring: RCAM Inner Loop Orbit Controller | accepted | 3 | 1503 | XL | 8 | Hao Ruan
Visual Anchoring | 454 – Upgrade UW X-Plane Plug-ins to VS2012 and X-Plane 10 | accepted | 3 | 1504 | L | 5 | Noel Kimber |  | 60%
General AFSL Lab | 455 – Field Testing Transportation Boxes (Part 1) | accepted | 3 | 1501 | M | 3 | Sanjit Samra |  | 100%
General AFSL Lab | 456 – GitHub Investigation and Preliminary Research | accepted | 3 | 1501 | M | 3 | Daniel Ablog |  | 100%
Visual Anchoring | 457 – Visual Anchoring Simulator Output to Google Earth | accepted | 3 | 1501 | M | 3 | Sanjit Samra |  | 100% | CL needs to fix names
Visual Anchoring | 458 – Orbit Controller Feature Level Design | accepted | 3 | 1501 | L | 5 | Dai Tsukada |  | 100%
Collision Awareness | 459 – UW-TV Interviews and Filming | accepted | 3 | 1410 | M | 3 | Christopher Lum |  | 100%
General AFSL Lab | 460 – AFSL Website Updates | descoped | 6 | 1608 | S | 2 | Arwa Sait |  | 5% | Facebook almost up
Mapping | 461 – TEDD Systems Integration | accepted | 3 | 1505 | M | 3 | Al Creigh |  | 80%
Mapping | 462 – Aerial Mapper Recovery System | accepted | 3 | 1501 | L | 5 | Henry Qin |  | 90%
Mapping | 463 – Plan and Execute Mt. Rainier Aerial Survey | in backlog | 0 | - | - | #N/A | -
Flight Operations | 464 – Aircraft Flight Testing Preparation and Legalities (UAS Configuration) | accepted | 3 | 1501 | XL | 8 | Melanie Clark |  | 80%
Flight Operations | 465 – Investigate Local Flight Testing Locations and Facilities | accepted | 3 | 1504 | XS | 1 | Maxine Tan |  | 100%
Flight Operations | 466 – Develop Flight Operations Policies and Procedures | accepted | 3 | 1411 | L | 5 | Maxine Tan |  | 60%
Flight Operations | 467 – UW UAS Wind Tunnel Test Model Preparation (Position 2) | in backlog | 0 | - | L | 5 | - |  | 75% | New part was polycarbonate and printed
General AFSL Lab | 468 – Sprint 1411 Administration | accepted | 3 | 1411 | L | 5 | Christopher Lum
General AFSL Lab | 469 – Add Desks to AERB 139 | accepted | 3 | 1411 | M | 3 | Alec Bueing
Australia Bushfire Monitoring | 470 – Australia Identify Conference and Create Skeleton Framework | accepted | 3 | 1501 | M | 3 | Angel Rodriguez |  | 90%
Mapping | 471 – Aerial Mapper Recovery System (Position 2) | accepted | 3 | 1501 | L | 5 | Ryan Valach |  | 90%
Visual Anchoring | 472 – Camera Image Example/Test Data | accepted | 3 | 1501 | L | 5 | Keisuke Tsujita |  | 5% | missing components
Visual Anchoring | 473 – Create UW Image Capture Application | accepted | 3 | 1505 | L | 5 | Justin Taft |  | 70% | may need to purchase a compatible capture card
Visual Anchoring | 474 – Image Processing Slant Range of Screen Pixels | accepted | 3 | 1501 | M | 3 | Jeremy Brenner |  | 50% | need camera
Visual Anchoring | 475 – Generate Visual Anchoring Demostrator Scenario and Project Vision | accepted | 3 | 1411 | M | 3 | Christopher Lum |  | 100%
Visual Anchoring | 476 – Pan/Tilt Camera Orientation Measurement | accepted | 3 | 1508 | XL | 8 | Ryan Valach | 1 | 90%
Visual Anchoring | 477 – Create UW Image Processing Application | dropped | #N/A | 1502 | L | 5 | Jeremy Brenner |  | 5% | interface block is setup.
Visual Anchoring | 478 – Create UW Visual Anchoring Data Fusion Algorithm | accepted | 3 | 1504 | M | 3 | Ryan Valach | 1 | 75% | pending code review
General AFSL Lab | 479 – Student Technology Fee Proposal | dropped | #N/A | 1902 | L | 5 | -
Visual Anchoring | 480 – Visual Anchoring: RCAM Outer Loop Controller | accepted | 3 | 1502 | L | 5 | Dai Tsukada |  | 100%
Visual Anchoring | 481 – Matlab Computer Vision Systems Toolbox Investigation | accepted | 3 | 1502 | M | 3 | Matthew Jones |  | 85% | Matthew Jones has this toolbox
Visual Anchoring | 482 – Setup X-Plane Simulator in AERB139 | accepted | 3 | 1501 | S | 2 | Christopher Lum |  | 100%
Visual Anchoring | 483 – Mission Planner Modifications (Simple) | in backlog | 0 | - | XL | 8 | - |  | 90%
Visual Anchoring | 484 – Mission Planner Modifications (Complex) | accepted | 3 | 1509 | L | 5 | Gage Winde |  | 80%
Visual Anchoring | 485 – PixHawk Custom Flight Mode (Simple) | accepted | 3 | 1507 | L | 5 | Gage Winde |  | 90%
Visual Anchoring | 486 – PixHawk Custom Flight Mode (Complex) | accepted | 3 | 1606 | XL | 8 | Gage Winde |  | 85% | waiting on vision processing system
Flight Operations | 487 – UWAA 3D Printing Investigation | accepted | 3 | 1411 | M | 3 | Aleksandr Tereshchenkov |  | 50%
Flight Operations | 488 – HAM Radio Operator Licensing | accepted | 3 | 1502 | M | 3 | Melanie Clark |  | 100%
Flight Operations | 489 – AFSL COA (Part 1) | accepted | 3 | 1503 | XL | 8 | Christopher Lum
Visual Anchoring | 490 – Image Processing Camera View in Inertial Frame | accepted | 3 | 1501 | L | 5 | Kevin Ueunten |  | 90% | need camera
General AFSL Lab | 491 – Move Lab from KWT102 to GUG105 (position 1) | accepted | 3 | 1412 | S | 2 | Christopher Lum |  |  | waiting on department to finish rennovations
Mapping | 492 – Aerial Mapper Systems Integration (position 2) | accepted | 3 | 1505 | M | 3 | Jason Hung |  | 75%
Visual Anchoring | 493 – Matlab Machine Vision Toolbox Investigation | accepted | 3 | 1504 | M | 3 | Melanie Clark | 1 | 75%
General AFSL Lab | 494 – Purchase Laboratory Computing Infrastructure (position 2) | accepted | 3 | 1502 | S | 2 | Bryan Ghahremani |  | 100%
General AFSL Lab | 495 – AFSL Website Updates (People Section) | accepted | 3 | 1412 | XS | 1 | Christopher Lum
General AFSL Lab | 496 – AFSL Website Updates (Facilities Section) | accepted | 3 | 1712 | XS | 1 | Karine Chen |  | 100%
General AFSL Lab | 497 – AFSL Website Updates (Research Section) | accepted | 3 | 1712 | XS | 1 | Karine Chen |  | 100%
General AFSL Lab | 498 – AFSL Website Updates (Publications Section) | accepted | 3 | 1712 | XS | 1 | Karine Chen |  | 100%
Flight Operations | 499 – FAA Certificate of Authorization (COA) for CONDOR – Identify Operations Location | accepted | 3 | 1503 | M | 3 | Keisuke Tsujita |  | 75%
General AFSL Lab | 500 – UWAA Fall Poster Session (2014 Helper 1) | accepted | 3 | 1411 | S | 2 | Brian Carpenter
General AFSL Lab | 501 – UWAA Fall Poster Session (2014 Helper 2) | accepted | 3 | 1411 | S | 2 | Angel Rodriguez
General AFSL Lab | 502 – UWAA Fall Poster Session (2014 Helper 3) | accepted | 3 | 1411 | S | 2 | Alexander Summers
General AFSL Lab | 503 – UWAA Fall Poster Session (2014 Helper 4) | accepted | 3 | 1411 | XS | 1 | Aleksandr Tereshchenkov
General AFSL Lab | 504 – UWAA Fall Poster Session (2014 Helper 5) | accepted | 3 | 1411 | XS | 1 | Brendan Doyle Wade
General AFSL Lab | 505 – UWAA Fall Poster Session (2014 Helper 6) | accepted | 3 | 1411 | XS | 1 | Kevin Ueunten
General AFSL Lab | 506 – UWAA Fall Poster Session (2014 Helper 7) | accepted | 3 | 1411 | XS | 1 | Bryan Ghahremani
General AFSL Lab | 507 – UWAA Fall Poster Session (2014 Helper 8) | accepted | 3 | 1411 | XS | 1 | Melanie Clark
General AFSL Lab | 508 – UWAA Fall Poster Session (2014 Helper 9) | accepted | 3 | 1411 | XS | 1 | Keisuke Tsujita
Flight Operations | 509 – Field Testing Transportation Boxes (Part 2) | accepted | 3 | 1608 | S | 2 | Arwa Sait |  | 35% | CONDOR box
General AFSL Lab | 510 – AFSL Website Updates (People Section) (Helper) | accepted | 3 | 1412 | XS | 1 | Justin Yantus
Visual Anchoring | 511 – CONDOR Ground Control Station Construction and Validation | accepted | 3 | 1605 | M | 3 | Alec Bueing |  | 90% | UPS is not functioning
Visual Anchoring | 512 – CONDOR RxMUX Integration | accepted | 3 | 1604 | M | 3 | Yifu Wang |  | 100%
Flight Operations | 513 – FAA Written Exam for Private Pilot Aircraft Certification | dropped | #N/A | 1609 | XL | 8 | Christopher Lum
Flight Operations | 514 – FAA Certificate of Authoriation (COA) for CONDOR – Register Aircraft | accepted | 3 | 1601 | L | 5 | Christopher Lum |  | 50%
General AFSL Lab | 515 – APM 2.6 Hardware-in-the-Loop Simulator | accepted | 3 | 1502 | L | 5 | Bryan Ghahremani |  | 90%
Visual Anchoring | 516 – CONDOR Camera Transmitter/Reciever Upgrade | in backlog | 0 | - | S | 2 | -
General AFSL Lab | 517 – Update Component Description Document | in backlog | 0 | - | L | 5 | -
Flight Operations | 518 – Integrate Backup Skywalker Aircraft into AFSL Systems | accepted | 3 | 1501 | M | 3 | Cory Hage
General AFSL Lab | 519 – Investigate Simulink APM Blockset | in backlog | 0 | - | M | 3 | - |  |  | optional
Flight Operations | 520 – Private Pilot Flight Simulator | accepted | 3 | 1502 | M | 3 | Al Creigh |  | 60% | Just need to demonstrate
Flight Operations | 521 – Flight Operations Work Items Part 1 | accepted | 3 | 1602 | M | 3 | Carter Beamish |  | 50% | Dub Cub?
General AFSL Lab | 522 – Undergraduate Research Conference Travel Award | in backlog | 0 | - | S | 2 | -
Flight Operations | 523 – Exploration Trip to Lester, WA | dropped | #N/A | 1501 | L | 5 | -
General AFSL Lab | 524 – Sprint 1412 Administration | accepted | 3 | 1412 | M | 3 | Christopher Lum
General AFSL Lab | 525 – Sprint 1501 Administration | accepted | 3 | 1501 | M | 3 | Christopher Lum |  | 100%
General AFSL Lab | 526 – Obtain HAM Radio Technician Class License (position 1) | accepted | 3 | 1412 | L | 5 | Christopher Lum
General AFSL Lab | 527 – Obtain HAM Radio Technician Class License (position 2) | accepted | 3 | 1412 | L | 5 | Melanie Clark
General AFSL Lab | 528 – Obtain HAM Radio Technician Class License (position 3) | in backlog | 0 | - | L | 5 | - |  | 50%
General AFSL Lab | 529 – Move Lab from KWT102 to GUG105 (position 2) | accepted | 3 | 1412 | XS | 1 | Alec Bueing
General AFSL Lab | 530 – Move Lab from KWT102 to GUG105 (position 3) | accepted | 3 | 1412 | XS | 1 | Melanie Clark
General AFSL Lab | 531 – Move Lab from KWT102 to GUG105 (position 4) | accepted | 3 | 1412 | XS | 1 | Erli Sheng
General AFSL Lab | 532 – Move Lab from KWT102 to GUG105 (position 5) | accepted | 3 | 1412 | XS | 1 | Keisuke Tsujita
General AFSL Lab | 533 – Move Lab from KWT102 to GUG105 (position 6) | accepted | 3 | 1412 | XS | 1 | Kevin Ueunten
General AFSL Lab | 534 – Perforce Visual Client (copy) | accepted | 3 | 1501 | XS | 1 | Matthew Jones |  | 100%
General AFSL Lab | 535 – Perforce Visual Client (copy) | accepted | 3 | 1503 | XS | 1 | Matthew Bolte
Flight Operations | 536 – Flight Operations Work Items Part 1 (Helper 1) | accepted | 3 | 1602 | XL | 8 | Andrew Jacobson |  | 85% | Need helper
Flight Operations | 537 – Flight Operations Work Items Part 1 (Helper 2) | accepted | 3 | 1602 | M | 3 | Daniel Varnum-Lowry
Visual Anchoring | 538 – Create UW Visual Anchoring Data Fusion Algorithm (Helper) | accepted | 3 | 1504 | M | 3 | Henry Qin |  | 75% | EE remoting in is a problem
General AFSL Lab | 539 – Obtain HAM Radio Technician Class License (position 4) | in backlog | 0 | - | L | 5 | - |  | 70% | Matt has the ARRL study book
General AFSL Lab | 540 – Generate Brochure for UWAA UAS Activities | accepted | 3 | 1501 | M | 3 | Christopher Lum |  | 100%
Visual Anchoring | 541 – PixHawk Custom Flight Mode (Simple) (Helper 1) | dropped | #N/A | 1510 | L | 5 | - |  | 30%
Flight Operations | 542 – FAA Certificate of Authoriation (COA) for CONDOR – Flight Parameters | accepted | 3 | 1504 | L | 5 | Maxine Tan |  | 100%
General AFSL Lab | 543 – Perforce Visual Client (copy) | accepted | 3 | 1501 | XS | 1 | Tarik Haj-Khalil
Flight Operations | 544 – Field Testing Transportation Boxes (Part 3) | accepted | 3 | 1608 | S | 2 | Daniel Arzouman |  |  | wine rack
General AFSL Lab | 545 – Purchase Laboratory Computing Infrastructure (Part 2) | accepted | 3 | 1502 | M | 3 | Christopher Lum |  | 100%
General AFSL Lab | 546 – Perforce Visual Client (copy) | accepted | 3 | 1501 | XS | 1 | Gage Winde
General AFSL Lab | 547 – Pixhawk Hardware-in-the-Loop Simulator | accepted | 3 | 1502 | XL | 8 | Christopher Lum |  | 100%
Visual Anchoring | 548 – CONDOR Camera Gimbal v2 Design | accepted | 3 | 1501 | XL | 8 | Brendan Doyle Wade
Visual Anchoring | 549 – CONDOR Camera Gimbal v2 Integration | accepted | 3 | 1503 | XL | 8 | Brendan Doyle Wade |  | 90%
Visual Anchoring | 550 – PixHawk Custom Flight Mode (Simple) (Helper 2) | accepted | 3 | 1507 | L | 5 | Dai Tsukada |  | 100%
Visual Anchoring | 551 – PixHawk Custom Flight Mode (Simple) (Helper 3) | accepted | 3 | 1504 | L | 5 | Gage Winde | 1 | 75%
General AFSL Lab | 552 - Sprint 1502 Administration | accepted | 3 | 1502 | M | 3 | Christopher Lum |  | 100%
Australia Bushfire Monitoring | 553 - Australia Conference Paper (Position 2) | accepted | 3 | 1503 | XL | 8 | Alexander Summers |  | 10%
Australia Bushfire Monitoring | 554 - Australia Conference Paper (Position 3) | accepted | 3 | 1503 | XL | 8 | Brian Carpenter |  | 95%
Mapping | 555 – Wildfire Reconnaisssance Camera (Preliminary Research) | accepted | 3 | 1505 | L | 5 | Cory Hage |  | 80%
Flight Operations | 556 – UAV Flight Termination and Recovery System (Preliminary Research) | accepted | 3 | 1505 | M | 3 | Melanie Clark |  | 50%
Visual Anchoring | 557 – PixHawk Custom Flight Mode (Simple) (Helper 4) | dropped | #N/A | 1504 | L | 5 | Cory Hage |  | 20%
Visual Anchoring | 558 – PixHawk Custom Flight Mode (Simple) (Helper 5) | dropped | #N/A | 1504 | L | 5 | Matthew Jones |  | 30%
Visual Anchoring | 559 – OpenCV Familiarization (Helper) | in backlog | 0 | - | L | 5 | - |  | 10% | strech?
Visual Anchoring | 560 – Matlab Computer Vision Processing Algorithm (Position 1) | accepted | 3 | 1503 | XL | 8 | Matthew Jones
Visual Anchoring | 561 – Matlab Computer Vision Processing Algorithm (Version 2.0) (Position 1) | accepted | 3 | 1504 | L | 5 | Matthew Jones |  | 65%
Visual Anchoring | 562 – CONDOR Demonstration Package | accepted | 3 | 1504 | L | 5 | Christopher Lum |  | 80%
Mapping | 563 – TEDD Demonstration Package | dropped | #N/A | 1708 | L | 5 | - |  | 50%
Flight Operations | 564 – Pixhawk Receiver/Transmitter Upgrade | accepted | 3 | 1504 | L | 5 | Christopher Lum |  | 90%
Flight Operations | 565 – AFSL Mini Quad Research Platform | accepted | 3 | 1508 | XL | 8 | Felipe Medeiros |  | 100% | need to order a chord for the camera and new board but the quad flies great
Visual Anchoring | 566 – GitHub Ardupilot Rollback to Stable Build | dropped | #N/A | 1510 | L | 5 | -
General AFSL Lab | 567 – Sprint 1503 Administration | accepted | 3 | 1503 | M | 3 | Christopher Lum
Mapping | 568 – TEDD Ground Testing | accepted | 3 | 1606 | XL | 8 | Vitor Vasconcelos |  | 50% | Tedd not fully assembeled
GROVER | 569 - UW Unmanned Ground Vehicle | accepted | 3 | 1512 | XL | 8 | Pico Premvuti |  | 99% | Justin listed as position 2 on this, may no longer be needed
GROVER | 570 – UW Unmanned Ground Vehicle Autonomy Integration | dropped | #N/A | 1708 | XL | 8 | - |  | 10%
GROVER | 571- UW Unmanned Ground Vehicle (Helper 1) | accepted | 3 | 1512 | L | 5 | Justin Chu |  | 95% | Can we solder in the lab yet??
GROVER | 572 - UW Unmanned Ground Vehicle (Helper 2) | accepted | 3 | 1601 | XL | 8 | Pico Premvuti |  | 75%
General AFSL Lab | 573 – Sprint 1504 Administration | accepted | 3 | 1504 | M | 3 | Christopher Lum
General AFSL Lab | 574 – Perforce Visual Client (copy) | accepted | 3 | 1504 | S | 2 | Justin Chu |  | 100%
General AFSL Lab | 575 – Perforce Visual Client (copy) | accepted | 3 | 1504 | S | 2 | Nick Anderson |  | 5%
General AFSL Lab | 576 – ScanEagle Simulator: Documentation (position 1) | accepted | 3 | 1505 | L | 5 | Noel Kimber
General AFSL Lab | 577 – ScanEagle Simulator: Documentation (position 2) | accepted | 3 | 1505 | L | 5 | Daniel Ablog |  | 90%
Visual Anchoring | 578 – Matlab Computer Vision Processing Algorithm (Version 2.0) (Position 2) | accepted | 3 | 1504 | L | 5 | Jeremy Brenner | 1 | 30%
Flight Operations | 579– FAA Certificate of Authorization (COA) for CONDOR (Helper 1) | dropped | #N/A | 1509 | M | 3 | - |  | 80% | 8050-1
Flight Operations | 580– FAA Certificate of Authorization (COA) for CONDOR (Helper 2) | accepted | 3 | 1602 | S | 2 | Maxine Tan |  | 75%
Flight Operations | 581 – AFSL Mini Quad Research Platform (Helper 1) | accepted | 3 | 1510 | S | 2 | Daniel Varnum-Lowry |  | 50% | need to build a static test bench
Visual Anchoring | 582 – Matlab Computer Vision Processing Algorithm (Version 2.0) (Position 3) | dropped | #N/A | 1509 | L | 5 | - |  | 5%
Australia Bushfire Monitoring | 583 - Australia Conference Paper Revisions (Position 1) | accepted | 3 | 1507 | M | 3 | Brian Carpenter
Australia Bushfire Monitoring | 584 - Australia Conference Paper Revisions (Position 2) | accepted | 3 | 1507 | M | 3 | Angel Rodriguez
Australia Bushfire Monitoring | 585 - Australia Conference Paper Revisions (Position 3) | accepted | 3 | 1507 | M | 3 | Alexander Summers
General AFSL Lab | 586 – Perforce Visual Client (copy) | accepted | 3 | 1505 | S | 2 | Benjamin Pennant |  | 100%
General AFSL Lab | 587 – Perforce Visual Client (copy) | accepted | 3 | 1505 | S | 2 | Bing Hu |  | 100%
General AFSL Lab | 588 – Perforce Visual Client (copy) | accepted | 3 | 1504 | S | 2 | Christina Hsu
Visual Anchoring | 589 – Image Processing System Integration (Position 1) | accepted | 3 | 1505 | M | 3 | Matthew Jones |  | 75%
Visual Anchoring | 590 – Image Processing System Integration (Position 2) | accepted | 3 | 1505 | M | 3 | Jeremy Brenner |  | 80%
Visual Anchoring | 591 – Image Processing System Integration (Position 3) | descoped | 6 | 1608 | M | 3 | Tadej Kosel |  | 85% | now working on Python scripting
Visual Anchoring | 592 – Image Processing System Integration (Position 4) | dropped | #N/A | 1606 | M | 3 | - |  | 95%
Visual Anchoring | 593 – Perforce Branching | dropped | #N/A | 1812 | M | 3 | -
Flight Operations | 594 – Implement Lost Link and Failsafe Protocols | accepted | 3 | 1505 | L | 5 | Al Creigh |  | 30%
Visual Anchoring | 595 – Matlab Computer Vision Processing Algorithm (Version 3.0) (Position 1) | dropped | #N/A | 1509 | L | 5 | - |  | 5%
Visual Anchoring | 596 – Matlab Computer Vision Processing Algorithm (Version 3.0) (Position 2) | dropped | #N/A | 1509 | L | 5 | -
Visual Anchoring | 597 – Matlab Computer Vision Processing Algorithm (Version 3.0) (Position 3) | dropped | #N/A | 1509 | L | 5 | -
Flight Operations | 598 – Wind Tunnel Model Documentation and Archival (Position 1) | accepted | 3 | 1505 | M | 3 | Aleksandr Tereshchenkov |  | 5%
Flight Operations | 599 – Wind Tunnel Model Documentation and Archival (Position 2) | accepted | 3 | 1505 | M | 3 | Jason Hung |  | 40%
General AFSL Lab | 600 – Sprint 1505 Administration | accepted | 3 | 1505 | M | 3 | Christopher Lum
General AFSL Lab | 601 – Investigate Hyperspectral Cameras | dropped | #N/A | 1506 | M | 3 | -
General AFSL Lab | 602 – Read Documentation on MicaSense Red Edge Camera | accepted | 3 | 1506 | L | 5 | Christopher Lum
Flight Operations | 603 – Weather Ballon Data Acquisition Platform | dropped | #N/A | 1506 | XL | 8 | -
Flight Operations | 604 – Procure HAM Radio | accepted | 3 | 1511 | M | 3 | Shida Xu |  | 100%
Visual Anchoring | 605 – Mission Planner Modifications (Simple) (Helper 1) | accepted | 3 | 1506 | M | 3 | Gage Winde |  | 90%
Flight Operations | 606 – APM 2.6 Hardware-in-the-Loop Simulator | dropped | #N/A | 1508 | M | 3 | - |  | 50%
Flight Operations | 607 – Field Box and Supplies | accepted | 3 | 1507 | M | 3 | Christopher Lum |  | 100%
Flight Operations | 608 – Mission Planner Familiarization (Position 1) | accepted | 3 | 1507 | L | 5 | Christopher Lum |  | 100%
Flight Operations | 609 – Procure Weather Station | accepted | 3 | 1601 | S | 2 | Ward Handley |  | 90% | On hold?
Australia Bushfire Monitoring | 610 – Finalize Aerotec Conference Submission and Presentation | accepted | 3 | 1508 | XL | 8 | Alexander Summers |  | 100%
Flight Operations | 611 – Fix and Clean Up RCAM Simulator | accepted | 3 | 1510 | XL | 8 | Christopher Lum |  | 75%
Flight Operations | 612 – Battery Research | accepted | 3 | 1610 | L | 5 | Chris Nee |  | 90%
Mapping | 613 – Photogrammary Familiarization (Introductory Level) | accepted | 3 | 1508 | XL | 8 | Zach Caratao | 1 | 100% | got NDVI photos in Matlab
General AFSL Lab | 614 – Sprint 1506 Administration | accepted | 3 | 1506 | M | 3 | Christopher Lum
Mapping | 615 – Geotagging Photos with Mission Planner | accepted | 3 | 1507 | XL | 8 | Felipe Medeiros | 1 | 100%
General AFSL Lab | 616 – Perforce Visual Client (copy) | accepted | 3 | 1506 | S | 2 | Felipe Medeiros
General AFSL Lab | 617 – Perforce Visual Client (copy) | accepted | 3 | 1506 | S | 2 | Zach Caratao
General AFSL Lab | 618 – Perforce Visual Client (copy) | accepted | 3 | 1506 | S | 2 | Scott Hoang
General AFSL Lab | 619 – Perforce Visual Client (copy) | accepted | 3 | 1506 | S | 2 | Casey Kilborn
General AFSL Lab | 620 – Perforce Visual Client (copy) | accepted | 3 | 1508 | S | 2 | Courtney Yeager
General AFSL Lab | 621 – Perforce Visual Client (copy) | accepted | 3 | 1506 | S | 2 | Hannah Olliges
General AFSL Lab | 622 – Perforce Visual Client (copy) | accepted | 3 | 1506 | S | 2 | Ananya Tegegn
General AFSL Lab | 623 – Perforce Visual Client (copy) | accepted | 3 | 1506 | S | 2 | Gizelle Gando
General AFSL Lab | 624 – Perforce Visual Client (copy) | accepted | 3 | 1506 | S | 2 | Andrew Jacobson
General AFSL Lab | 625 – Perforce Visual Client (copy) | accepted | 3 | 1506 | S | 2 | Yifu Wang
General AFSL Lab | 626 – Perforce Visual Client (copy) | accepted | 3 | 1510 | XS | 1 | Emil Caga-anan |  | 75%
General AFSL Lab | 627 – Perforce Visual Client (copy) | accepted | 3 | 1506 | S | 2 | Tyler Sheehan
General AFSL Lab | 628 – Perforce Visual Client (copy) | accepted | 3 | 1510 | XS | 1 | Shida Xu |  | 70%
General AFSL Lab | 629 – Perforce Visual Client (copy) | accepted | 3 | 1601 | XS | 1 | Elaiza Luker
General AFSL Lab | 630 – Perforce Visual Client (copy) | accepted | 3 | 1506 | S | 2 | Lien Chang
General AFSL Lab | 631 – Perforce Visual Client (copy) | accepted | 3 | 1506 | S | 2 | Stephanie Rogers
CERES | 632 – Perforce Visual Client (copy) | accepted | 3 | 1601 | XS | 1 | Harrison Stankey
Risk Assessment | 633 – Risk Assessment Paper Setup | accepted | 3 | 1507 | L | 5 | Dai Tsukada |  | 100%
Risk Assessment | 634 – Risk Assessment Paper Writing (Part 1) | accepted | 3 | 1509 | XL | 8 | Dai Tsukada |  | 100%
Risk Assessment | 635 – Risk Assessment Code and Simulation | accepted | 3 | 1509 | XL | 8 | Dai Tsukada |  | 100%
Flight Operations | 636 – AFSL Mini Quad Research Platform (Helper 2) | accepted | 3 | 1510 | S | 2 | Pico Premvuti |  | 85% | Start off with repairs
Visual Anchoring | 637 – CONDOR RxMUX Integration (Helper 1) | dropped | #N/A | 1508 | M | 3 | -
Flight Operations | 638 – Mission Planner Familiarization (Position 2) | accepted | 3 | 1508 | XL | 8 | Hannah Olliges |  | 50%
Flight Operations | 639 – Mission Planner Familiarization (Position 3) | accepted | 3 | 1508 | XL | 8 | Gizelle Gando |  | 15%
CERES | 640 – Mission Planner Familiarization (Position 4) | dropped | #N/A | 1602 | M | 3 | -
CERES | 641 – Mission Planner Familiarization (Position 5) | dropped | #N/A | 1602 | XL | 8 | - |  | 20%
CERES | 642 – Mission Planner Familiarization (Position 6) | dropped | #N/A | 1602 | M | 3 | - |  | 65%
Mapping | 643 – Photogrammary Familiarization (Introductory Level) (Position 2) | accepted | 3 | 1512 | XL | 8 | Charlie Shaw-Feather |  | 100% | May be complete?
Mapping | 644 – Canon CHDK Research and Development | dropped | #N/A | 1711 | XL | 8 | - |  | 75% | Waiting for new 8GB SD card. Tests failed for 2 GB and 16 GB SD Cards.
Mapping | 645 – Australia Preparations and Test Run (Position 1) | accepted | 3 | 1508 | XL | 8 | Christopher Lum |  | 100%
Mapping | 646 – Australia Preparations and Test Run (Position 2) | accepted | 3 | 1508 | XL | 8 | Hannah Olliges |  | 10%
Mapping | 647 – Australia Preparations and Test Run (Position 3) | dropped | #N/A | 1508 | XL | 8 | -
Mapping | 648 – Australia Preparations and Test Run (Position 4) | accepted | 3 | 1508 | XL | 8 | Gizelle Gando |  | 5%
Flight Operations | 649 – APM 2.6 Hardware-in-the-Loop Simulator (Position 2) | accepted | 3 | 1508 | M | 3 | Felipe Medeiros |  | 100%
Flight Operations | 650 – APM 2.6 Hardware-in-the-Loop Simulator (Position 3) | dropped | #N/A | 1508 | M | 3 | -
Flight Operations | 651 – APM 2.6 Hardware-in-the-Loop Simulator (Position 4) | accepted | 3 | 1508 | M | 3 | Hannah Olliges |  | 75%
Flight Operations | 652 – Integrate Marco Polo Tracking System | accepted | 3 | 1509 | M | 3 | Christopher Lum |  | 100%
Flight Operations | 653 – Integrate Moebius Camera System | accepted | 3 | 1508 | L | 5 | Felipe Medeiros |  | 100%
General AFSL Lab | 654 – Sprint 1507 Administration | accepted | 3 | 1507 | M | 3 | Christopher Lum
General AFSL Lab | 655 – Sprint 1508 Administration | accepted | 3 | 1508 | L | 5 | Christopher Lum
JCATI 2015 | 656 - New Computer Construction | accepted | 3 | 1508 | S | 2 | Alec Bueing |  | 100%
JCATI 2015 | 657 - New Computer Construction (Helper 1) | accepted | 3 | 1508 | S | 2 | Courtney Yeager |  | 100%
JCATI 2015 | 658 - Hood River Logistics | accepted | 3 | 1508 | M | 3 | Alec Bueing |  | 100%
JCATI 2015 | 659 - ADS-B Basic Concepts & Systems Familiarization | accepted | 3 | 1508 | S | 2 | Alec Bueing |  | 100%
JCATI 2015 | 660 - ADS-B Basic Concepts & Systems Familiarization (Copy 1) | accepted | 3 | 1508 | S | 2 | Courtney Yeager |  | 100%
JCATI 2015 | 661 – ADS-B Basic Concepts & Systems Familiarization (Copy 2) | accepted | 3 | 1508 | S | 2 | Yifu Wang |  | 30%
Mapping | 662 – FAA Certificate of Authoriation (COA) for TEDD | accepted | 3 | 1606 | XS | 1 | Harrison Stankey |  | 90% | Chris and Harrison should talk
JCATI 2015 | 663 - ADS-B Basic Concepts & Familiarization (Copy 3) | accepted | 3 | 1508 | M | 3 | Ward Handley |  | 100%
JCATI 2015 | 664 - ADS-B Basic Concepts & Familiarization (Copy 4) | accepted | 3 | 1509 | S | 2 | Andrew Jacobson |  | 100%
JCATI 2015 | 665 - ADS-B Basic Concepts & Familiarization (Copy 5) | accepted | 3 | 1508 | S | 2 | Henry Qin |  | 100%
JCATI 2015 | 666 - ADS-B Basic Concepts & Familiarization (Copy 6) | accepted | 3 | 1508 | S | 2 | Ryan Valach |  | 100%
Visual Anchoring | 667 - ArduPilot Software-in-the-Loop Simulator | accepted | 3 | 1508 | L | 5 | Gage Winde | 1 | 100% | working on simulator
JCATI 2015 | 668 – Sagetech Product Familiarization | accepted | 3 | 1510 | L | 5 | Robert Larson |  | 85% | order has been placed
General AFSL Lab | 669 – Lab Infrastructure: Internet Connectivity | accepted | 3 | 1512 | S | 2 | Adrien Simkins |  | 100%
General AFSL Lab | 670 – Lab Infrastructure: Shelving and Work Bench Area | accepted | 3 | 1601 | M | 3 | Scott An
JCATI 2015 | 671 – Generate JCATI 2015 Demostrator Scenario and Project Vision | accepted | 3 | 1509 | M | 3 | Christopher Lum |  | 100%
General AFSL Lab | 672 – Perforce Visual Client (copy) | accepted | 3 | 1508 | S | 2 | Robert Larson
JCATI 2015 | 673 – ADS-B Basic Concepts & Systems Familiarization (Copy 7) | accepted | 3 | 1508 | S | 2 | Robert Larson
JCATI 2015 | 674 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1509 | M | 3 | Ward Handley |  | 99%
JCATI 2015 | 675 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1509 | M | 3 | Robert Larson |  | 100%
JCATI 2015 | 676 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1509 | M | 3 | Alec Bueing |  | 100%
JCATI 2015 | 677 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1510 | M | 3 | Marissa Reid |  | 95%
JCATI 2015 | 678 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1509 | M | 3 | Yifu Wang |  | 90%
JCATI 2015 | 679 – Unit Testing Background Training (copy) | accepted | 3 | 1509 | M | 3 | Ward Handley |  | 99%
JCATI 2015 | 680 – Unit Testing Background Training (copy) | accepted | 3 | 1509 | M | 3 | Robert Larson |  | 100%
JCATI 2015 | 681 – Unit Testing Background Training (copy) | accepted | 3 | 1509 | M | 3 | Alec Bueing |  | 100%
JCATI 2015 | 682 – Unit Testing Background Training (copy) | accepted | 3 | 1510 | M | 3 | Marissa Reid |  | 95%
JCATI 2015 | 683 – Unit Testing Background Training (copy) | accepted | 3 | 1509 | M | 3 | Yifu Wang |  | 90%
General AFSL Lab | 684 – Lab Infrastructure: Computer Inventory and Upgrades | accepted | 3 | 1509 | M | 3 | Alec Bueing |  | 100%
JCATI 2015 | 685 – Multi-Source Position Reports and Data Fusion Literature Review | accepted | 3 | 1509 | M | 3 | Ward Handley |  | 95%
JCATI 2015 | 686 – Multi-Source Position Reports and Data Fusion Development Prototype | accepted | 3 | 1510 | XL | 8 | Ward Handley |  | 90%
JCATI 2015 | 687 – Kalman Filter Algorithm Development in C# | accepted | 3 | 1602 | XL | 8 | Robert Larson |  | 80%
JCATI 2015 | 688 – Multi-Source Position Reports and Data Fusion Unit Testing | dropped | #N/A | 1604 | XL | 8 | - |  | 15%
JCATI 2015 | 689 – Multi-Source Position Reports and Data Fusion Literature Review (Position 2) | accepted | 3 | 1509 | M | 3 | Robert Larson |  | 90%
JCATI 2015 | 690 – Multi-Source Position Reports and Data Fusion Literature Review (Position 3) | accepted | 3 | 1509 | M | 3 | Alec Bueing |  | 100%
JCATI 2015 | 691 – Multi-Source Position Reports and Data Fusion Literature Review (Position 3) | dropped | #N/A | 1509 | M | 3 | -
JCATI 2015 | 692 – TRAPIS GUI Prototype (Position 1) | accepted | 3 | 1510 | XL | 8 | Henry Qin |  | 100% | pending discussion/code review
JCATI 2015 | 693 – TRAPIS GUI Prototype (Position 2) | accepted | 3 | 1510 | XL | 8 | Ryan Valach |  | 100% | pending discussion/code review
JCATI 2015 | 694 – TRAPIS: C# Data Buffer Class | accepted | 3 | 1512 | L | 5 | Henry Qin |  | 100% | need to talk to JCATI team
JCATI 2015 | 695 – TRAPIS: Formalization of the Data Fusion Algorithm | accepted | 3 | 1511 | XL | 8 | Ward Handley |  | 100%
JCATI 2015 | 696 – TRAPIS: C# Unit Testing: ADS-B and ASTERIX Packet Parsing Utilities | accepted | 3 | 1511 | L | 5 | Yifu Wang |  | 65% | Wants help - anyone interested in a helper user story
JCATI 2015 | 697 – JACTI 2015: Administrative Support | accepted | 3 | 1511 | S | 2 | Ward Handley |  | 50%
General AFSL Lab | 698 – Lab Maintenance: Organization and Upkeep | accepted | 3 | 1607 | M | 3 | Vitor Vasconcelos |  | 75%
JCATI 2015 | 699 – Latitude and Longitude Distance Conversion Coding | accepted | 3 | 1510 | XS | 1 | Ryan Valach |  | 90%
JCATI 2015 | 700 – Kinematic Model Coding | accepted | 3 | 1510 | XL | 8 | Ward Handley |  | 95%
General AFSL Lab | 701 – Sprint 1509 Administration | accepted | 3 | 1509 | M | 3 | Christopher Lum |  | 100%
General AFSL Lab | 702 – Sprint 1510 Administration | accepted | 3 | 1510 | M | 3 | Christopher Lum |  | 50%
JCATI 2015 | 703 – TRAPIS: C# Data Buffer Class (Position 2) | accepted | 3 | 1512 | L | 5 | Ryan Valach |  | 100% | need to talk to JCATI team
General AFSL Lab | 704 – Perforce Visual Client (copy) | accepted | 3 | 1510 | XS | 1 | Marissa Reid |  | 100%
General AFSL Lab | 705 – Perforce Visual Client (copy) | accepted | 3 | 1510 | XS | 1 | Adrien Simkins |  | 95%
General AFSL Lab | 706 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1710 | M | 3 | Caelen Wang |  | 70%
General AFSL Lab | 707 – Unit Testing Background Training (copy) | accepted | 3 | 1711 | M | 3 | Caelen Wang |  | 75%
General AFSL Lab | 708 – Perforce Visual Client (copy) | accepted | 3 | 1510 | XS | 1 | Luke Macfarlan |  | 100%
General AFSL Lab | 709 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1510 | M | 3 | Shida Xu |  | 40%
General AFSL Lab | 710 – Unit Testing Background Training (copy) | accepted | 3 | 1510 | M | 3 | Shida Xu |  | 40%
General AFSL Lab | 711 – Perforce Visual Client (copy) | accepted | 3 | 1512 | XS | 1 | Jennifer Look |  | 100%
General AFSL Lab | 712 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1510 | M | 3 | Emil Caga-anan |  | 90%
General AFSL Lab | 713 – Unit Testing Background Training (copy) | accepted | 3 | 1510 | M | 3 | Emil Caga-anan |  | 90% | need a better computer
General AFSL Lab | 714 – Sprint 1510 Administration (Position 2) | accepted | 3 | 1510 | S | 2 | Ward Handley |  | 75%
General AFSL Lab | 715 – Sprint 1510 Administration (Position 3) | accepted | 3 | 1510 | S | 2 | Robert Larson |  | 75%
Visual Anchoring | 716 – CONDOR Airworthiness | accepted | 3 | 1604 | XL | 8 | Brendan Doyle Wade |  | 100%
General AFSL Lab | 717 – UWSDK Unit Testing Triage | accepted | 3 | 1510 | M | 3 | Alec Bueing |  | 75%
JCATI 2015 | 718 – TRAPIS: C# Unit Testing: ADS-B and ASTERIX Packet Parsing Utilities (Position 2) | accepted | 3 | 1512 | XS | 1 | Marissa Reid |  | 10%
JCATI 2015 | 719 – Design JCATI2015 Flight Test Experiment/Demonstration | accepted | 3 | 1608 | XL | 8 | Robert Larson |  | 75%
General AFSL Lab | 720 – AFSL Website Updates (copy) | accepted | 3 | 1712 | L | 5 | Karine Chen |  | 100%
Mapping | 721 – Rought Draft for PAM Project Conference Paper | accepted | 3 | 1601 | L | 5 | Gizelle Gando |  | 40%
Mapping | 722 – Consolidate and Organize PAM Data | accepted | 3 | 1510 | L | 5 | Christopher Lum |  | 90%
Mapping | 723 – PAM Software Tools Exploration | accepted | 3 | 1512 | M | 3 | Jennifer Look |  | 50%
Mapping | 724 – PAM Client Market Study | accepted | 3 | 1601 | M | 3 | Madison Mackenzie |  | 40%
Mapping | 725 – Matlab Familiarization for PAM | accepted | 3 | 1601 | M | 3 | Jennifer Look |  | 100%
JCATI 2015 | 726 – ANPC Integration Part 1 | accepted | 3 | 1510 | XL | 8 | Gage Winde
JCATI 2015 | 727 – ANPC Integration Part 2 | accepted | 3 | 1511 | XL | 8 | Gage Winde |  | 50%
JCATI 2015 | 728 – TRAPISPacket Position 1 | accepted | 3 | 1510 | S | 2 | Henry Qin |  | 100%
JCATI 2015 | 729 – TRAPISPacket Position 2 | accepted | 3 | 1510 | S | 2 | Ryan Valach |  | 100%
General AFSL Lab | 730 – Generate Sponsor Marketing Packet | accepted | 3 | 1512 | M | 3 | Madison Mackenzie |  | 60%
JCATI 2015 | 731 – JCATI2015 FAA Paperwork and COA | accepted | 3 | 1602 | M | 3 | Shida Xu |  | 90%
JCATI 2015 | 732 – User Story 687 position 2 | accepted | 3 | 1512 | XL | 8 | Ward Handley |  | 5%
General AFSL Lab | 733 – General Lab Support: soldering station improvements | dropped | #N/A | 1511 | S | 2 | Andrew Jacobson
JCATI 2015 | 734 – JCATI 2015: Wi-Fi Data Packet Sipping | accepted | 3 | 1512 | S | 2 | Ryan Valach |  | 80%
JCATI 2015 | 735 – JCATI 2015: Sagetech GPS Solution, Part 1 (Procurement) | accepted | 3 | 1512 | S | 2 | Robert Larson |  | 100%
JCATI 2015 | 736 – JCATI 2015: iPad and WingX app procurement | accepted | 3 | 1511 | S | 2 | Robert Larson |  | 100%
JCATI 2015 | 737 – JCATI 2015: Pair aircraft ICAO ID (ADS-B) to Mode C Squawk (LAMS) | accepted | 3 | 1602 | L | 5 | Christopher Lum |  | 95% | Chris has code implemented for this
JCATI 2015 | 738 – JCATI 2015: Sagetech GPS Solution, Part 2 (Implementation) | accepted | 3 | 1601 | XL | 8 | Emil Caga-anan |  | 100%
General AFSL Lab | 739 – Generate Sponsor Marketing Packet (Position 2) | accepted | 3 | 1512 | XS | 1 | Hannah Olliges |  | 60%
General AFSL Lab | 740 – New Computer Construction (DBF01) | accepted | 3 | 1511 | M | 3 | Alec Bueing |  | 100%
JCATI 2015 | 741 – Obtain UW Section 333 Exemption | accepted | 3 | 1602 | XS | 1 | Luke Macfarlan |  | 25%
JCATI 2015 | 742 – Obtain UW Section 333 Exemption (Position 2) | dropped | #N/A | 1609 | XL | 8 | Christopher Lum |  | 25%
JCATI 2015 | 743 – Register HAPRA with FAA | accepted | 3 | 1601 | M | 3 | Christopher Lum
JCATI 2015 | 744 – TRAPIS Map Prototype (Position 1) | accepted | 3 | 1601 | L | 5 | Henry Qin |  | 90% | need to discuss definition of done
JCATI 2015 | 745 – TRAPIS Map Prototype (Position 2) | accepted | 3 | 1601 | L | 5 | Ryan Valach |  | 80% | need to discuss definition of done
Mapping | 746 – PAM Initial Data Processing and Analysis | accepted | 3 | 1512 | L | 5 | Christopher Lum |  | 100%
Mapping | 747 – PAM Miscellanous Improvements | accepted | 3 | 1601 | L | 5 | Charlie Shaw-Feather |  | 50%
Mapping | 748 – QGIS Familiarization | accepted | 3 | 1512 | L | 5 | Charlie Shaw-Feather |  | 85%
MARV | 749 – MARV Airworthiness (Position 1) | accepted | 3 | 1601 | L | 5 | Daniel Varnum-Lowry
JCATI 2015 | 750 – Obtain UW Section 333 Exemption (Position 3) | dropped | #N/A | 1606 | XL | 8 | Alec Bueing |  | 75%
JCATI 2015 | 751 – Identify and Obtain Clearance for JCATI 2015 Flight Experiment Base of Operations | accepted | 3 | 1604 | L | 5 | Robert Larson |  | 90%
JCATI 2015 | 752 – JCATI 2015: Sagetech GPS Solution, Part 2 (Implementation) (Position 2) | accepted | 3 | 1601 | XL | 8 | Ward Handley |  | 100%
JCATI 2015 | 753 – JCATI 2015: ASTERIX Decoder Development | accepted | 3 | 1512 | M | 3 | Yifu Wang |  | 100%
Mapping | 754 – Agisoft PhotoScan Pro Familiarization | accepted | 3 | 1512 | L | 5 | Charlie Shaw-Feather |  | 100%
Mapping | 755 – PAM General Remote Sensing Research | accepted | 3 | 1601 | S | 2 | Jennifer Look |  | 100%
JCATI 2015 | 756 – Mapping Utility: Polar Coordinates to Lat/Lon | accepted | 3 | 1512 | M | 3 | Yifu Wang
JCATI 2015 | 757 – JCATI 2015: Convert CAT 048 Units to Standard Units | accepted | 3 | 1601 | XS | 1 | Gage Winde |  | 50%
JCATI 2015 | 758 – ANPC Integration Part 3 | accepted | 3 | 1512 | XL | 8 | Gage Winde |  | 100%
MARV | 759 – MARV Airworthiness (Position 2) | accepted | 3 | 1601 | L | 5 | Pico Premvuti
JCATI 2015 | 760 – JCATI 2015: Sagetech GPS Solution, Part 2 (Implementation) (Position 3) | accepted | 3 | 1601 | S | 2 | Robert Larson |  | 100%
JCATI 2015 | 761 – TRAPIS User Settings Control | accepted | 3 | 1601 | XL | 8 | Marissa Reid |  | 20%
JCATI 2015 | 762 – TRAPIS Non-Blocking UDP Listen on Different Ports | accepted | 3 | 1601 | L | 5 | Henry Qin |  | 100%
General AFSL Lab | 763 – UWSDK Unit Testing Fixes | accepted | 3 | 1604 | L | 5 | Anupam Gupta |  | 80%
JCATI 2015 | 764 – LAMS and Clarity Message Encoding/Decoding | accepted | 3 | 1605 | L | 5 | Gage Winde |  | 100% | Need to fix bug found during 04/13/16 test
JCATI 2015 | 765 – Skywalker X8 (HAPRA) Aircraft Flight Manual | accepted | 3 | 1601 | M | 3 | Alec Bueing |  | 75% | please review with PIC
JCATI 2015 | 766 – Skywalker 1900 (TEDD & CONDOR) Aircraft Flight Manual | accepted | 3 | 1608 | M | 3 | Vitor Vasconcelos |  | 95% | next flight test should have a run to do skywalker 1900 basic performance
CERES | 767 – Obtain COA for CERES Project | accepted | 3 | 1605 | XL | 8 | Alec Bueing |  | 75% | waiting on registration
JCATI 2015 | 768 – AFSL Multi-Rotor Purchase | accepted | 3 | 1604 | M | 3 | Zachary Williams |  | 85%
General AFSL Lab | 769 – AFSL Aircraft Launcher | dropped | #N/A | 1605 | XL | 8 | -
CERES | 770 – Obtain Authorization to Operate in Canada (Preliminary Research) | accepted | 3 | 1601 | S | 2 | Navdeep Sandhu
General AFSL Lab | 771 – Sprint 1511 Administration | accepted | 3 | 1511 | L | 5 | Christopher Lum
General AFSL Lab | 772 – Sprint 1512 Administration | accepted | 3 | 1512 | L | 5 | Christopher Lum
General AFSL Lab | 773 – Sprint 1601 Administration | accepted | 3 | 1601 | L | 5 | Christopher Lum
General AFSL Lab | 774 – Sprint 1602 Administration | accepted | 3 | 1602 | L | 5 | Christopher Lum
General AFSL Lab | 775 – Sprint 1603 Administration | accepted | 3 | 1603 | L | 5 | Christopher Lum
General AFSL Lab | 776 – Sprint 1604 Administration | accepted | 3 | 1604 | L | 5 | Christopher Lum
General AFSL Lab | 777 – Sprint 1605 Administration | accepted | 3 | 1605 | L | 5 | Christopher Lum
General AFSL Lab | 778 – Sprint 1606 Administration | accepted | 3 | 1606 | L | 5 | Christopher Lum
General AFSL Lab | 779 – Sprint 1607 Administration | accepted | 3 | 1607 | L | 5 | Christopher Lum
General AFSL Lab | 780 – Sprint 1608 Administration | accepted | 3 | 1608 | L | 5 | Christopher Lum
General AFSL Lab | 781 – Sprint 1609 Administration | accepted | 3 | 1609 | L | 5 | Christopher Lum
General AFSL Lab | 782 – Sprint 1610 Administration | accepted | 3 | 1610 | L | 5 | Christopher Lum
General AFSL Lab | 783 – Sprint 1611 Administration | accepted | 3 | 1611 | L | 5 | Christopher Lum
Mapping | 784 - Agisoft PhotoScan Pro Familiarization (copy) | accepted | 3 | 1707 | XS | 1 | Carter Kraus
General AFSL Lab | 784 – Sprint 1612 Administration | accepted | 3 | 1612 | L | 5 | Christopher Lum
JCATI 2015 | 785 – Clarity Message Encoder Prototype | accepted | 3 | 1512 | M | 3 | Ryan Valach
Mapping | 786 – PAM Conference Paper Draft | accepted | 3 | 1512 | S | 2 | Charlie Shaw-Feather
MARV | 787 - MARV Aircraft Flight Manual | accepted | 3 | 1602 | M | 3 | Daniel Varnum-Lowry |  | 40%
JCATI 2015 | 788 – Unit Testing for Current Sprint | accepted | 3 | 1512 | S | 2 | Marissa Reid
JCATI 2015 | 789 – Unit Testing for Current Sprint | accepted | 3 | 1601 | S | 2 | Shida Xu |  | 25%
JCATI 2015 | 790 – Unit Testing for Current Sprint | accepted | 3 | 1601 | XS | 1 | Emil Caga-anan
JCATI 2015 | 791 – Unit Testing for Current Sprint | accepted | 3 | 1601 | S | 2 | Marissa Reid |  | 50%
General AFSL Lab | 792 – Unit Testing for Current Sprint | dropped | #N/A | 1902 | S | 2 | -
CERES | 793 – CERES Fluids System Prototype | accepted | 3 | 1601 | XL | 8 | Navdeep Sandhu
CERES | 794 – CERES Timeline | accepted | 3 | 1602 | L | 5 | Harrison Stankey
CERES | 795 – CERES Market Study | accepted | 3 | 1606 | XL | 8 | Brian Carpenter |  | 40%
CERES | 796 – CERES Sprint Administration | accepted | 3 | 1601 | S | 2 | Alec Bueing
CERES | 797 – CERES Market Study (Position 2) | accepted | 3 | 1601 | M | 3 | Tyler Leis
CERES | 798 – CERES Fluids System Prototype (Helper 1) | accepted | 3 | 1601 | XL | 8 | Tyler Leis
CERES | 799 – CERES Fluids System Prototype (Helper 2) | dropped | #N/A | 1602 | S | 2 | -
CERES | 800 – CERES FAA Test Sites Investigation | accepted | 3 | 1601 | S | 2 | Mia Lee
CERES | 801 – CERES Preliminary Flight Plan | accepted | 3 | 1601 | M | 3 | Alec Bueing |  | 40%
General AFSL Lab | 802 – Perforce Visual Client (copy) | accepted | 3 | 1601 | XS | 1 | Simeng Zhu |  | 80%
General AFSL Lab | 803 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1601 | M | 3 | Simeng Zhu |  | 0%
General AFSL Lab | 804 – Unit Testing Background Training (copy) | accepted | 3 | 1601 | M | 3 | Simeng Zhu |  | 0%
CERES | 805 – CERES Poster Creation | accepted | 3 | 1601 | M | 3 | Brian Carpenter
CERES | 806 – CERES Project Management | accepted | 3 | 1601 | L | 5 | Brian Carpenter
CERES | 807 – CERES Project Management (Helper) | accepted | 3 | 1601 | L | 5 | Harrison Stankey
CERES | 808 – Perforce Visual Client (copy) | accepted | 3 | 1601 | XS | 1 | Tyler Leis
CERES | 809 – Obtain Authorization to Operate in Canada (Preliminary Research) (Helper) | accepted | 3 | 1601 | XS | 1 | Alec Bueing
CERES | 810 – CERES CFD | accepted | 3 | 1604 | XL | 8 | Navdeep Sandhu
CERES | 811 – CERES Budgeting | accepted | 3 | 1601 | M | 3 | Mia Lee
JCATI 2015 | 812 – JCATI 2015 Symposium Trip Logistics | accepted | 3 | 1603 | S | 2 | Christopher Lum
JCATI 2015 | 813– ANPC Integration Part 4 | accepted | 3 | 1601 | XL | 8 | Gage Winde |  | 25%
Mapping | 814 – Matlab Analysis of NDVI Maps | descoped | 6 | 1608 | XL | 8 | Vitor Vasconcelos |  | 50%
Mapping | 815 – Report write-up | accepted | 3 | 1605 | XL | 8 | Madison Mackenzie |  | 85%
Mapping | 816 – Matlab Analysis of DSMs | accepted | 3 | 1803 | L | 5 | Carter Kraus |  | 30%
JCATI 2015 | 817 – Clarity Message Encoder/Decoder Implementation and Testing | accepted | 3 | 1601 | XL | 8 | Ryan Valach |  | 95%
Mapping | 818 – UWAA Poster Session 2016 | accepted | 3 | 1601 | L | 5 | Elaiza Luker |  | 50%
Flight Operations | 819 – Radio Mobile Investigation | accepted | 3 | 1602 | M | 3 | Robert Larson |  | 100%
JCATI 2015 | 820 – JCATI 2015: Flight Version of TRAPIS Payload | accepted | 3 | 1603 | L | 5 | Emil Caga-anan |  | 70%
CERES | 821 – CERES Mission Planner Familiarization (Position 1) | accepted | 3 | 1602 | S | 2 | Alec Bueing |  | 50%
CERES | 822 – CERES Mission Planner Familiarization (Position 2) | accepted | 3 | 1603 | S | 2 | Brian Carpenter
CERES | 823 – CERES Mission Planner Familiarization (Position 3) | accepted | 3 | 1603 | S | 2 | Harrison Stankey
CERES | 824 – CERES Liaison to AFSL Launcher Team | accepted | 3 | 1601 | M | 3 | Mia Lee
CERES | 825 – CERES FAA Documents Proofreading | accepted | 3 | 1601 | M | 3 | Harrison Stankey
JCATI 2015 | 826 – JCATI 2015: Flight Version of TRAPIS Payload Software | accepted | 3 | 1603 | XL | 8 | Ward Handley |  | 50% | demo following US 876 resolution
Flight Operations | 827 – Antenna Tracker | accepted | 3 | 1606 | XL | 8 | Yifu Wang |  | 85%
Flight Operations | 828 – UAS Parachute Flight Termination and Recovery System | dropped | #N/A | 1902 | XL | 8 | -
Flight Operations | 829 – Camera Gimbal and Head Tracking Unit Research | accepted | 3 | 1605 | M | 3 | Zachary Williams |  | 100%
General AFSL Lab | 830 – Perforce Visual Client (copy) | accepted | 3 | 1603 | S | 2 | Zachary Williams |  | 15%
General AFSL Lab | 831 – Perforce Visual Client (copy) | accepted | 3 | 1601 | S | 2 | Daniel Zhu
General AFSL Lab | 832 – Perforce Visual Client (copy) | accepted | 3 | 1603 | S | 2 | Scott An
General AFSL Lab | 833 – Perforce Visual Client (copy) | accepted | 3 | 1605 | S | 2 | Nathan Isaman |  | 100%
General AFSL Lab | 834 – Perforce Visual Client (copy) | accepted | 3 | 1609 | S | 2 | Ryan Grimes
General AFSL Lab | 834 – Perforce Visual Client (copy) | accepted | 3 | 1611 | S | 2 | Andrew Park
General AFSL Lab | 834 – Perforce Visual Client (copy) | dropped | #N/A | 1612 | S | 2 | Jenny Garner
General AFSL Lab | 835 – Perforce Visual Client (copy) | accepted | 3 | 1606 | S | 2 | Aaron Goldfogel | 70
General AFSL Lab | 836 – Perforce Visual Client (copy) | accepted | 3 | 1602 | S | 2 | Connor Kafka |  | 15%
General AFSL Lab | 837 – Perforce Visual Client (copy) | accepted | 3 | 1601 | S | 2 | Anupam Gupta
JCATI 2015 | 838 – TRAPIS Support for Current Sprint | accepted | 3 | 1601 | XS | 1 | Henry Qin
JCATI 2015 | 839 – TRAPIS Support for Current Sprint | accepted | 3 | 1601 | XS | 1 | Ryan Valach
GROVER | 840 – UW Unmanned Ground Vehicle Autonomy Integration (copy) | dropped | #N/A | 1708 | XL | 8 | - |  | 10%
JCATI 2015 | 841 – Identify and Obtain Clearance for JCATI 2015 Flight Experiment Base of Operations (copy) | accepted | 3 | 1607 | M | 3 | Robert Larson |  | 100% | Please bug chris about WA park scientific permit
CERES | 842 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1602 | M | 3 | Harrison Stankey
CERES | 843 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1603 | S | 2 | Brian Carpenter
CERES | 844 – Unit Testing Background Training (copy) | accepted | 3 | 1602 | M | 3 | Harrison Stankey
CERES | 845 – Unit Testing Background Training (copy) | accepted | 3 | 1603 | M | 3 | Brian Carpenter
Flight Operations | 846 – RC Simulator | accepted | 3 | 1604 | L | 5 | Connor Kafka |  | 50%
JCATI 2015 | 847 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1604 | M | 3 | Scott An
JCATI 2015 | 848 – Unit Testing Background Training (copy) | accepted | 3 | 1606 | M | 3 | Scott An |  | 80%
CERES | 849 – CERES Power Analysis | accepted | 3 | 1601 | S | 2 | Harrison Stankey
CERES | 850 – CERES CDR Assistance | accepted | 3 | 1601 | XS | 1 | Harrison Stankey
CERES | 851 – CERES Budgeting (Helper) | accepted | 3 | 1601 | S | 2 | Brian Carpenter
Flight Operations | 852 – Mobile Weather Station Shakeout | accepted | 3 | 1602 | M | 3 | Yifu Wang |  | 60%
CERES | 853 – FUNRA Airframe Build | descoped | 6 | 1608 | XL | 8 | Selina Lui |  | 75%
Flight Operations | 854 – Read Approved COA and Integrate Constraints into Operations | accepted | 3 | 1606 | M | 3 | Harrison Stankey |  | 90%
JCATI 2015 | 855 – Add Stochastic Elements to TRAPISSimulator | accepted | 3 | 1607 | XL | 8 | Christopher Lum |  | 50% | need to add uncertainty to Clarity packets (AKA ADS-B)
CERES | 856 – CERES Airframe Build (copy) | accepted | 3 | 1605 | XL | 8 | Carter Beamish |  | 100%
JCATI 2015 | 857 – TRAPIS Map Architecture | accepted | 3 | 1602 | L | 5 | Henry Qin |  | 80%
JCATI 2015 | 858 – TRAPIS Map Architecture (copy) | accepted | 3 | 1602 | L | 5 | Ryan Valach |  | 90%
Visual Anchoring | 859 – Mission Planner Python Interface | accepted | 3 | 1608 | S | 2 | Tadej Kosel |  | 95%
Mapping | 860 – PAM Paper Submission | accepted | 3 | 1605 | XL | 8 | Madison Mackenzie |  | 85%
CERES | 861 – CERES Structural Analysis | accepted | 3 | 1605 | M | 3 | Mia Lee |  | 100%
CERES | 862 – CERES Ground Test Mount Preliminary Research | accepted | 3 | 1603 | S | 2 | Mia Lee
CERES | 863 – CERES Fluids System Prototype - Part 2 | accepted | 3 | 1603 | XL | 8 | Tyler Leis
CERES | 864 – CERES Fluids System Prototype - Part 2 (Helper) | accepted | 3 | 1603 | M | 3 | Navdeep Sandhu
JCATI 2015 | 865 – JCATI 2015: TRAPIS Payload Data Logger | dropped | #N/A | 1603 | S | 2 | Ward Handley |  |  | Is anyone else interested in this story?
JCATI 2015 | 866 – TRAPIS payload field testing (round 1) | accepted | 3 | 1602 | XS | 1 | Ward Handley |  |  | meadowbrook farm feb 6th, 2016
JCATI 2015 | 867 – Skywalker X-8 Stability with TRAPIS payload | dropped | #N/A | 1610 | XS | 1 | Robert Larson |  | 70%
General AFSL Lab | 868 – Software Developer Background Training (Algorithm and Back End) (copy) | accepted | 3 | 1602 | M | 3 | Daniel Zhu
General AFSL Lab | 869 – Unit Testing Background Training (copy) | accepted | 3 | 1603 | M | 3 | Daniel Zhu |  | 90%
JCATI 2015 | 870 – Cesium 1: Orientation | accepted | 3 | 1602 | S | 2 | Simeng Zhu |  | 10%
JCATI 2015 | 871 – Cesium 2: Polyline Volumes | dropped | #N/A | 1605 | M | 3 | Simeng Zhu |  | 55%
JCATI 2015 | 872 – Cesium 3: Multiple Aircraft Tracks | dropped | #N/A | 1605 | M | 3 | Simeng Zhu
JCATI 2015 | 873 – Cesium 4: Terrain Caching | dropped | #N/A | 1605 | M | 3 | Simeng Zhu
JCATI 2015 | 874 – Wake Turbulence App: Model Definition | accepted | 3 | 1602 | L | 5 | Ward Handley |  | 80%
JCATI 2015 | 875 – Wake Turbulence App: TRAPIS output to .czml | accepted | 3 | 1605 | XL | 8 | Ward Handley |  | 100%
JCATI 2015 | 876 – TRAPIS payload field testing anamoly investigation | accepted | 3 | 1603 | M | 3 | Ward Handley |  | 50% | failure analysis
JCATI 2015 | 877 – TRAPIS payload field testing (round 2) | accepted | 3 | 1603 | M | 3 | Ward Handley |  | 0%
GROVER | 878 – Upgrade/Fix GROVER | accepted | 3 | 1607 | L | 5 | Zach Caratao |  | 100%
JCATI 2015 | 879 – TRAPIS NIC and NACp Support | accepted | 3 | 1602 | M | 3 | Henry Qin |  | 75%
JCATI 2015 | 880 – TRAPIS NIC and NACp Support (copy) | accepted | 3 | 1602 | M | 3 | Ryan Valach |  | 50%
JCATI 2015 | 881 – AFSL Aircraft Launcher (copy) | dropped | #N/A | 1606 | L | 5 | -
Flight Operations | 882 – Develop Flight Crew Communication Solution | accepted | 3 | 1606 | M | 3 | Christopher Lum |  | 30%
Flight Operations | 883 – Flight Operations Work Items Part 2 | dropped | #N/A | 1607 | XL | 8 | Zachary Williams |  | 20% | Argo
JCATI 2015 | 884 – LAMS Related Items | accepted | 3 | 1602 | XL | 8 | Gage Winde |  | 50%
CERES | 885 - CERES HiL simulator construction | accepted | 3 | 1603 | M | 3 | Alec Bueing
CERES | 886 - CERES Algorithm Development & Support (Part 1, Position 1) | accepted | 3 | 1602 | L | 5 | Alec Bueing
CERES | 887 - CERES Algorithm Development & Support (Part 1, Position 2) | dropped | #N/A | 1605 | M | 3 | -
CERES | 888 - CERES Algorithm Development & Support (Part 1, Position 3) | accepted | 3 | 1603 | S | 2 | Brian Carpenter
CERES | 889 - BARNSTORMER Networking Research | accepted | 3 | 1603 | M | 3 | Alec Bueing
JCATI 2015 | 890 – Wake Turbulence App: Model Simulation | accepted | 3 | 1603 | M | 3 | Ward Handley |  | 85%
JCATI 2015 | 891 – Wake Turbulence App: Model Write Up | accepted | 3 | 1603 | L | 5 | Ward Handley |  | 0%
JCATI 2015 | 892 – Cesium 1: Orientation (copy) | accepted | 3 | 1602 | M | 3 | Ward Handley
JCATI 2015 | 893 - Fusion of Kalman Filter Vehicle Position Estimates | accepted | 3 | 1606 | XL | 8 | Robert Larson |  | 80%
JCATI 2015 | 894 - Kalman Filter Implementation in Demo Scenarios (Part 1) | accepted | 3 | 1604 | M | 3 | Robert Larson |  | 75%
Mapping | 895 – Explore Esri Products | accepted | 3 | 1701 | M | 3 | Eze Klarnet
JCATI 2015 | 896 – Obtain Landowner Permission for JCATI2016 Flight Test | accepted | 3 | 1604 | M | 3 | Daniel Zhu |  | 50%
Flight Operations | 897 - Incorporate Lessons Learned from RC Fun Day #2 | dropped | #N/A | 1606 | L | 5 | -
CERES | 898 - Industry Project Presentation (Position 1) | accepted | 3 | 1603 | S | 2 | Brian Carpenter |  | 100%
CERES | 899 - Industry Project Presentation (Position 2) | accepted | 3 | 1603 | S | 2 | Alec Bueing |  | 100%
CERES | 900 - Industry Project Presentation (Position 3) | accepted | 3 | 1603 | S | 2 | Harrison Stankey |  | 100%
CERES | 901 - Industry Project Presentation (Position 4) | accepted | 3 | 1603 | S | 2 | Mia Lee |  | 100%
CERES | 902 - Industry Project Presentation (Position 5) | accepted | 3 | 1603 | S | 2 | Tyler Leis |  | 100%
CERES | 903 - Industry Project Presentation (Position 6) | accepted | 3 | 1603 | S | 2 | Navdeep Sandhu |  | 100%
CERES | 904 - College of Engineering CERES Award Submission (Position 1) | accepted | 3 | 1603 | S | 2 | Brian Carpenter |  | 100%
CERES | 905 - College of Engineering CERES Award Submission (Position 2) | accepted | 3 | 1603 | S | 2 | Mia Lee |  | 100%
CERES | 906 - CERES Structual Research | accepted | 3 | 1604 | M | 3 | Mia Lee |  | 100%
CERES | 907 - CERES Ground Test and Launcher | accepted | 3 | 1604 | XL | 8 | Mia Lee |  | 100%
CERES | 908 - CFD Hand Calculations | accepted | 3 | 1604 | M | 3 | Navdeep Sandhu |  | 100%
CERES | 909 - CERES Fluid System Testing: Part 1 | accepted | 3 | 1603 | XL | 8 | Tyler Leis |  | 100%
CERES | 910 - CERES Fluid System Image Processing | accepted | 3 | 1605 | L | 5 | Navdeep Sandhu |  | 95%
CERES | 911 - CERES Ground Testing Site Acquisition and Planning | accepted | 3 | 1604 | S | 2 | Brian Carpenter |  | 100%
CERES | 912 - CERES Preliminary Design Review Presentation (Position 1) | accepted | 3 | 1603 | M | 3 | Brian Carpenter |  | 100%
CERES | 913 - CERES Preliminary Design Review Presentation (Position 2) | accepted | 3 | 1603 | M | 3 | Harrison Stankey |  | 100%
CERES | 914 - CERES Dempsey Flight Test Logistics Planning | accepted | 3 | 1604 | L | 5 | Brian Carpenter
CERES | 915 - CERES Dempsey Flight Test Planning | accepted | 3 | 1604 | M | 3 | Alec Bueing |  | 50%
CERES | 916 - CERES Sunnyside Flight Test Logistical Planning (Position 1) | accepted | 3 | 1605 | L | 5 | Brian Carpenter |  | 80%
CERES | 917 - CERES Sunnyside Flight Test Logistical Planning (Position 2) | accepted | 3 | 1605 | L | 5 | Harrison Stankey |  | 90%
CERES | 918 - CERES Sunnyside Flight Test Planning | accepted | 3 | 1605 | M | 3 | Alec Bueing |  | 95%
JCATI 2015 | 919 - Kalman Filter Refinement and Testing | accepted | 3 | 1603 | M | 3 | Robert Larson
JCATI 2015 | 920 – Master’s Thesis Rough Draft (Handley) | accepted | 3 | 1604 | XL | 8 | Ward Handley |  | 25% | chris needs to look at this
JCATI 2015 | 921 – Master’s Thesis Revisions (Handley) | accepted | 3 | 1605 | XL | 8 | Ward Handley |  | 100%
JCATI 2015 | 922 – Master’s Thesis Presentation (Handley) | accepted | 3 | 1605 | XL | 8 | Ward Handley |  | 65%
JCATI 2015 | 923 – TRAPIS Truck Test + RC Fun Day 3 | accepted | 3 | 1604 | M | 3 | Ward Handley |  | 25%
JCATI 2015 | 924 – TRAPIS Truck Test + RC Fun Day 3 (Copy 1) | accepted | 3 | 1604 | M | 3 | Robert Larson |  | 30%
JCATI 2015 | 925 – TRAPIS Truck Test | accepted | 3 | 1604 | M | 3 | Gage Winde
JCATI 2015 | 926 – TRAPIS Truck Test (Copy 1) | accepted | 3 | 1605 | M | 3 | Christopher Lum |  | 100%
JCATI 2015 | 927 – TRAPIS Truck Test Logistics | accepted | 3 | 1604 | XS | 1 | Gage Winde
JCATI 2015 | 928 – TRAPIS Development Miscellaneous | accepted | 3 | 1604 | M | 3 | Gage Winde
JCATI 2015 | 929 – TRAPIS Development Miscellaneous (Copy) | accepted | 3 | 1604 | L | 5 | Gage Winde |  | 100% | Completed in sprint 1603
JCATI 2015 | 930 – TRAPIS Development Miscellaneous (Copy) | accepted | 3 | 1604 | M | 3 | Gage Winde |  | 100% | Completed in sprint 1602
JCATI 2015 | 931 – TRAPIS Flight Demo Scenario | accepted | 3 | 1604 | M | 3 | Gage Winde |  | 100% | Completed in sprint 1602
JCATI 2015 | 932 – NACp Degrader | accepted | 3 | 1604 | L | 5 | Gage Winde |  | 100% | Completed in sprint 1603
JCATI 2015 | 933 - TRAPIS X8 Integration | accepted | 3 | 1604 | M | 3 | Emil Caga-anan |  | 75%
JCATI 2015 | 934 – JCATI Symposium Presentation | accepted | 3 | 1604 | M | 3 | Ward Handley |  | 25%
Visual Anchoring | 935 – CONDOR Gimbal Documentation | accepted | 3 | 1604 | XL | 8 | Brendan Doyle Wade |  | 100%
CERES | 936 – Industry Project Presentation | accepted | 3 | 1605 | S | 2 | Brian Carpenter |  | 75%
CERES | 937 – BARNSTORMER Algorithm Development & Support | accepted | 3 | 1604 | L | 5 | Alec Bueing
CERES | 938 – BARNSTORMER Algorithm Development & Support | accepted | 3 | 1604 | S | 2 | Brian Carpenter
CERES | 939 - CERES Launcher Modifications | accepted | 3 | 1604 | L | 5 | Mia Lee
CERES | 940 - CFD Detailed Calculations | accepted | 3 | 1606 | L | 5 | Navdeep Sandhu |  | 85%
CERES | 941 – CERES Fluid System Testing - Part 2 | accepted | 3 | 1604 | L | 5 | Tyler Leis
CERES | 942 – CERES Fluid System Image Processing 2 | accepted | 3 | 1605 | XS | 1 | Navdeep Sandhu |  | 50%
CERES | 943 - CERES Technical Report Writer - Main | accepted | 3 | 1606 | XL | 8 | Harrison Stankey |  | 15%
CERES | 944 - CERES Technical Report Writer - Assistant | accepted | 3 | 1606 | XL | 8 | Brian Carpenter |  | 15%
CERES | 945 - CERES Technical Report Writer - Helper | accepted | 3 | 1606 | XL | 8 | Navdeep Sandhu |  | 15%
CERES | 946 - CERES Technical Report Writer - Helper | accepted | 3 | 1606 | XL | 8 | Tyler Leis |  | 15%
CERES | 947 - CERES Technical Report Writer - Helper | accepted | 3 | 1606 | XL | 8 | Mia Lee |  | 15%
CERES | 948 - CERES Technical Report Writer - Helper | accepted | 3 | 1606 | XL | 8 | Alec Bueing |  | 80%
CERES | 949 - CERES Aircraft Integration | accepted | 3 | 1604 | L | 5 | Harrison Stankey
CERES | 950 – CERES Pixhawk PWM converter | accepted | 3 | 1604 | M | 3 | Alec Bueing |  | 99%
Flight Operations | 951 – Head-Tracking Unit Research | accepted | 3 | 1607 | M | 3 | Zachary Williams
Flight Operations | 952 – Head-Tracking Unit Installation | descoped | 6 | 1608 | M | 3 | Yifu Wang
Flight Operations | 953 – Mapping Gimbal Installation | dropped | #N/A | 1701 | M | 3 | -
Flight Operations | 954 – Internet Connectivity in the Field | accepted | 3 | 1607 | M | 3 | Anupam Gupta |  | 85%
CERES | 955- CERES Critical Design Review Presentater - Position 1 | accepted | 3 | 1604 | L | 5 | Brian Carpenter
CERES | 956- CERES Critical Design Review Presentater - Position 2 | accepted | 3 | 1604 | L | 5 | Harrison Stankey
CERES | 957 - CERES CDR Fluids Preperation - Position 1 | accepted | 3 | 1604 | M | 3 | Navdeep Sandhu
CERES | 958 - CERES CDR Fluids Preperation - Position 2 | accepted | 3 | 1604 | M | 3 | Tyler Leis
CERES | 959 - CERES GNC CDR Preperation | accepted | 3 | 1604 | M | 3 | Alec Bueing
CERES | 960 - CERES Structural CDR Preparation | accepted | 3 | 1604 | M | 3 | Mia Lee
CERES | 961 - Dempsey Flight Test Structures Preparation - Main | accepted | 3 | 1604 | L | 5 | Mia Lee
CERES | 962 - Dempsey Flight test Structures Preparation - Helper | accepted | 3 | 1604 | M | 3 | Brian Carpenter
CERES | 963 - Dempsey Flight Test GNC Preparation | accepted | 3 | 1604 | M | 3 | Alec Bueing
CERES | 964 - Dempsey Flight Test Fluids Preparation - Position 1 | accepted | 3 | 1604 | S | 2 | Navdeep Sandhu
CERES | 965 - Dempsey Flight Test Fluids Preparation - Position 2 | accepted | 3 | 1604 | S | 2 | Tyler Leis
CERES | 966 - Dempsey Flight Test Integration Preparation | accepted | 3 | 1604 | M | 3 | Harrison Stankey
CERES | 967 - Dempsey Flight Test | accepted | 3 | 1604 | M | 3 | Brian Carpenter
CERES | 968 - Dempsey Flight Test | accepted | 3 | 1604 | M | 3 | Harrison Stankey
CERES | 969 - Dempsey Flight Test | accepted | 3 | 1604 | M | 3 | Alec Bueing
CERES | 970 - Dempsey Flight Test | accepted | 3 | 1604 | M | 3 | Navdeep Sandhu
CERES | 971 - Dempsey Flight Test | accepted | 3 | 1604 | M | 3 | Tyler Leis
CERES | 972 - Dempsey Flight Test | accepted | 3 | 1604 | M | 3 | Mia Lee
Flight Operations | 973 - AFSL Large Scale Multi-Rotor Purchase | accepted | 3 | 1605 | XL | 8 | Zachary Williams |  | 50%
Flight Operations | 974 - AFSL Large Scale Multi-Rotor Purchase (copy) | accepted | 3 | 1605 | S | 2 | Connor Kafka |  | 50%
JCATI 2015 | 975 - Kalman Filter Implementation in Demo Scenarios (Part 2) | accepted | 3 | 1606 | L | 5 | Robert Larson |  | 80%
Flight Operations | 976 – Enclosed Trailer Purchase | accepted | 3 | 1605 | XL | 8 | Christopher Lum
JCATI 2015 | 977 – TRAPIS ADS-B Retractable Antenna Design | accepted | 3 | 1605 | L | 5 | Emil Caga-anan
JCATI 2015 | 978 – TRAPIS ADS-B Retractable Antenna Design (Helper) | accepted | 3 | 1605 | XS | 1 | Scott An
JCATI 2015 | 979 – TRAPIS ADS-B Retractable Antenna Implementation | dropped | #N/A | 1608 | L | 5 | -
JCATI 2015 | 980 – TRAPIS ADS-B Retractable Antenna Implementation (Helper) | dropped | #N/A | 1608 | M | 3 | Scott An |  | 25%
JCATI 2015 | 981 – Wake Estimator: C# Mapping Tools | accepted | 3 | 1605 | XL | 8 | Ward Handley |  | 100%
JCATI 2015 | 982 – Wake Estimator: C# Vortex Evolution Model | accepted | 3 | 1605 | XL | 8 | Ward Handley |  | 100%
JCATI 2015 | 983 – Wake Estimator: C# UI and Database Visualization | accepted | 3 | 1605 | XL | 8 | Ward Handley |  | 100%
JCATI 2015 | 984 – Master’s Thesis Polishing (Handley) | accepted | 3 | 1606 | XL | 8 | Ward Handley
Visual Anchoring | 985 – Custom Mission Planner Build | accepted | 3 | 1607 | L | 5 | Simeng Zhu
Visual Anchoring | 986 – Custom ArduPlane Build | accepted | 3 | 1607 | L | 5 | Tadej Kosel |  | 90% | problem is 3.5.3 and 3.6.0 has a bug with the camera stabilization
General AFSL Lab | 987 – Outfit the Mobile Flight Operations Center (MFOC) (Position 1) | accepted | 3 | 1607 | M | 3 | Carter Beamish |  | 15%
General AFSL Lab | 988 – Outfit the Mobile Flight Operations Center (MFOC) (Position 2) | accepted | 3 | 1607 | XL | 8 | Daniel Arzouman
General AFSL Lab | 989 – Outfit the Mobile Flight Operations Center (MFOC) (Position 3) | accepted | 3 | 1607 | XL | 8 | Christopher Lum
JCATI 2015 | 990 – Fusion of Kalman Filter Vehicle Position Estimates (Helper) | accepted | 3 | 1606 | L | 5 | Gage Winde |  | 75%
Mapping | 991 – TEDD Documentation Infrastructure | accepted | 3 | 1606 | S | 2 | Vitor Vasconcelos
Mapping | 992 – TEDD Flight Testing and Workflow Validation | descoped | 6 | 1608 | XL | 8 | Vitor Vasconcelos |  | 50%
CERES | 993 - BARNSTORMER Walk around test | accepted | 3 | 1605 | M | 3 | Alec Bueing
CERES | 994 - Meadowbrook Flight Test Structures Preparation and Modification | accepted | 3 | 1605 | L | 5 | Mia Lee
CERES | 995 - Meadowbrook Flight Test GNC Preparation | accepted | 3 | 1605 | L | 5 | Alec Bueing
CERES | 996 - Meadowbrook Flight Test Airframe Preparation | accepted | 3 | 1605 | L | 5 | Tyler Leis
CERES | 997 - Meadowbrook Flight Test Logistic Preparation | accepted | 3 | 1605 | L | 5 | Brian Carpenter
CERES | 998 - Meadowbrook Flight Test Logistic Preparation - Helper | accepted | 3 | 1605 | L | 5 | Harrison Stankey
CERES | 999 - Meadowbrook Flight Test | accepted | 3 | 1605 | M | 3 | Brian Carpenter
TRAPIS2 | Document TRAPIS MAVLink Packager | accepted | 3 | 1804 | S | 2 | Jacob Longhurst
LARI | 2887 — Make Systems View and Components View Scrollable | accepted | 3 | 1904 | M | 3 | Tina Li |  | 100% | Verified by Ravi
LARI | 2888 — Make the Main Window Dynamically Resizable | accepted | 3 | 1904 | M | 3 | Hannah Bi |  | 100% | Waiting on US_2889 (done)
LARI | 2889 — Add Adjustable Divider Between Systems and Components View | accepted | 3 | 1904 | M | 3 | Kevin Zhu |  | 100% | Verified by Ravi
LARI | 2890 — Component Tracker Tech Demo | dropped | #N/A | 1905 | M | 3 | Ravi Patel
LARI | 2891 — Use Timestamped Data to Better Represent Data Fields | dropped | #N/A | 1904 | S | 2 | - |  |  | Not sure if this is necessary, do not pickup
General AFSL Lab | 2892 – JHA LiPo Battery Handling | accepted | 3 | 1902 | M | 3 | Nicholas Price
General AFSL Lab | 2893 – JHA Soldering Station | accepted | 3 | 1902 | M | 3 | Nicholas Price
General AFSL Lab | 2894 – JHA UAV Assembly | dropped | #N/A | 1908 | S | 2 | Nicholas Price
General AFSL Lab | 2895 – JHA Flight Testing | dropped | #N/A | 1908 | S | 2 | Nicholas Price
General AFSL Lab | 2896 – Chemical Waste Collection Request | dropped | #N/A | 1904 | XS | 1 | Nicholas Price
General AFSL Lab | 2897 – Anakin Repairs (Copy) | accepted | 3 | 1902 | M | 3 | Michael Friend
Visual Anchoring | 2898 – Visual Anchoring move onto Peach | accepted | 3 | 1901 | M | 3 | Rostyk Svitelskyi
Visual Anchoring | 2899 – Visual Anchoring modify old gimbal | accepted | 3 | 1901 | S | 2 | Rostyk Svitelskyi
Visual Anchoring | 2900 – Visual Anchoring tune new gimbal | dropped | #N/A | 1902 | S | 2 | Rostyk Svitelskyi
Risk Assessment | 2901 - Generate Virtual Flight Test Matrix | dropped | #N/A | 1904 | S | 2 | Liam Mortell
Risk Assessment | 2902 - Generate Virtual Flight Test Matrix | dropped | #N/A | 1904 | S | 2 | Cherie Wu
Risk Assessment | 2903 - Matlab Simulation Environment Literature Review | accepted | 3 | 1901 | S | 2 | Zech Latimer
Risk Assessment | 2904 - Setup Matlab Simulation Environment | accepted | 3 | 1902 | M | 3 | Akshay Raikar
Risk Assessment | 2905 - Setup Matlab Simulation Environment | dropped | #N/A | 1904 | M | 3 | Jaspreet Sidhu
Risk Assessment | 2905 - Investigate Existing Simulator Environments | dropped | #N/A | 1904 | S | 2 | Ethan Uehara
Risk Assessment | 2906 - Generate Nominal Scenario | dropped | #N/A | 1904 | S | 2 | Cherie Wu
Risk Assessment | 2907 - Generate Nominal Scenario | accepted | 3 | 1902 | S | 2 | Liam Mortell
Risk Assessment | 2908 - Airbus White Paper for TOFU | accepted | 3 | 1901 | S | 2 | Christopher Lum
Risk Assessment | 2909 - Airbus White Paper for TOFU | accepted | 3 | 1901 | S | 2 | Akshay Raikar
Risk Assessment | 2910 - ME Final Report Document Skeleton | accepted | 3 | 1906 | S | 2 | Akshay Raikar
Risk Assessment | 2911 - ME Final Report Document Skeleton | dropped | #N/A | 1904 | S | 2 | Cherie Wu
Risk Assessment | 2912 - Investigating Quadrotor Dynamic Models | accepted | 3 | 1901 | S | 2 | Akshay Raikar
CellNav | 2913 – Looking into Zak Kassas’ publications-Exploiting LTE signals | in backlog | 0 | 1909 | S | 2 | -
General AFSL Lab | 2914 – Perforce Visual Client (copy) | accepted | 3 | 1902 | S | 2 | An Nguyen
General AFSL Lab | 2915 – Perforce Visual Client (copy) | accepted | 3 | 1902 | S | 2 | Lyddie Austin
General AFSL Lab | 2916 – Perforce Visual Client (copy) | accepted | 3 | 1902 | S | 2 | Chris Hayner
General AFSL Lab | 2917 - Flight Ops Administration (1901) | accepted | 3 | 1901 | XL | 8 | Helen Kuni
AMFAV | 2918 - Cleaning Up 8/20/18 Mapping Data | accepted | 3 | 1901 | S | 2 | Jaspreet Sidhu
AMFAV | 2919 - Preparing Mapping Presentation | accepted | 3 | 1902 | M | 3 | Jaspreet Sidhu
LARI | 2920 - Investigate whitespace issue with XML | dropped | #N/A | 1903 | M | 3 | -
LARI | 2921 - Make inventory permanent (non-deletable) | dropped | #N/A | 1906 | S | 2 | -
LARI | 2922 - Make methods multithreaded | in backlog | 0 | 1908 | L | 5 | -
LARI | 2923 - Implement Systems EDIT button | accepted | 3 | 1904 | M | 3 | Shawn Stanley |  | 100% | Verified by Ravi
LARI | 2924 - Convert database from XML to SQL | accepted | 3 | 1904 | XL | 8 | Ravi Patel
AMFAV | 2925 - Preparing Mapping Presentation (copy) | accepted | 3 | 1902 | S | 2 | Helen Kuni
General AFSL Lab | 2926 – Perforce Visual Client (copy) | accepted | 3 | 1902 | S | 2 | Hannah Bi
General AFSL Lab | 2927 – Perforce Visual Client (copy) | accepted | 3 | 1902 | S | 2 | Tina Li
General AFSL Lab | 2928 – Perforce Visual Client (copy) | dropped | #N/A | 1904 | S | 2 | -
General AFSL Lab | 2929 – Perforce Visual Client (copy) | accepted | 3 | 1904 | S | 2 | Nathan Han
General AFSL Lab | 2930 – Anakin Repairs (Copy) | accepted | 3 | 1902 | M | 3 | Zech Latimer
General AFSL Lab | 2931 – Anakin Repairs (Copy) | accepted | 3 | 1902 | M | 3 | Liam Mortell
Flight Operations | 2931 - Hardware Inventory | accepted | 3 | 1904 | L | 5 | Jaspreet Sidhu
CellNav | 2933 - MangOH Initial Setup | accepted | 3 | 1901 | L | 5 | Connor Kafka
LARAMID | 2934 — Frodo Stall Test Data Analysis | accepted | 3 | 1901 | M | 3 | Chung Choi
Risk Assessment | 2935 - Implement Simple Propulsion Model | dropped | #N/A | 1902 | M | 3 | Akshay Raikar
Risk Assessment | 2936 - Investigate extracting DJI flight logs | in backlog | 0 | 1908 | S | 2 | -
Risk Assessment | 2937 - Automate virtual flight test procedure | accepted | 3 | 1904 | L | 5 | Christopher Lum
LARAMID | 2935 — Manual Flight Simulation with Ultrasonic Sensor | accepted | 3 | 1902 | S | 2 | Cathy Lee
Flight Operations | 2936 - Assess HiL airworthiness | accepted | 3 | 1902 | S | 2 | Josh Lee
Flight Operations | 2937 - Replace TEDD's motor | accepted | 3 | 1902 | XS | 1 | Josh Lee
Flight Operations | 2938 - BVLOS Waiver Investigation | dropped | #N/A | 1902 | M | 3 | -
General AFSL Lab | 2939 - Update Lab Room Map | accepted | 3 | 1902 | XS | 1 | Sean Carda
Flight Operations | 2940 -- Flight Test Attendance 02/02/19 | accepted | 3 | 1902 | S | 2 | Helen Kuni
Flight Operations | 2941 -- Flight Test Attendance 02/02/19 | accepted | 3 | 1902 | S | 2 | Rostyk Svitelskyi
Flight Operations | 2942 -- Flight Test Attendance 02/02/19 | accepted | 3 | 1902 | S | 2 | Liam Mortell
Flight Operations | 2943 - Data Tech 02/02/19 | accepted | 3 | 1903 | XS | 1 | Helen Kuni
General AFSL Lab | 2944 - Setup new battery charger | accepted | 3 | 1902 | XS | 1 | Sita Manne
Flight Operations | 2945 - Assess HiL airworthiness (copy) | accepted | 3 | 1902 | S | 2 | An Nguyen
Flight Operations | 2946 - Replace TEDD's motor (copy) | accepted | 3 | 1902 | XS | 1 | An Nguyen
Visual Anchoring | 2947 – Visual Anchoring thesis (copy) | accepted | 1 | 1905 | XL | 8 | Rostyk Svitelskyi
Visual Anchoring | 2948 – Visual Anchoring Peach model processing code | accepted | 1 | 1903 | L | 5 | Rostyk Svitelskyi
Flight Operations | 2949 - Fix Flight Logs | accepted | 1 | 1902 | XS | 1 | Chris Hayner
General AFSL Lab | 2950 - Flight Ops Administration (1902) | accepted | 3 | 1902 | XL | 8 | Helen Kuni
General AFSL Lab | 2951 – Perforce Visual Client (copy) | accepted | 3 | 1902 | S | 2 | Natanael Putra
LARAMID | 2952 – LARAMID Docking Frame Design (part5) (copy) | accepted | 3 | 1903 | M | 3 | Yubin Kim
Risk Assessment | 2953 - TOFU Simulator Manual Initial Development | dropped | #N/A | 1906 | S | 2 | Zech Latimer
Risk Assessment | 2954 - TOFU Simulator Basic Failure Mechanism | accepted | 3 | 1902 | S | 2 | Zech Latimer
Risk Assessment | 2955 - TOFU Simulator Monte Carlo Implementation | dropped | #N/A | 1906 | S | 2 | Zech Latimer
Risk Assessment | 2956 - TOFU Simulator Manual Initial Development (Copy) | dropped | #N/A | 1906 | S | 2 | Akshay Raikar
Risk Assessment | 2957 - TOFU Simulator Basic Failure Mechanism (Copy) | accepted | 3 | 1902 | S | 2 | Akshay Raikar
Risk Assessment | 2958 - TOFU Simulator Monte Carlo Implementation (Copy) | dropped | #N/A | 1906 | S | 2 | Akshay Raikar
CellNav | 2959- Research on filtering LTE signals | in backlog | 0 | 1909 | S | 2 | -
LARI | 2960 - C# GUI Tutorial | accepted | 3 | 1902 | M | 3 | Shawn Stanley |  | 100% | Verified by Ravi Patel
LARI | 2961 - C# GUI Tutorial | accepted | 3 | 1903 | S | 2 | Kevin Zhu |  | 100% | Verified by Ravi
LARI | 2962 - C# GUI Tutorial | accepted | 3 | 1903 | M | 3 | Hannah Bi |  | 100% | Verified by Ravi
CellNav | 2963 - Define Mechanical Work | accepted | 3 | 1902 | XS | 1 | Sita Manne
CellNav | 2964 - Detailed design of board enclosure | accepted | 3 | 1902 | M | 3 | Sita Manne
CellNav
CellNav | 2965 - MangOH Red Hardware Review | accepted | 3 | 1902 | S | 2 | Connor Kafka
CellNav | 2966 - New Antenna Research | accepted | 3 | 1902 | M | 3 | Connor Kafka
CellNav | 2967 - GPS Degrader Trade Study | accepted | 3 | 1902 | S | 2 | Connor Kafka
General AFSL Lab | 2968 - Repair of DJI Inspire 1 | blocked | 5 | 1904 | S | 2 | Michael Friend
LARI | 2969 - LARI Development Environment Setup | accepted | 3 | 1902 | S | 2 | Shawn Stanley |  | 100% | Verified by Ravi Patel
LARI | 2970 - LARI Development Environment Setup (copy) | accepted | 3 | 1902 | S | 2 | Hannah Bi |  | 100% | Verified by Ravi Patel
LARI | 2971 - LARI Development Environment Setup (copy) | accepted | 3 | 1902 | S | 2 | Tina Li |  | 100% | Verified by Ravi Patel
LARI | 2972 - LARI Development Environment Setup (copy) | accepted | 3 | 1902 | S | 2 | Kevin Zhu |  | 100% | Verified by Ravi Patel
LARI | 2973 - LARI Setup Documentation and Review | accepted | 3 | 1902 | M | 3 | Ravi Patel |  | 100% | Creates some documentation for new devs
LARAMID | 2974 – LARAMID Electromagnet Receiver Design Optimization | accepted | 3 | 1902 | L | 5 | Natanael Putra
LARAMID | 2975 – LARAMID Electromagnet Receiver Design Optimization (copy) | accepted | 3 | 1902 | M | 3 | Yubin Kim
LARAMID | 2976 – LARAMID Detachment Process Implementation using Raspberry Pi | accepted | 3 | 1904 | L | 5 | Chung Choi
LARAMID | 2977 – LARAMID Detachment Process Implementation using Raspberry Pi (copy) | dropped | #N/A | 1904 | L | 5
General AFSL Lab | 2978 – September 2018 Safety Checklist | accepted | 3 | 1903 | XS | 1 | Nicholas Price
General AFSL Lab | 2979 -- JCATI 2019 Proposal | accepted | 3 | 1902 | S | 2 | Helen Kuni
General AFSL Lab | 2980 -- Install new USB ports on AFSL Condor | accepted | 3 | 1902 | XS | 1 | Zech Latimer
LARAMID | 2981 - Drone and Quadcopter Inspection | accepted | 3 | 1902 | XS | 1 | Cameron Tavakoli
CellNav | 2982 - Antenna Mounting Research | accepted | 3 | 1903 | XS | 1 | Sita Manne
Flight Operations | 2983 -- Flight Test Attendance 03/02/19 | accepted | 3 | 1903 | S | 2 | Helen Kuni
Flight Operations | 2984 -- Flight Test Attendance 03/02/19 | accepted | 3 | 1903 | S | 2 | Rostyk Svitelskyi
Flight Operations | 2985 -- Flight Test Attendance 03/02/19 | accepted | 3 | 1903 | S | 2 | Chris Hayner
Flight Operations | 2986 -- Flight Test Attendance 03/02/19 | accepted | 3 | 1903 | S | 2 | Liam Mortell
Flight Operations | 2987 -- Flight Test Attendance 03/02/19 | accepted | 3 | 1903 | S | 2 | Jaspreet Sidhu
Flight Operations | 2988 -- Flight Test Attendance 03/02/19 | accepted | 3 | 1903 | S | 2 | Wasif Siddique
Flight Operations | 2989 -- Flight Test Attendance 03/02/19 | accepted | 3 | 1903 | S | 2 | Zech Latimer
Flight Operations | 2990 - Data Tech 03/02/19 | accepted | 3 | 1903 | XS | 1 | Helen Kuni
LARAMID | 2991 – LARAMID Frodo Thrust Test and Analysis | accepted | 3 | 1904 | S | 2 | Chung Choi
LARAMID | 2992 – LARAMID Frodo Thrust Test and Analysis (copy) | accepted | 3 | 1904 | XS | 1 | Natanael Putra
LARAMID | 2993 – LARAMID Coupled Aircraft Moment Calculation | accepted | 3 | 1904 | S | 2 | Chung Choi
LARAMID | 2994 – LARAMID Samwise altitude hold mode and Take-Off Capacity | accepted | 3 | 1903 | S | 2 | John Choi
LARAMID | 2995 – LARAMID Separation Process Design | accepted | 3 | 1904 | M | 3 | Chung Choi
Visual Anchoring | 2996 — Visual Anchoring Plane state-space model | accepted | 3 | 1903 | M | 3 | Rostyk Svitelskyi
Visual Anchoring | 2997 — Visual Anchoring Rectification algorithm update | accepted | 3 | 1903 | S | 2 | Rostyk Svitelskyi
Visual Anchoring | 2998 — Visual Anchoring radius and bearing transmission study | accepted | 3 | 1903 | S | 2 | Rostyk Svitelskyi
Visual Anchoring | 2999 — Visual Anchoring UW mode 3 study | accepted | 3 | 1903 | XL | 8 | Rostyk Svitelskyi
Visual Anchoring | 3000 — Visual Anchoring Pixhawk ADC enable. | accepted | 3 | 1903 | M | 3 | Rostyk Svitelskyi
Visual Anchoring | 3001 — Visual Anchoring UW mode 5 implementation | accepted | 3 | 1904 | S | 2 | Rostyk Svitelskyi
Chelan Land Trust | 3002 - Investigate surveying drone options | accepted | 3 | 1904 | XS | 1 | Lyddie Austin
Visual Anchoring | 3003 — Visual Anchoring Peach repairs | accepted | 3 | 1903 | S | 2 | Rostyk Svitelskyi
Risk Assessment | Disassemble and measure Inspire components | accepted | 3 | 1904 | M | 3 | Liam Mortell
Risk Assessment | Disassemble and measure Inspire components | accepted | 3 | 1904 | M | 3 | Chris Hayner
Risk Assessment | Integrate a thrust model into TOFU simple simulator | accepted | 3 | 1904 | L | 5 | Akshay Raikar
Risk Assessment | Generate simple controller for TOFU simple simulator | accepted | 3 | 1904 | XL | 8 | Akshay Raikar
Risk Assessment | Generate simple controller for TOFU simple simulator | accepted | 3 | 1904 | XL | 8 | Christopher Lum
Risk Assessment | Investigate pulling blocks from Mathworks Sim over to TOFU simple simulator (visualization) | accepted | 3 | 1904 | S | 2 | Zech Latimer
Visual Anchoring | 3004 — Visual Anchoring move onto Peach | accepted | 3 | 1903 | XS | 1 | Rostyk Svitelskyi
Flight Operations | 3005 -- Flight Test Attendance 03/09/19 | accepted | 3 | 1903 | S | 2 | Helen Kuni
Flight Operations | 3006 -- Flight Test Attendance 03/09/19 | accepted | 3 | 1903 | S | 2 | Rostyk Svitelskyi
Flight Operations | 3007 -- Flight Test Attendance 03/09/19 | accepted | 3 | 1903 | S | 2 | Liam Mortell
Flight Operations | 3008 -- Flight Test Attendance 03/09/19 | accepted | 3 | 1903 | S | 2 | Nathan Han
Flight Operations | 3009 -- Flight Test Attendance 03/09/19 | accepted | 3 | 1903 | S | 2 | Chris Hayner
Flight Operations | 3010 -- Flight Test Attendance 03/09/19 | accepted | 3 | 1903 | S | 2 | Jaspreet Sidhu
Flight Operations | 3011 -- Flight Test Attendance 03/09/19 | accepted | 3 | 1903 | S | 2 | Josh Lee
Flight Operations | 3012 - Data Tech 03/02/19 (copy) | accepted | 3 | 1903 | XS | 1 | Chris Hayner
Flight Operations | 3013 - Data Tech 03/02/19 (copy) | accepted | 3 | 1903 | XS | 1 | Liam Mortell
Flight Operations | 3014 - Data Tech 03/09/19 | accepted | 3 | 1903 | XS | 1 | Wasif Siddique
Flight Operations | 3015 - Data Tech 03/12/19 | accepted | 3 | 1903 | XS | 1 | Jaspreet Sidhu
General AFSL Lab | 3016 - Flight Ops Administration (1903) | accepted | 3 | 1903 | XL | 8 | Helen Kuni
LARI | 3017 - Research a tooling architecture | accepted | 3 | 1903 | L | 5 | Wasif Siddique
LARI | 3018 - Figure out hosting options at UW | accepted | 3 | 1903 | M | 3 | Wasif Siddique
LARI | 3019 - Figure out LARI requirements for ci/cd pipeline | accepted | 3 | 1903 | S | 2 | Wasif Siddique
Visual Anchoring | 3020 — Visual Anchoring move onto Pear | accepted | 3 | 1903 | S | 2 | Rostyk Svitelskyi
CellNav | 3XXX - Winter Quarter Trello Board work | accepted | 1 | 1903 | M | 3 | Pranav Natarajan
CellNav | 3XXX - Winter Quarter Trello Board work | accepted | 1 | 1903 | XL | 8 | Matt Davis
LARAMID | 3021 – LARAMID Manual update for Samwise, Frodo and Merry | dropped | #N/A | 1906 | S | 2 | John Choi
LARAMID | 3022 – LARAMID System Full Configuration CAD | accepted | 1 | 1903 | XS | 1 | John Choi
LARAMID | 3023 – LARAMID Ground Test with new Mounting Structure | accepted | 1 | 1903 | XS | 1 | John Choi
Flight Operations | 3024 -- Flight Test Attendance 03/23/19 | accepted | 3 | 1903 | S | 2 | Helen Kuni
Flight Operations | 3025 -- Flight Test Attendance 03/23/19 | accepted | 3 | 1903 | S | 2 | Rostyk Svitelskyi
Flight Operations | 3026 -- Flight Test Attendance 03/23/19 | accepted | 3 | 1903 | S | 2 | Chris Hayner
Flight Operations | 3027 -- Flight Test Attendance 03/23/19 | accepted | 3 | 1903 | S | 2 | Nicholas Price
Flight Operations | 3028 - Data Tech 03/23/19 | accepted | 3 | 1903 | XS | 1 | Nicholas Price
Visual Anchoring | 3029 — Visual Anchoring flight test result process | accepted | 3 | 1904 | L | 5 | Rostyk Svitelskyi
Visual Anchoring | 3030 — Visual Anchoring flight test result presentation | accepted | 3 | 1904 | M | 3 | Rostyk Svitelskyi
Visual Anchoring | 3031 — Visual Anchoring controller study | accepted | 3 | 1904 | XL | 8 | Rostyk Svitelskyi
LARI | 3032 - C# GUI Tutorial | accepted | 3 | 1904 | M | 3 | Sam Lee
Flight Operations | 3033 -- Flight Test Attendance 04/13/19 | accepted | 3 | 1904 | S | 2 | Helen Kuni
Flight Operations | 3034 -- Flight Test Attendance 04/13/19 | accepted | 3 | 1904 | S | 2 | Rostyk Svitelskyi
Flight Operations | 3035 -- Flight Test Attendance 04/13/19 | accepted | 3 | 1904 | S | 2 | Tadej Kosel
Flight Operations | 3036 -- Flight Test Attendance 04/13/19 | accepted | 3 | 1904 | S | 2 | Nicholas Price
Flight Operations | 3037 -- Flight Test Attendance 04/13/19 | accepted | 3 | 1904 | S | 2 | Chris Hayner
Flight Operations | 3038 - Data Tech 04/13/19 | accepted | 3 | 1904 | XS | 1 | Nicholas Price
General AFSL Lab | 3039 - Flight Ops Administration (1904) | accepted | 3 | 1904 | XL | 8 | Helen Kuni
General AFSL Lab | 3040 – Perforce Visual Client (copy) | accepted | 3 | 1904 | S | 2 | Rori Fortmann
General AFSL Lab | 3041 – Perforce Visual Client (copy) | accepted | 3 | 1907 | S | 2 | Arvean Labib
General AFSL Lab | 3042 – Perforce Visual Client (copy) | dropped | #N/A | 1907 | S | 2 | Aaditya Srivathsan
General AFSL Lab | 3043 – Perforce Visual Client (copy) | dropped | #N/A | 1905 | S | 2 | Rabab Ibrahim
Visual Anchoring | 3044 — Visual Anchoring plane and computer preparation | accepted | 3 | 1904 | S | 2 | Rostyk Svitelskyi
Visual Anchoring | 3045 — Visual Anchoring controller study (copy) | accepted | 3 | 1904 | S | 2 | Rostyk Svitelskyi
Visual Anchoring | 3046 — Visual Anchoring Documentation | accepted | 3 | 1905 | S | 2 | Rostyk Svitelskyi
Visual Anchoring | 3047 — Visual Anchoring Promo Video | accepted | 3 | 1906 | L | 5 | Rostyk Svitelskyi
Flight Operations | 3048 -- Flight Test Attendance 04/17/19 | accepted | 3 | 1904 | S | 2 | Helen Kuni
Flight Operations | 3049 -- Flight Test Attendance 04/17/19 | accepted | 3 | 1904 | S | 2 | Rostyk Svitelskyi
Flight Operations | 3050 -- Flight Test Attendance 04/17/19 | accepted | 3 | 1904 | S | 2 | Tadej Kosel
Flight Operations | 3051 -- Flight Test Attendance 04/17/19 | accepted | 3 | 1904 | S | 2 | Nicholas Price
Flight Operations | 3052 - Data Tech 04/17/19 | accepted | 3 | 1904 | XS | 1 | Nicholas Price
Flight Operations | 3053 -- Flight Test Attendance 04/20/19 | accepted | 3 | 1904 | S | 2 | Helen Kuni
Flight Operations | 3054 -- Flight Test Attendance 04/20/19 | accepted | 3 | 1904 | S | 2 | Chung Choi
Flight Operations | 3055 -- Flight Test Attendance 04/20/19 | accepted | 3 | 1904 | S | 2 | Dylan Hoff
Flight Operations | 3056 -- Flight Test Attendance 04/20/19 | accepted | 3 | 1904 | S | 2 | Rostyk Svitelskyi
Flight Operations | 3057 -- Flight Test Attendance 04/20/19 | accepted | 3 | 1904 | S | 2 | Natanael Putra
Flight Operations | 3058 - Data Tech 04/20/19 | accepted | 3 | 1904 | XS | 1 | Nicholas Price
Visual Anchoring | 3059 — Visual Anchoring flight test aircraft prepare | accepted | 3 | 1904 | XS | 1 | Rostyk Svitelskyi
Visual Anchoring | 3060 — Visual Anchoring Journal Article (1019 copy) | accepted | 3 | 1905 | XL | 8 | Rostyk Svitelskyi
LARI | 3061 - LARI Development Environment Setup (copy) | accepted | 3 | 1905 | L | 5 | Sam Lee
LARI | 3062 - C# GUI Tutorial (copy) | dropped | #N/A | 1904 | L | 5 | -
Chelan Land Trust | 3063 - Potential Flight Path Planning | accepted | 3 | 1905 | XS | 1 | An Nguyen
Chelan Land Trust | 3064 - Vehicle & Sensor Research | accepted | 3 | 1904 | XS | 1 | An Nguyen
General AFSL Lab | 3065 - AFSL Condor Repairs | accepted | 3 | 1904 | S | 2 | Nicholas Price
General AFSL Lab | 3066 - 2019 Safety Survey | accepted | 3 | 1904 | XS | 1 | Nicholas Price
Flight Operations | 3067 – Flight Training Program – Multi-Rotor (Copy) | accepted | 3 | 1906 | L | 5 | Sean Carda
Flight Operations | 3068 – Flight Training Program – Fixed Wing (Copy) | accepted | 3 | 1906 | L | 5 | Chris Hayner
General AFSL Lab | 3069 - Part 107 Test Preparation (copy) | accepted | 3 | 1907 | M | 3 | Chris Hayner
General AFSL Lab | 3070 - Engineering Discovery Days | accepted | 3 | 1904 | S | 2 | Helen Kuni
General AFSL Lab | 3071 - Engineering Discovery Days | accepted | 3 | 1904 | S | 2 | Nicholas Price
General AFSL Lab | 3072 - Engineering Discovery Days | accepted | 3 | 1904 | XS | 1 | Rostyk Svitelskyi
General AFSL Lab | 3073 - Engineering Discovery Days | accepted | 3 | 1904 | XS | 1 | Chris Hayner
General AFSL Lab | 3074 - Engineering Discovery Days | accepted | 3 | 1904 | XS | 1 | Josh Lee
General AFSL Lab | 3075 - Engineering Discovery Days | accepted | 3 | 1904 | XS | 1 | An Nguyen
Risk Assessment | 3076 - Automating Unit Tests | accepted | 3 | 1904 | S | 2 | Liam Mortell
Risk Assessment | 3077 - Automating Unit Tests | accepted | 3 | 1904 | S | 2 | Zech Latimer
Risk Assessment | 3078 - Creating Drag Coefficient Function | accepted | 3 | 1904 | XS | 1 | Liam Mortell
Risk Assessment | 3079 - Quadrotor Inertia Matrix | accepted | 3 | 1904 | S | 2 | Liam Mortell
LARAMID | 3080 - Docking Frame Extension Build | accepted | 3 | 1904 | XS | 1 | Natanael Putra
LARAMID | 3081 - Landing Gear Rebuild | accepted | 3 | 1905 | M | 3 | Natanael Putra
Flight Operations | 3057 -- Flight Test Attendance 05/04/19 | accepted | 3 | 1905 | S | 2 | Helen Kuni
Flight Operations | 3058 -- Flight Test Attendance 05/04/19 | accepted | 3 | 1905 | S | 2 | Chung Choi
Flight Operations | 3059 -- Flight Test Attendance 05/04/19 | accepted | 3 | 1905 | S | 2 | Cameron Tavakoli
Flight Operations | 3060 -- Flight Test Attendance 05/04/19 | accepted | 3 | 1905 | S | 2 | Chris Hayner
Flight Operations | 3061 -- Flight Test Attendance 05/04/19 | accepted | 3 | 1905 | S | 2 | Nathan Han
Flight Operations | 3062 -- Flight Test Attendance 05/04/19 | accepted | 3 | 1905 | S | 2 | Rostyk Svitelskyi
Flight Operations | 3063 -- Flight Test Attendance 05/04/19 | accepted | 3 | 1905 | S | 2 | Sean Carda
Flight Operations | 3064 - Data Tech 05/04/19 | accepted | 3 | 1904 | XS | 1 | Chris Hayner
Visual Anchoring | 3065 — Visual Anchoring controller study (copy) | accepted | 3 | 1905 | S | 2 | Rostyk Svitelskyi
Flight Operations | 3066 -- Flight Test Attendance 05/09/19 | accepted | 3 | 1905 | S | 2 | Helen Kuni
Flight Operations | 3067 -- Flight Test Attendance 05/09/19 | accepted | 3 | 1905 | S | 2 | Chung Choi
Flight Operations | 3068 -- Flight Test Attendance 05/09/19 | accepted | 3 | 1905 | S | 2 | Chris Hayner
Flight Operations | 3069 -- Flight Test Attendance 05/11/19 | accepted | 3 | 1905 | S | 2 | Helen Kuni
Flight Operations | 3070 -- Flight Test Attendance 05/11/19 | accepted | 3 | 1905 | S | 2 | Chung Choi
Flight Operations | 3071 -- Flight Test Attendance 05/11/19 | accepted | 3 | 1905 | S | 2 | Rostyk Svitelskyi
Flight Operations | 3072 -- Flight Test Attendance 05/11/19 | accepted | 3 | 1905 | S | 2 | Chris Hayner
Flight Operations | 3073 -- Flight Test Attendance 05/11/19 | accepted | 3 | 1905 | S | 2 | John Choi
Flight Operations | 3074 -- Flight Test Attendance 05/11/19 | accepted | 3 | 1905 | S | 2 | Cameron Tavakoli
Flight Operations | 3075 - Data Tech 05/09/19 | accepted | 3 | 1906 | XS | 1 | Chris Hayner
Flight Operations | 3076 - Data Tech 05/11/19 | accepted | 3 | 1905 | XS | 1 | Rostyk Svitelskyi
Visual Anchoring | 3082 – Visual Anchoring thesis (copy) | accepted | 1 | 1905 | XL | 8 | Rostyk Svitelskyi
Visual Anchoring | 3083 – Visual Anchoring thesis Presentation | accepted | 1 | 1905 | XL | 8 | Rostyk Svitelskyi
LARI | 3084 - Load Components | accepted | 3 | 1905 | L | 5 | Kevin Zhu
LARI | 3085 - Load Components (copy) | accepted | 3 | 1905 | L | 5 | Shawn Stanley
LARI | 3086 - Load Components (copy) | accepted | 3 | 1905 | L | 5 | Abhishek Babu
LARI | [5 empty] | #N/A
General AFSL Lab | 3087 - Perforce Visual Client (copy) | accepted | 3 | 1905 | S | 2 | Abhishek Babu
LARI | 3088 - Populate Components (copy) | accepted | 3 | 1905 | L | 5 | Sam Lee
LARI | 3089 - Populate Components (copy) | accepted | 3 | 1905 | L | 5 | Mozes Jacobs
LARI | 3090 - Close Window on Apply | accepted | 3 | 1905 | M | 3 | Kevin Zhu
LARI | 3091 - Close Window on Apply (copy) | accepted | 3 | 1905 | M | 3 | Shawn Stanley
LARI | 3092 - Close Window on Apply (copy) | accepted | 3 | 1905 | M | 3 | Abhishek Babu
LARI | 3093 - Close Window on Apply (copy) | accepted | 3 | 1905 | M | 3 | Veen Oung
LARI | 3094 - Create Crash History object [Backend] | in backlog | 0 | 1908 | L | 5 | -
LARI | 3095 - Create Notes object [Backend] | in backlog | 0 | 1908 | L | 5 | -
LARI | 3096 - Change Component Implementation [Backend] | in backlog | 0 | 1908 | L | 5 | -
LARI | 3097 - Add startDate to AFSLSystem [Backend] | in backlog | 0 | 1908 | L | 5 | -
LARI | 3098 - Make all Data objects comparable [Backend] | in backlog | 0 | 1908 | L | 5 | -
LARI | 3099 - Make all Data objects comparable [Backend] | in backlog | 0 | 1908 | L | 5 | -
LARI | 3100 - Speed Up Fleet Access in Equipage [Backend] | in backlog | 0 | 1908 | L | 5 | -
General AFSL Lab | 3101- Repairing Gary | accepted | 3 | 1904 | M | 3 | Nathan Han
General AFSL Lab | 3102- Multirotor Flight Training - Simulator Time | accepted | 3 | 1906 | S | 2 | Nathan Han
General AFSL Lab | 3103 - Repair battery packs | accepted | 3 | 1905 | XS | 1 | Nathan Han
Flight Operations | 3104 -- Flight Test Attendance 04/27/19 | accepted | 3 | 1904 | S | 2 | Helen Kuni
Flight Operations | 3105 -- Flight Test Attendance 04/27/19 | accepted | 3 | 1904 | S | 2 | Rostyk Svitelskyi
Flight Operations | 3106 -- Flight Test Attendance 04/27/19 | accepted | 3 | 1904 | S | 2 | Nicholas Price
Flight Operations | 3107 -- Flight Test Attendance 04/27/19 | accepted | 3 | 1904 | S | 2 | Nathan Han
General AFSL Lab | 3108 - Flight Ops Administration (1905) | accepted | 3 | 1905 | M | 3 | Helen Kuni
LARI | 3109 — Setup Continuous Integration Tool (copy) | accepted | 3 | 1905 | XL | 8 | Wasif Siddique
Risk Assessment | 3110 - outer loop controller design | accepted | 3 | 1905 | S | 2 | Zech Latimer
LARI | 3111 - Continuous Integration Tool Documentation | accepted | 3 | 1905 | L | 5 | Wasif Siddique
Visual Anchoring | 3112 – Visual Anchoring thesis (copy) | accepted | 3 | 1906 | M | 3 | Rostyk Svitelskyi
Visual Anchoring | 3112 – Visual Anchoring journal article (copy) | in progress | 1 | 1908 | M | 3 | Rostyk Svitelskyi
Mapping | 3113 - Pix4D Runtime Improvement Testing | accepted | 3 | 1906 | M | 3 | Eli Sitchin
Flight Operations | 3114 -- Flight Test Attendance 06/22/19 | accepted | 3 | 1906 | S | 2 | Helen Kuni
Flight Operations | 3115 -- Flight Test Attendance 06/22/19 | accepted | 3 | 1906 | S | 2 | Nicholas Price
Flight Operations | 3116 -- Flight Test Attendance 06/22/19 | accepted | 3 | 1906 | S | 2 | Chris Hayner
Flight Operations | 3117 -- Flight Test Attendance 06/22/19 | accepted | 3 | 1906 | S | 2 | An Nguyen
Flight Operations | 3118 -- Flight Test Attendance 06/22/19 | accepted | 3 | 1906 | S | 2 | Rori Fortmann
Flight Operations | 3119 -- Flight Test Attendance 06/22/19 | accepted | 3 | 1906 | S | 2 | Liam Mortell
Flight Operations | 3120 - Data Tech 06/22/19 | in progress | 1 | 1905 | XS | 1 | Liam Mortell
Flight Operations | 3121 - Multirotor Flight Training - Simulator Time | accepted | 3 | 1906 | S | 2 | Eli Sitchin
Mapping | 3122 - Pix4D GCP Reduction Testing | accepted | 3 | 1906 | XS | 1 | Eli Sitchin
Search and Locate | 3123 - Get Samwise Flight Ready | accepted | 3 | 1908 | S | 2 | Rori Fortmann
General AFSL Lab | 3124 - Fix Inspire | blocked | 5 | 1908 | XL | 8 | Chris Hayner |  | 95%
Search and Locate | 3125 - Integrating RedEdge into Samwise | accepted | 3 | 1907 | S | 2 | Eli Sitchin
Search and Locate | 3125 - Integrating RedEdge into Samwise (copy) | accepted | 3 | 1907 | S | 2 | Chris Hayner
Search and Locate | 3126 - Integrating RedEdge into the Inspire | dropped | #N/A | 1908 | S | 2
Search and Locate | 3126 - Integrating RedEdge into the Inspire (copy) | dropped | #N/A | 1907 | S | 2 | Chris Hayner
Search and Locate | 3127 - Software to be used to control Drone during SAR | accepted | 3 | 1907 | S | 2 | Parker Mayhew
Flight Operations | 3128 - Processing CDLT Flight Data in Pix4D | accepted | 3 | 1907 | XS | 1 | Eli Sitchin
Flight Operations | 3129 -- Flight Test Attendance 07/02/19 | accepted | 3 | 1907 | S | 2 | Helen Kuni
Flight Operations | 3130 -- Flight Test Attendance 07/02/19 | accepted | 3 | 1907 | S | 2 | Liam Mortell
Flight Operations | 3131 -- Flight Test Attendance 07/02/19 | accepted | 3 | 1907 | S | 2 | Rori Fortmann
Flight Operations | 3132 -- Flight Test Attendance 07/02/19 | accepted | 3 | 1907 | S | 2 | An Nguyen
Flight Operations | 3133 -- Flight Test Attendance 07/02/19 | accepted | 3 | 1907 | S | 2 | Eli Sitchin
Flight Operations | 3134 -- Flight Test Attendance 07/02/19 | accepted | 3 | 1907 | S | 2 | Nicholas Price
General AFSL Lab | 3135 - Part 107 Test Preparation | accepted | 3 | 1907 | M | 3 | Eli Sitchin
General AFSL Lab | 3136 - Flight Ops Administration (1906) | accepted | 3 | 1906 | M | 3 | Helen Kuni
General AFSL Lab | 3137 - Flight Ops Administration (1906) | accepted | 3 | 1906 | M | 3 | Liam Mortell
Risk Assessment | 3138 - RUACH Development | accepted | 3 | 1906 | S | 2 | Liam Mortell
General AFSL Lab | 3139 – Perforce Visual Client (copy) | accepted | 3 | 1906 | S | 2 | Eli Sitchin
General AFSL Lab | 3139 – Perforce Visual Client (copy) | accepted | 3 | 1906 | S | 2 | Parker Mayhew
General AFSL Lab | 3139 – Perforce Visual Client (copy) | in backlog | 0 | 1908 | S | 2 | Ravi Sangani
General AFSL Lab | 3139 – Perforce Visual Client (copy) | in backlog | 0 | 1908 | S | 2 | David Wong
Search and Locate | 3140 - Use Pix4D to analyze data taken off of the RedEdge | accepted | 3 | 1907 | XS | 1 | Eli Sitchin
Search and Locate | 3141 - Creation of a database of project related material | accepted | 3 | 1907 | S | 2 | Chris Hayner
Search and Locate | 3142 - Research the FAA regulations around SAL Drone Missions | accepted | 3 | 1907 | S | 2 | Howard Peng
Search and Locate | 3143 - Plan for SAL Flight Test 7/23/19 | accepted | 3 | 1907 | XS | 1 | Chris Hayner
Flight Operations | 3144 - Research on Pix4D Merging Without GCPs | accepted | 3 | 1907 | XS | 1 | Eli Sitchin
Mapping | 3145 - Map Grass Heights at Karen's Farm | accepted | 3 | 1907 | XS | 1 | Eli Sitchin
Mapping | 3146 - Integrating LiDAR into Samwise | accepted | 3 | 1908 | S | 2 | Eli Sitchin
Flight Operations | 3147 - Fixed-Wing Simulator Time | accepted | 3 | 1907 | XS | 1 | Eli Sitchin
Search and Locate | 3148 - Get MAPSS Gimbal Operational | accepted | 3 | 1907 | S | 2 | Chris Hayner
Search and Locate | 3149 - Get Fat Shark and Mobius Operational | accepted | 3 | 1908 | XS | 1 | An Nguyen
Search and Locate | 3150 - Plan for SAL Flight Test (copy) 7/23/19 | accepted | 3 | 1907 | XS | 1 | An Nguyen
Search and Locate | 3151 - Plan for SAL Flight Test (copy) 7/23/19 | accepted | 3 | 1907 | XS | 1 | Parker Mayhew
Flight Operations | 3152 - Processing 07/19/19 flight test data in Pix4D | accepted | 3 | 1908 | S | 2 | Eli Sitchin
Flight Operations | 3153 -- Flight Test Attendance 07/13/19 | accepted | 3 | 1907 | S | 2 | Helen Kuni
Flight Operations | 3154 -- Flight Test Attendance 07/13/19 | accepted | 3 | 1907 | S | 2 | Rori Fortmann
Flight Operations | 3155 -- Flight Test Attendance 07/13/19 | accepted | 3 | 1907 | S | 2 | Eli Sitchin
Flight Operations | 3156 -- Flight Test Attendance 07/13/19 | accepted | 3 | 1907 | S | 2 | Chris Hayner
Flight Operations | 3157 -- Flight Test Attendance 07/19/19 | accepted | 3 | 1907 | S | 2 | Helen Kuni
Flight Operations | 3158 -- Flight Test Attendance 07/19/19 | accepted | 3 | 1907 | S | 2 | Eli Sitchin
Flight Operations | 3159 -- Flight Test Attendance 07/19/19 | accepted | 3 | 1907 | S | 2 | Liam Mortell
Flight Operations | 3160 -- Flight Test Attendance 07/19/19 | accepted | 3 | 1907 | S | 2 | Rori Fortmann
Flight Operations | 3161 -- Flight Test Attendance 07/19/19 | accepted | 3 | 1907 | S | 2 | An Nguyen
Chelan Land Trust | 3162 - Creation of CDLT Site Data Spreadsheet | accepted | 3 | 1907 | XS | 1 | Eli Sitchin
Search and Locate | 3163 - Plan for SAL Flight Test (copy) 7/23/19 | accepted | 3 | 1907 | XS | 1 | Helen Kuni
Search and Locate | 3164 - Plan for SAL Flight Test (copy) 7/23/19 | accepted | 3 | 1907 | XS | 1 | Liam Mortell
Search and Locate | 3165 - Plan for SAL Flight Test (copy) 7/23/19 | accepted | 3 | 1907 | XS | 1 | Eli Sitchin
Search and Locate | 3166 - Plan for SAL Flight Test (copy) 7/23/19 | accepted | 3 | 1907 | XS | 1 | Howard Peng
Ground Penetrating Radar | 3167 - Get Argo flight ready | in progress | 1 | 1908 | M | 3 | Chris Hayner
Ground Penetrating Radar | 3168 - Design and manufacture radar antenna mounts | in progress | 1 | 1908 | M | 3 | Chris Hayner
General AFSL Lab | 3169 - Research Lab Tools | accepted | 3 | 1907 | XS | 1 | Chris Hayner
Search and Locate | 3170 - SAL Administration (1907) | accepted | 3 | 1907 | S | 2 | Chris Hayner
Ground Penetrating Radar | 3171 - Tuning Pixhawk 2 | in progress | 1 | 1908 | S | 2 | Chris Hayner
Mapping | 3172 - Manufacture Lidar Mounts | accepted | 3 | 1907 | XS | 1 | Chris Hayner
Flight Operations | 3173 -- Flight Test Attendence 07/13/19 (NDCL) | accepted | 3 | 1907 | XS | 1 | Chris Hayner
General AFSL Lab | 3174 - Part 107 Test Preparation | accepted | 3 | 1907 | M | 3 | An Nguyen
Search and Locate | 3175 - Mount Camera Gimbal onto Samwise | accepted | 3 | 1908 | XS | 1 | Eli Sitchin
General AFSL Lab | 3176 - Research Security Camera Live Stream | accepted | 3 | 1907 | XS | 1 | Eli Sitchin
Search and Locate | 3177 - FAA Waiver Research | accepted | 3 | 1908 | S | 2 | Howard Peng
Search and Locate | 3178 - Python Development | accepted | 3 | 1908 | XL | 8 | Parker Mayhew
Search and Locate | 3179 - MATLAB Development | dropped | #N/A | 1908 | M | 3 | Parker Mayhew
Search and Locate | 3180 - MATLAB Development (Copy) | dropped | #N/A | 1908 | M | 3 | Chris Hayner
Flight Operations | 3181 -- Flight Test Attendence 08/01/19 (NDCL) | accepted | 3 | 1908 | XS | 1 | Chris Hayner
Flight Operations | 3182 -- Flight Test Attendence 08/01/19 (NDCL) | accepted | 3 | 1908 | XS | 1 | Eli Sitchin
Ground Penetrating Radar | 3183 - Design Antenna Mount for Argo | accepted | 3 | 1908 | XS | 1 | Eli Sitchin
Flight Operations | 3184 – Flight Training Program – Multi Rotor (Copy) | accepted | 3 | 1907 | L | 5 | Chris Hayner
Flight Operations | 3185 – Flight Training Program – Multi Rotor (Copy) | accepted | 3 | 1908 | S | 2 | Eli Sitchin
Flight Operations | 3186 – Flight Training Program – Multi Rotor (Copy) | in progress | 1 | 1908 | L | 5 | An Nguyen
Chelan Land Trust | 3187 - CDLT Presentation | accepted | 3 | 1908 | S | 2 | An Nguyen
Mapping | 3188 - Research Pix4D Alternatives | accepted | 3 | 1907 | S | 2 | An Nguyen
Flight Operations | 3189 - Flight Ops Administration (1907) | accepted | 3 | 1907 | XL | 8 | Helen Kuni
Flight Operations | 3190 - Flight Ops Administration (1907) | accepted | 3 | 1907 | L | 5 | Liam Mortell
CellNav | 3191 - Raspberry Pi Power System | accepted | 3 | 1907 | S | 2 | Parker Mayhew
Chelan Land Trust | 3192 - CDLT Presentation and Future Test Site Selection | accepted | 3 | 1908 | XS | 1 | Eli Sitchin
Flight Operations | 3193 -- Flight Test Attendence 08/02/19 (NDCL) | dropped | #N/A | 1908 | XS | 1 | Chris Hayner
Search and Locate | 3194 - Make SAL Presentation | accepted | 3 | 1908 | S | 2 | Chris Hayner
Search and Locate | 3195 - Make SAL Presentation (Copy) | finished | 2 | 1909 | S | 2 | Helen Kuni
Search and Locate | 3196 - Produce a live video feed from a UAS | accepted | 3 | 1908 | S | 2 | An Nguyen
Search and Locate | 3196 - Produce a live video feed from a UAS (copy) | accepted | 3 | 1908 | S | 2 | Eli Sitchin
Search and Locate | 3197 - Install YOLO w/ Darknet on lab computer | accepted | 3 | 1908 | S | 2 | Chris Hayner
Search and Locate | 3197 - Install YOLO w/ Darknet on lab computer (Copy) | accepted | 3 | 1908 | S | 2 | Parker Mayhew
Risk Assessment | 3198 - Fixing and tuning quadrotor controller for simulation | accepted | 3 | 1907 | M | 3 | Zech Latimer
Risk Assessment | 3199 - Setting up automated simulation infrastructure | accepted | 3 | 1907 | L | 5 | Zech Latimer
Risk Assessment | 3200 - Develop saving and visualization infrastructure | accepted | 3 | 1907 | S | 2 | Zech Latimer
Risk Assessment | 3200 - Develop saving and visualization infrastructure (Copy) | accepted | 3 | 1907 | S | 2 | Liam Mortell
Risk Assessment | 3201 - Final Report and Documentation Rough Draft | accepted | 3 | 1907 | S | 2 | Zech Latimer
Risk Assessment | 3201 - Final Report and Documentation Rough Draft (Copy) | accepted | 3 | 1907 | S | 2 | Liam Mortell
Search and Locate | 3202 - Determine FLIR Duo Pro R fire saturation | accepted | 3 | 1908 | XS | 1 | Eli Sitchin
Flight Operations | 3203 -- Flight Test Attendence 08/03/19 | accepted | 3 | 1908 | S | 2 | Helen Kuni
Flight Operations | 3204 -- Flight Test Attendence 08/03/19 | accepted | 3 | 1908 | S | 2 | Chris Hayner
Flight Operations | 3205 -- Flight Test Attendence 08/03/19 | accepted | 3 | 1908 | S | 2 | Rori Fortmann
Flight Operations | 3206 -- Flight Test Attendence 08/03/19 | accepted | 3 | 1908 | S | 2 | An Nguyen
Flight Operations | 3207 -- Flight Test Attendence 08/03/19 | accepted | 3 | 1908 | S | 2 | Parker Mayhew
Flight Operations | 3208 -- Flight Test Attendence 08/03/19 | accepted | 3 | 1908 | S | 2 | Alyssa Mell
Flight Operations | 3209 -- Flight Test Attendence 08/03/19 | accepted | 3 | 1908 | S | 2 | Nicholas Price
Search and Locate | 3210 - Python Development (Copy) | dropped | #N/A | 1908 | M | 3 | Chris Hayner
Search and Locate | 3211 - SAL Administration (1908) | accepted | 3 | 1908 | S | 2 | Chris Hayner
Search and Locate | 3212 - Research Neural Networks | in progress | 1 | 1908 | XS | 1 | Chris Hayner
Ground Penetrating Radar | 3213 -- Flight Test Attendence 08/08/19 | accepted | 3 | 1908 | XS | 1 | Chris Hayner
Search and Locate | 3214 - Give MAPSS gimbal pitch control | accepted | 3 | 1908 | M | 3 | Rori Fortmann
Ground Penetrating Radar | 3215 - Integrate RTK GPS system onto ARGO | dropped | #N/A | 1908 | S | 2 | Chris Hayner
Search and Locate | 3216 - Create a method for dataset creation in YOLO | accepted | 3 | 1908 | XL | 8 | Chris Hayner
Search and Locate | 3217 - Create a method for dataset creation in YOLO (Copy) | accepted | 3 | 1908 | XL | 8 | Parker Mayhew
Search and Locate | 3218 - Initial Research into Integrating Exaustive Search into SAL | in progress | 1 | 1908 | M | 3 | Chris Hayner
Search and Locate | 3219 - Initial Research into Integrating Exaustive Search into SAL (copy) | in progress | 1 | 1908 | L | 5 | Akshay Raikar
Search and Locate | 3220 - Get Mobius Gimbal up and running | accepted | 3 | 1908 | XS | 1 | An Nguyen
Ground Penetrating Radar | 3221 -- Flight Test Attendence 08/08/19 (Copy) | accepted | 3 | 1908 | XS | 1 | Parker Mayhew
Ground Penetrating Radar | 3222 -- Flight Test Attendence 08/08/19 (Copy) | accepted | 3 | 1908 | XS | 1 | Rori Fortmann
Ground Penetrating Radar | 3223 - Make a XT90 Charging Cord | in backlog | 0 | 1908 | XS | 1
Search and Locate | 3224 - High Quality Radio Transmission Product Research (Copy) | accepted | 3 | 1908 | S | 2 | An Nguyen
Search and Locate | 3225 - Troubleshoot FPV system | accepted | 3 | 1908 | S | 2 | An Nguyen
Search and Locate | 3226 - Investigate New Drone Platforms | in backlog | 0 | 1908 | XS | 1
Ground Penetrating Radar | 3227 - Investigate New Drone Platforms | in progress | 1 | 1908 | XS | 1 | Chris Hayner
Mapping | 3228 - Familiarize with Velodyne Pucklite | accepted | 3 | 1908 | XS | 1 | Chris Hayner
Search and Locate | 3229 - SciTech Paper | stretch | #N/A | 1908 | XL | 8 | Chris Hayner
Search and Locate | 3230 - Investigate External Dataset Manufacturing | accepted | 3 | 1908 | XS | 1 | Chris Hayner
Mapping | 3231 - Integrate Velodyne Pucklite onto Argo | in progress | 1 | 1908 | S | 2 | Chris Hayner
Mapping | 3232 - Integrate Velodyne Pucklite onto Argo (Copy) | accepted | 3 | 1908 | XS | 1 | Eli Sitchin
Search and Locate | 3233 - AFSL Waiver Research | accepted | 3 | 1908 | S | 2 | Howard Peng
General AFSL Lab | 3234 - Part 107 Test Preparation | accepted | 3 | 1908 | M | 3 | Rori Fortmann
General AFSL Lab | 3235 - Anakin Repairs: Foam repair | in progress | 1 | 1908 | M | 3 | Rori Fortmann
General AFSL Lab | 3236 - Anakin Repairs: Foam repair (Copy) | in progress | 1 | 1908 | M | 3 | Arvean Labib
General AFSL Lab | 3237 - Anakin Repairs: Electronic testing/Pixhawk setup | accepted | 3 | 1908 | XS | 1 | Rori Fortmann
General AFSL Lab | 3238 - Anakin Repairs: Electronic testing/Pixhawk setup (Copy) | accepted | 3 | 1908 | XS | 1 | An Nguyen
Mapping | 3239 - Process 08/15/19 Flight Test Data (No GCPs) | accepted | 3 | 1908 | XS | 1 | Eli Sitchin
Search and Locate | 3240 - AFSL Waiver Research (Copy) | accepted | 3 | 1908 | L | 5 | An Nguyen
Search and Locate | 3241 - Computer Vision/YOLO Introduction | accepted | 3 | 1908 | S | 2 | Akshay Raikar
Search and Locate | 3242 - Thermal Imaging analysis with a Neural Network | in backlog | 0 | 1908 | S | 2
Search and Locate | 3243 - Location/Fabrication of MAPSS gimbal mount to Argo | dropped | #N/A | 1908 | S | 2
Search and Locate | 3244 - Creation of SAL Documentation for Perforce | in progress | 1 | 1908 | S | 2 | Chris Hayner
Search and Locate | 3244 - Creation of SAL Documentation for Perforce (copy) | in progress | 1 | 1908 | XS | 1 | Helen Kuni
Search and Locate | 3244 - Creation of SAL Documentation for Perforce (copy) | in progress | 1 | 1908 | S | 2 | Parker Mayhew
General AFSL Lab | 3245 - Research in new tools/lab equipment | accepted | 3 | 1908 | S | 2 | Chris Hayner
Search and Locate | 3240 - AFSL Waiver Research (Copy) | in progress | 1 | 1908 | XS | 1 | Liam Mortell
Search and Locate | 3214 - Give MAPSS gimbal pitch control (copy) | accepted | 3 | 1908 | S | 2 | Chris Hayner
Search and Locate | 3215 - Shift YOLO to Tahoma | accepted | 3 | 1908 | L | 5 | Chris Hayner
Ground Penetrating Radar | 3216 - Interference Testing with Argo | in progress | 1 | 1908 | S | 2 | Chris Hayner
Ground Penetrating Radar | 3217 - Woof3D printer access | in progress | 1 | 1908 | XS | 1 | Chris Hayner
Ground Penetrating Radar | 3218 - MARV tuning practice | in progress | 1 | 1908 | S | 2 | Chris Hayner
Ground Penetrating Radar | 3219 - MARV tuning practice (copy) | in progress | 1 | 1908 | S | 2 | Rori Fortmann
Ground Penetrating Radar | 3220 - Repair Argo | in progress | 1 | 1908 | S | 2 | Chris Hayner
Ground Penetrating Radar | 3221 - CG testing with Argo | in progress | 1 | 1908 | S | 2 | Chris Hayner
Ground Penetrating Radar | 3222 - CG testing with Argo (copy) | in progress | 1 | 1908 | S | 2 | Rori Fortmann
Search and Locate | 3223 - Shift YOLO to Hyak | in progress | 1 | 1908 | L | 5 | Chris Hayner
Search and Locate
Search and Locate | 3224 - Create Tiling script for YOLO | in backlog | 0 | 1909 | L | 5

## sprint_metrics
Number | Sprint | Accepted Story Points | Descoped Story Points | Blocked Story Points | Stretch Goal Story Points | Number Developers | Accepted per Developer | Descoped per Developer | Blocked per Developer | Descoped% / Accepted%
1 | 1309 | 29 | 20 | 0 | - | 10 | 2.9 | 2 | 0 | 0.68966
2 | 1310 | 49 | 2 | 11 | - | 12 | 4.0833 | 0.16667 | 0.91667 | 0.040816
3 | 1311 | 56 | 21 | 18 | 65 | 16 | 3.5 | 1.3125 | 1.125 | 0.375
4 | 1312 | 125 | 29 | 18 | 68 | 17 | 7.3529 | 1.7059 | 1.0588 | 0.232
5 | 1313 | 32 | 77 | 20 | 69 | 17 | 1.8824 | 4.5294 | 1.1765 | 2.4062
6 | 1401 | 68 | 62 | 24 | 42 | 17 | 4 | 3.6471 | 1.4118 | 0.91176
7 | 1402 | 97 | 48 | 28 | 14 | 19 | 5.1053 | 2.5263 | 1.4737 | 0.49485
8 | 1403 | 96 | 45 | 9 | 38 | 19 | 5.0526 | 2.3684 | 0.47368 | 0.46875
9 | 1404 | 42 | 15 | 18 | - | 19 | 2.2105 | 0.78947 | 0.94737 | 0.35714
10 | 1405 | 49 | 33 | 21 | 69 | 21 | 2.3333 | 1.5714 | 1 | 0.67347
11 | 1406 | 49 | 16 | 29 | 70 | 21 | 2.3333 | 0.7619 | 1.381 | 0.32653
12 | 1407 | 40 | 0 | 22 | - | 8 | 5 | 0 | 2.75 | 0
13 | 1408 | 19 | 0 | 29 | - | 6 | 3.1667 | 0 | 4.8333 | 0
14 | 1409 | 62 | 0 | 26 | - | 5 | 12.4 | 0 | 5.2 | 0
15 | 1410 | 132 | 83 | 31 | 50 | 33 | 4 | 2.5152 | 0.93939 | 0.62879
16 | 1411 | 72 | 131 | 31 | 51 | 32 | 2.25 | 4.0938 | 0.96875 | 1.8194
17 | 1412 | 24 | 0 | 0 | 0 | 32 | 0.75 | 0 | 0 | 0
18 | 1501 | 102 | 62 | 34 | 133 | 32 | 3.1875 | 1.9375 | 1.0625 | 0.60784
19 | 1502 | 54 | 161 | 32 | 47 | 29 | 1.8621 | 5.5517 | 1.1034 | 2.9815
20 | 1503 | 63 | 113 | 11 | 42 | 24 | 2.625 | 4.7083 | 0.45833 | 1.7937
21 | 1504 | 70 | 128 | 0 | 16 | 28 | 2.5 | 4.5714 | 0 | 1.8286
22 | 1505 | 50 | 111 | 9 | 29 | 28 | 1.7857 | 3.9643 | 0.32143 | 2.22
23 | 1506 | 35 | 114 | 30 | 0 | 20 | 1.75 | 5.7 | 1.5 | 3.2571
24 | 1507 | 43 | 129 | 16 | 76 | 25 | 1.72 | 5.16 | 0.64 | 3
25 | 1508 | 119 | 68 | 22 | 22 | 24 | 4.9583 | 2.8333 | 0.91667 | 0.57143
26 | 1509 | 68 | 49 | 30 | 32 | 12 | 5.6667 | 4.0833 | 2.5 | 0.72059
27 | 1510 | 102 | 64 | 16 | 45 | 21 | 4.8571 | 3.0476 | 0.7619 | 0.62745
28 | 1511 | 42 | 146 | 29 | 24 | 24 | 1.75 | 6.0833 | 1.2083 | 3.4762
29 | 1512 | 101 | 122 | 27 | 40 | 24 | 4.2083 | 5.0833 | 1.125 | 1.2079
30 | 1601 | 198 | 106 | 54 | 53 | 36 | 5.5 | 2.9444 | 1.5 | 0.53535
31 | 1602 | 108 | 163 | 56 | 51 | 30 | 3.6 | 5.4333 | 1.8667 | 1.5093
32 | 1603 | 112 | 175 | 37 | 0 | 29 | 3.8621 | 6.0345 | 1.2759 | 1.5625
33 | 1604 | 211 | 152 | 35 | 0 | 22 | 9.5909 | 6.9091 | 1.5909 | 0.72038
34 | 1605 | 212 | 135 | 24 | 30 | 26 | 8.1538 | 5.1923 | 0.92308 | 0.63679
35 | 1606 | 171 | 74 | 10 | 48 | 23 | 7.4348 | 3.2174 | 0.43478 | 0.43275
36 | 1607 | 82 | 48 | 27 | 32 | 17 | 4.8235 | 2.8235 | 1.5882 | 0.58537
37 | 1608 | 37 | 75 | 0 | 0 | 13 | 2.8462 | 5.7692 | 0 | 2.027
38 | 1609 | 73 | 17 | 32 | 0 | 14 | 5.2143 | 1.2143 | 2.2857 | 0.23288
39 | 1610 | 131 | 180 | 5 | 11 | 32 | 4.0938 | 5.625 | 0.15625 | 1.374
40 | 1611 | 115 | 95 | 20 | 111 | 33 | 3.4848 | 2.8788 | 0.60606 | 0.82609
41 | 1612 | 79 | 99 | 19 | 60 | 31 | 2.5484 | 3.1935 | 0.6129 | 1.2532
42 | 1701 | 112 | 120 | 12 | 34 | 29 | 3.8621 | 4.1379 | 0.41379 | 1.0714
43 | 1702 | 202 | 99 | 24 | 84 | 27 | 7.4815 | 3.6667 | 0.88889 | 0.4901
44 | 1703 | 215 | 65 | 24 | 73 | 40 | 5.375 | 1.625 | 0.6 | 0.30233
45 | 1704 | 226 | 50 | 8 | 102 | 43 | 5.2558 | 1.1628 | 0.18605 | 0.22124
46 | 1705 | 243 | 51 | 23 | 94 | 44 | 5.5227 | 1.1591 | 0.52273 | 0.20988
47 | 1706 | 160 | 113 | 20 | 46 | 39 | 4.1026 | 2.8974 | 0.51282 | 0.70625
48 | 1707 | 127 | 61 | 59 | 72 | 24 | 5.2917 | 2.5417 | 2.4583 | 0.48031
49 | 1708 | 107 | 28 | 50 | 44 | 26 | 4.1154 | 1.0769 | 1.9231 | 0.26168
50 | 1709 | 35 | 0 | 15 | 5 | 5 | 7 | 0 | 3 | 0
51 | 1710 | 202 | 110 | 15 | 70 | 37 | 5.4595 | 2.973 | 0.40541 | 0.54455
52 | 1711 | 92 | 210 | 20 | 69 | 39 | 2.359 | 5.3846 | 0.51282 | 2.2826
53 | 1712 | 127 | 120 | 5 | 85 | 38 | 3.3421 | 3.1579 | 0.13158 | 0.94488
54 | 1801 | 202 | 195 | 12 | 58 | 42 | 4.8095 | 4.6429 | 0.28571 | 0.96535
55 | 1802 | 388 | 114 | 18 | 82 | 47 | 8.2553 | 2.4255 | 0.38298 | 0.29381
56 | 1803 | 147 | 136 | 11 | 69 | 40 | 3.675 | 3.4 | 0.275 | 0.92517

## developer_metrics
Accepted | 1309 | 1310 | 1311 | 1312 | 1313 | 1401 | 1402 | 1403 | 1404 | 1405 | 1406 | 1407 | 1408 | 1409 | 1410 | 1411 | 1412 | 1501 | 1502 | 1503 | 1504 | 1505 | 1506 | 1507 | 1508 | 1509 | 1510 | 1511 | 1512 | 1601 | 1602 | 1603 | 1604 | 1605 | 1606 | 1607 | 1608 | 1609 | 1610 | 1611 | 1612 | 1701 | 1702 | 1703 | 1704 | 1705 | 1706 | 1707 | 1708 | 1709 | 1710 | 1711 | 1712 | 1801 | TOTAL
Christopher Lum | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Kevin Ueunten | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Madison Peck | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Richard Fukutome | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Keisuke Tsujita | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Al Creigh | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Davis | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bao Le | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Henry Qin | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Brian Chang | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Taylor Campbell | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Ablog | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Federico Alvarez | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Noel Kimber | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Dai Tsukada | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Robert McSwain | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Seunghyun Ko | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ryan Valach | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Aleksandr Tereshchenkov | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Justin Yantus | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
John Marshall | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Taras Eremenko | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Alec Bueing | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Alexander Summers | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Angel Rodriguez | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Brian Carpenter | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ben Landes | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bryan Ghahremani | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Cory Hage | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Dana Fraij | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Erli Sheng | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Hao Ruan | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Henry Ly | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jason Hung | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Justin Taft | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Mason Steinbrueck | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Maxine Tan | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Melanie Clark | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Pei Jia | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Randy Lirano | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Robert Soo | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Jones | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sanjit Samra | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Bolte | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tarik Haj-Khalil | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Gage Winde | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Brendan Doyle Wade | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nick Anderson | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Justin Chu | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Benjamin Pennant | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bing Hu | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Christina Hsu | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Dichek | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ananya Tegegn | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Andrew Jacobson | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Casey Kilborn | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Felipe Medeiros | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Hanah Olliges | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jessica Trinh | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Lien Chang | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Scott Hoang | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Stephanie Rogers | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tyler Sheehan | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Yifu Wang | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zach Caratao | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Courtney Yeager | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ward Handley | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Robert Larson | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Adrien Simkins | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Emil Caga-anan | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Madison Mackenzie | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Carter Beamish | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Varnum-Lowry | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Shida Xu | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Pico Premvuti | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Luke Macfarlan | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Marissa Reid | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jennifer Look | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Gizelle Gando | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Charlie Shaw-Feather | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Elaiza Luker | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Harrison Stankey | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Scott An | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daehyun Kim | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zachary Pankratz | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Navdeep Sandhu | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Mia Lee | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Simeng Zhu | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zachary Williams | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sam Hordeski | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Connor Kafka | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Anupam Gupta | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Zhu | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Arwa Sait | [13 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nathan Isaman | [13 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Andrea Ostwald | [13 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Aaron Goldfogel | [13 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tadej Kosel | [13 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Arzouman | [30 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vitor Vasconcelos | [30 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Selina Lui | [30 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zhenzhen Su | [30 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Hannah Rotta | [36 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Andrew Park | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jenny Garner | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Aditya Sharma | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Chris Nee | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Lee | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Matthew | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Eze Klarnet | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
James Kurniawan | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jason Borgida | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Karine Chen | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Michael Brady | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Riley Turk | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ryan Grimes | [36 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Shumin Lin | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Truc Hoa | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Aaron Su | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Max McDonald | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Taehan Kook | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tommy Zhou | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
BJ Arun | [40 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Brett Myers | [40 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Kelsey Gabel | [40 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Kibaek Jeong | [40 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ge Bao | [41 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Maius Wong | [41 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sicong Huang | [41 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nikita Filippov | [41 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sam Buxton | [41 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Alex Banh | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Cole Morgan | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Conor Reiland | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Helen Kuni | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Lanhao Wu | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nicholas Price | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nick Armstrong | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nico Miguel | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Riley Harris | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Szymon Sarnowicz | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zach Kirwan | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Kai Simpson | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Carter Kraus | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Keegan McGrath | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ken Sekine | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Lee | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Gavin Cai | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Richard Jiang | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Adam Mokhalalati | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
TJ Stark | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Mircea Cozmei | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tinnabhand Patana-anake | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sean Lin | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Lemelin | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Forrest Malcolm | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Rick Huang | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tom Pflibsen | [46 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Eric Wang | [46 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Alex Lange | [46 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
David Kim | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ravi Patel | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Andrew Redd | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Emilynn Roehrich | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Areesa Trevino | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Chung Choi | [48 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bryson Bruno | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jason Yarrow | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sita Manne | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jaspreet Sidhu | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sai Ranganathan | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Griffin Klett | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Dylan Hoff | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sid Raman | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Deepanshu Gupta | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tushar Lakhanpal | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Firn Tieanklin | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Caelen Wang | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Joshua Brockschmidt | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Mike Kurnia | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Varith Hong | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vivian Hua | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Blake Fletcher | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Orion Black-Brown | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Travis Clement | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jacob Longhurst | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Grant Bringham | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tao Jin | [52 empty] | #VALUE! | #VALUE! | #VALUE!
Yao Dou | [52 empty] | #VALUE! | #VALUE! | #VALUE!
Sheershak Agarwal | [52 empty] | #VALUE! | #VALUE! | #VALUE!
Alex Bernard | [53 empty] | #VALUE! | #VALUE!
Christopher Lynch | [53 empty] | #VALUE! | #VALUE!
Gabriella Sciuchetti | [53 empty] | #VALUE! | #VALUE!
Samden Sherpa | [53 empty] | #VALUE! | #VALUE!
Zachary Rotter | [53 empty] | #VALUE! | #VALUE!
Laura Smit | [53 empty] | #VALUE! | #VALUE!
Kirby Taylor | [53 empty] | #VALUE! | #VALUE!
Bohao Zhu | [53 empty] | #VALUE! | #VALUE!
Shaunak Pandit | [53 empty] | #VALUE! | #VALUE!
Mason Guiste | [53 empty] | #VALUE! | #VALUE!
Amol Sharma | [53 empty] | #VALUE! | #VALUE!
Rostyk Svitelskyi | [53 empty] | #VALUE! | #VALUE!
Descoped (auto, will lose values once you change stories)
Christopher Lum |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Kevin Ueunten |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Madison Peck |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Richard Fukutome |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Keisuke Tsujita |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Al Creigh |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Davis |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bao Le |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Henry Qin |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Brian Chang |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Taylor Campbell |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Ablog |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Federico Alvarez |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Noel Kimber |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Dai Tsukada |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Robert McSwain |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Seunghyun Ko |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ryan Valach |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Aleksandr Tereshchenkov |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Justin Yantus |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
John Marshall |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Taras Eremenko |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Alec Bueing |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Alexander Summers |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Angel Rodriguez |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Brian Carpenter |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ben Landes |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bryan Ghahremani |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Cory Hage |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Dana Fraij |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Erli Sheng |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Hao Ruan |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Henry Ly |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jason Hung |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Justin Taft |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Mason Steinbrueck |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Maxine Tan |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Melanie Clark |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Pei Jia |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Randy Lirano |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Robert Soo |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Jones |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sanjit Samra |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Bolte |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tarik Haj-Khalil |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Gage Winde |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Brendan Doyle Wade |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nick Anderson |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Justin Chu |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Benjamin Pennant |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bing Hu |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Christina Hsu |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Dichek |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ananya Tegegn |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Andrew Jacobson |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Casey Kilborn |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Felipe Medeiros |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Hanah Olliges |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jessica Trinh |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Lien Chang |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Scott Hoang |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Stephanie Rogers |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tyler Sheehan |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Yifu Wang |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zach Caratao |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Courtney Yeager | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ward Handley | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Robert Larson | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Adrien Simkins | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Emil Caga-anan | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Madison Mackenzie | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Carter Beamish | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Varnum-Lowry | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Shida Xu | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Pico Premvuti | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Luke Macfarlan | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Marissa Reid | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jennifer Look | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Gizelle Gando | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Charlie Shaw-Feather | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Elaiza Luker | [6 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Harrison Stankey | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Scott An | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daehyun Kim | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zachary Pankratz | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Navdeep Sandhu | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Mia Lee | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Simeng Zhu | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zachary Williams | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sam Hordeski | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Connor Kafka | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Anupam Gupta | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Zhu | [13 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Arwa Sait | [13 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nathan Isaman | [13 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Andrea Ostwald | [13 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Aaron Goldfogel | [13 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tadej Kosel | [13 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Arzouman | [26 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vitor Vasconcelos | [26 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Selina Lui | [26 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zhenzhen Su | [26 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Hannah Rotta | [36 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Andrew Park | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jenny Garner | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Aditya Sharma | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Chris Nee | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Lee | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Matthew | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Eze Klarnet | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
James Kurniawan | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jason Borgida | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Karine Chen | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Michael Brady | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Riley Turk | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ryan Grimes | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Shumin Lin | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Truc Hoa | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Aaron Su | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Max McDonald | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Taehan Kook | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tommy Zhou | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
BJ Arun | [40 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Brett Myers | [40 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Kelsey Gabel | [40 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Kibaek Jeong | [40 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ge Bao | [41 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Maius Wong | [41 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sicong Huang | [41 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nikita Filippov | [42 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sam Buxton | [42 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Alex Banh | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Cole Morgan | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Conor Reiland | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Helen Kuni | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Lanhao Wu | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nicholas Price | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nick Armstrong | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nico Miguel | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Riley Harris | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Szymon Sarnowicz | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zach Kirwan | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Kai Simpson | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Carter Kraus | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Keegan McGrath | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ken Sekine | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Lee | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Gavin Cai | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Richard Jiang | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Adam Mokhalalati | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
TJ Stark | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Mircea Cozmei | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tinnabhand Patana-anake | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sean Lin | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Lemelin | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Forrest Malcolm | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Rick Huang | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tom Pflibsen | [46 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Eric Wang | [46 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Alex Lange | [46 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
David Kim | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ravi Patel | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Andrew Redd | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Emilynn Roehrich | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Areesa Trevino | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Chung Choi | [48 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bryson Bruno | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jason Yarrow | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sita Manne | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jaspreet Sidhu | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sai Ranganathan | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Griffin Klett | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Dylan Hoff | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sid Raman | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Deepanshu Gupta | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tushar Lakhanpal | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Firn Tieanklin | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Caelen Wang | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Joshua Brockschmidt | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Mike Kurnia | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Varith Hong | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vivian Hua | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Blake Fletcher | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Orion Black-Brown | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Travis Clement | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jacob Longhurst | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Grant Bringham | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tao Jin | [52 empty] | #VALUE! | #VALUE! | #VALUE!
Yao Dou | [52 empty] | #VALUE! | #VALUE! | #VALUE!
Sheershak Agarwal | [52 empty] | #VALUE! | #VALUE! | #VALUE!
Alex Bernard | [53 empty] | #VALUE! | #VALUE!
Christopher Lynch | [53 empty] | #VALUE! | #VALUE!
Gabriella Sciuchetti | [53 empty] | #VALUE! | #VALUE!
Samden Sherpa | [53 empty] | #VALUE! | #VALUE!
Zachary Rotter | [53 empty] | #VALUE! | #VALUE!
Laura Smit | [53 empty] | #VALUE! | #VALUE!
Kirby Taylor | [53 empty] | #VALUE! | #VALUE!
Bohao Zhu | [53 empty] | #VALUE! | #VALUE!
Shaunak Pandit | [53 empty] | #VALUE! | #VALUE!
Mason Guiste | [53 empty] | #VALUE! | #VALUE!
Amol Sharma | [53 empty] | #VALUE! | #VALUE!
Rostyk Svitelskyi | [53 empty] | #VALUE! | #VALUE!
Descoped
Christopher Lum | [8 empty] | 3 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 8 | 13 | 13 |  | 8 | 0 | 8 | 0 | 21 | 16 | 8 | 11 | 0 | 11 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 2 | 2 | 6 | #VALUE! | THESE RED CELLS ARE HARD CODED VALUES SO DO NOT CHANGE THEM, JUST UPDATE THE STRUCTURE OF THE TABLE
Kevin Ueunten | [8 empty] | 0 | 0 | 5 | 0 | 0 | 0 | #VALUE! | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Madison Peck | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Richard Fukutome | [8 empty] | 0 | 8 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Keisuke Tsujita | [8 empty] | 3 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 8 | 8 | 8 | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Al Creigh | [8 empty] | 3 | 0 | 3 | 0 | 0 | 0 | #VALUE! | 3 | 0 | 5 | 8 | 8 | 11 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Matthew Davis | [8 empty] | 0 | 3 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Bao Le | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Henry Qin | [8 empty] | 3 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 5 | 0 | 0 | 0 | 5 | 0 | 3 |  | 0 | 3 | 8 | 5 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Brian Chang | [8 empty] | 3 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 3 | 0 | 3 | 3 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Taylor Campbell | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Daniel Ablog | [8 empty] | 3 | 3 | 3 | 0 | 0 | 0 | #VALUE! | 3 | 0 | 0 | 8 | 8 | 5 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Federico Alvarez | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Noel Kimber | [8 empty] | 5 | 5 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 5 | 5 | 5 | 5 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Dai Tsukada | [8 empty] | 5 | 5 | 0 | 0 | 0 | 0 | #VALUE! | 10 | 0 | 5 | 5 | 5 | 5 | 5 |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Robert McSwain | [8 empty] | 0 | 1 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Seunghyun Ko | [8 empty] | 2 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Ryan Valach | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 5 | 0 | 3 | 8 | 8 | 0 | 3 |  | 8 | 3 | 8 | 5 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Aleksandr Tereshchenkov | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 5 | 0 | 0 | 13 | 16 | 0 | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Justin Yantus | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 2 | 0 | 2 | 4 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
John Marshall | [8 empty] | 6 | 5 | 5 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Taras Eremenko | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Alec Bueing | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 5 | 0 | 3 | 3 | 0 | 8 | 11 |  | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 3 | 0 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Alexander Summers | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 3 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Angel Rodriguez | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 3 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Brian Carpenter | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 5 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 15 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Ben Landes | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Bryan Ghahremani | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 3 | 0 | 3 | 0 | 0 | 5 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Cory Hage | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 5 | 0 | 0 | 10 | 5 | 13 | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Dana Fraij | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Erli Sheng | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Hao Ruan | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 8 | 0 | 13 | 8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Henry Ly | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Jason Hung | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 8 | 0 | 0 | 8 | 3 | 3 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Justin Taft | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 8 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Mason Steinbrueck | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 5 | 0 | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Maxine Tan | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 5 | 0 | 0 | 5 | 5 | 6 | 6 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Melanie Clark | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 3 | 3 | 3 | 5 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Pei Jia | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Randy Lirano | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Robert Soo | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Matthew Jones | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 3 | 5 | 5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Sanjit Samra | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 6 | 3 | 3 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Matthew Bolte | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 4 | 9 | 8 | 8 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Tarik Haj-Khalil | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 8 | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Gage Winde | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 5 | 5 | 0 | 3 |  | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 5 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Brendan Doyle Wade | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 8 | 5 | 5 | 5 |  | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Nick Anderson | [20 empty] | 0 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Justin Chu | [20 empty] | 8 | 8 |  | 8 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
Benjamin Pennant | [20 empty] | 2 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Bing Hu | [20 empty] | 2 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Christina Hsu | [20 empty] | 0 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Daniel Dichek | [20 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ananya Tegegn | [23 empty] | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
Andrew Jacobson | [23 empty] | 3 | 5 | 3 | 3 | 3 | 5 | 0 | 8 | 8 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
Casey Kilborn | [23 empty] | 8 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
Felipe Medeiros | [23 empty] | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
Hanah Olliges | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jessica Trinh | [23 empty] | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
Lien Chang | [23 empty] | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Scott Hoang | [23 empty] | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
Stephanie Rogers | [23 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
Tyler Sheehan | [23 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
Yifu Wang | [23 empty] | 3 | 3 | 3 | 8 | 3 | 3 | 8 | 3 | 3 | 8 | 8 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59
Zach Caratao | [23 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41
Courtney Yeager | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ward Handley | [24 empty] | 0 | 0 | 0 | 16 | 2 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
Robert Larson | [24 empty] | 0 | 0 | 0 | 10 | 10 | 16 | 0 | 13 | 5 | 10 | 8 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96
Adrien Simkins | [26 empty] | 8 | 6 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
Emil Caga-anan | [26 empty] | 0 | 0 | 8 | 0 | 7 | 1 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
Madison Mackenzie | [26 empty] | 1 | 7 | 4 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
Carter Beamish | [26 empty] | 4 | 8 | 8 | 7 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
Daniel Varnum-Lowry | [26 empty] | 0 | 3 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
Shida Xu | [26 empty] | 3 | 0 | 0 | 0 | 11 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 5 | 17 | 1 | 0 | 46
Pico Premvuti | [26 empty] | 0 | 8 | 5 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
Luke Macfarlan | [26 empty] | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
Marissa Reid | [26 empty] | 0 | 5 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34
Jennifer Look | [26 empty] | 1 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
Gizelle Gando | [26 empty] | 0 | 5 | 5 | 0 | 8 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42
Charlie Shaw-Feather | [26 empty] | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Elaiza Luker | [26 empty] | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48
Harrison Stankey | [29 empty] | 5 | 0 | 6 | 5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
Scott An | [29 empty] | 2 | 7 | 5 | 8 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
Daehyun Kim | [29 empty] | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
Zachary Pankratz | [29 empty] | 10 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
Navdeep Sandhu | [29 empty] | 0 | 0 | 8 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34
Mia Lee | [29 empty] | 0 | 0 | 11 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
Simeng Zhu | [29 empty] | 0 | 3 | 3 | 9 | 0 | 5 | 0 | 0 | 0 | 0 | 11 | 16 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
Zachary Williams | [29 empty] | 2 | 10 | 0 | 19 | 0 | 0 | 0 | 6 | 8 | 14 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 24 | 0 | 97
Sam Hordeski | [29 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Connor Kafka | [29 empty] | 2 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 11 | 0 | 0 | 43
Anupam Gupta | [29 empty] | 0 | 5 | 5 | 0 | 3 | 3 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
Daniel Zhu | [31 empty] | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
Arwa Sait | [33 empty] | 6 | 4 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
Nathan Isaman | [33 empty] | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48
Andrea Ostwald | [33 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Aaron Goldfogel | [33 empty] | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
Tadej Kosel | [33 empty] | 3 | 19 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
Daniel Arzouman | [35 empty] | 0 | 0 | 0 | 16 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48
Vitor Vasconcelos | [35 empty] | 3 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
Selina Lui | [35 empty] | 8 | 11 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 9 | 0 | 8 | 54
Zhenzhen Su | [35 empty] | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Hannah Rotta | [36 empty] | 8 | 0 | 2 | 1 | 0 | 3 | 8 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 13 | 21 | 3 | 10 | 89
Andrew Park | [38 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Jenny Garner | [38 empty] | 5 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
Aditya Sharma | [38 empty] | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
Chris Nee | [38 empty] | 11 | 8 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
Daniel Lee | [38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daniel Matthew | [38 empty] | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
Eze Klarnet | [38 empty] | 16 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48
James Kurniawan | [38 empty] | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Jason Borgida | [38 empty] | 5 | 8 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
Karine Chen | [38 empty] | 5 | 3 | 5 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 40
Michael Brady | [38 empty] | 8 | 8 | 8 | 8 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38
Riley Turk | [38 empty] | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 8 | 8 | 0 | 26
Ryan Grimes | [38 empty] | 0 | 3 | 0 | 10 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 2 | 17 | 1 | 0 | 43
Shumin Lin | [38 empty] | 8 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
Truc Hoa | [38 empty] | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Aaron Su | [39 empty] | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Max McDonald | [39 empty] | 5 | 3 | 5 | 5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
Taehan Kook | [39 empty] | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5 | 28
Tommy Zhou | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BJ Arun | [40 empty] | 0 | 4 | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
Brett Myers | [40 empty] | 0 | 2 | 20 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
Kelsey Gabel | [40 empty] | 0 | 3 | 11 | 7 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
Kibaek Jeong | [40 empty] | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
Ge Bao | [41 empty] | 7 | 0 | 8 | 3 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
Maius Wong | [41 empty] | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Sicong Huang | [41 empty] | 4 | 0 | 10 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
Nikita Filippov | [42 empty] | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Sam Buxton | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex Banh | [43 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 24 | 24 | 96
Cole Morgan | [43 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Conor Reiland | [43 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Helen Kuni | [43 empty] | 0 | 3 | 3 | 0 | 0 | 5 | 0 | 0 | 2 | 0 | 5 | 18
Lanhao Wu | [43 empty] | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Nicholas Price | [43 empty] | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 9
Nick Armstrong | [43 empty] | 2 | 2 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
Nico Miguel | [43 empty] | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Riley Harris | [43 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Szymon Sarnowicz | [43 empty] | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Zach Kirwan | [43 empty] | 2 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 18
Kai Simpson | [43 empty] | 2 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
Carter Kraus | [44 empty] | 0 | 0 | 9 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 19
Keegan McGrath | [44 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Ken Sekine | [44 empty] | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 7
Matthew Lee | [44 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Gavin Cai | [44 empty] | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
Richard Jiang | [44 empty] | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Adam Mokhalalati | [45 empty] | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
TJ Stark | [45 empty] | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Mircea Cozmei | [45 empty] | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 10
Tinnabhand Patana-anake | [45 empty] | 0 | 15 | 8 | 0 | 0 | 3 | 3 | 3 | 0 | 32
Sean Lin | [45 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Matthew Lemelin | [45 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Forrest Malcolm | [45 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rick Huang | [45 empty] | 0 | 5 | 0 | 5 | 0 | 6 | 3 | 0 | 0 | 19
Tom Pflibsen | [46 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Eric Wang | [46 empty] | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 18
Alex Lange | [46 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
David Kim | [47 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ravi Patel | [47 empty] | 0 | 1 | 0 | 5 | 8 | 0 | 16 | 30
Andrew Redd | [47 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Emilynn Roehrich | [47 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Areesa Trevino | [47 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Chung Choi | [48 empty] | 0 | 0 | 0 | 5 | 5 | 14 | 24
Bryson Bruno | [50 empty] | 3 | 3 | 6 | 3 | 15
Jason Yarrow | [50 empty] | 0 | 0 | 0 | 0 | 0
Sita Manne | [50 empty] | 3 | 5 | 5 | 0 | 13
Jaspreet Sidhu | [50 empty] | 0 | 0 | 2 | 0 | 2
Sai Ranganathan | [50 empty] | 0 | 3 | 3 | 5 | 11
Griffin Klett | [50 empty] | 2 | 2 | 0 | 0 | 4
Dylan Hoff | [50 empty] | 2 | 9 | 0 | 0 | 11
Sid Raman | [50 empty] | 2 | 2 | 0 | 0 | 4
Deepanshu Gupta | [50 empty] | 2 | 3 | 0 | 0 | 5
Tushar Lakhanpal | [50 empty] | 2 | 5 | 5 | 2 | 14
Firn Tieanklin | [50 empty] | 2 | 2 | 2 | 2 | 8
Caelen Wang | [50 empty] | 0 | 0 | 0 | 0 | 0
Joshua Brockschmidt | [50 empty] | 6 | 4 | 7 | 7 | 24
Mike Kurnia | [50 empty] | 2 | 7 | 4 | 0 | 13
Varith Hong | [50 empty] | 0 | 0 | 0 | 0 | 0
Vivian Hua | [50 empty] | 0 | 2 | 2 | 0 | 4
Blake Fletcher | [50 empty] | 0 | 0 | 0 | 0 | 0
Orion Black-Brown | [51 empty] | 0 | 0 | 0 | 0
Travis Clement | [51 empty] | 10 | 0 | 0 | 10
Jacob Longhurst | [51 empty] | 0 | 0 | 0 | 0
Grant Bringham | [51 empty] | 2 | 2 | 2 | 6
Tao Jin | [52 empty] | 0 | 3 | 3
Yao Dou | [52 empty] | 3 | 2 | 5
Sheershak Agarwal | [52 empty] | 0 | 4 | 4
Alex Bernard | [53 empty] | 2 | 2
Christopher Lynch | [53 empty] | 6 | 6
Gabriella Sciuchetti | [53 empty] | 4 | 4
Samden Sherpa | [53 empty] | 2 | 2
Zachary Rotter | [53 empty] | 9 | 9
Laura Smit | [53 empty] | 12 | 12
Kirby Taylor | [53 empty] | 12 | 12
Bohao Zhu | [53 empty] | 11 | 11
Shaunak Pandit | [53 empty] | 3 | 3
Mason Guiste | [53 empty] | 3 | 3
Amol Sharma | [53 empty] | 5 | 5
Rostyk Svitelskyi | [53 empty] | 0 | 0
Shame Index (Accepted - Descoped) | [54 empty] | TOTAL (lower number means more shame)
Christopher Lum |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Kevin Ueunten |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Madison Peck |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Richard Fukutome |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Keisuke Tsujita |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Al Creigh |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Davis |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bao Le |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Henry Qin |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Brian Chang |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Taylor Campbell |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Ablog |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Federico Alvarez |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Noel Kimber |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Dai Tsukada |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Robert McSwain |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Seunghyun Ko |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ryan Valach |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Aleksandr Tereshchenkov |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Justin Yantus |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
John Marshall |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Taras Eremenko |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Alec Bueing |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Alexander Summers |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Angel Rodriguez |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Brian Carpenter |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ben Landes |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bryan Ghahremani |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Cory Hage |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Dana Fraij |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Erli Sheng |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Hao Ruan |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Henry Ly |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jason Hung |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Justin Taft |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Mason Steinbrueck |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Maxine Tan |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Melanie Clark |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Pei Jia |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Randy Lirano |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Robert Soo |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Jones |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sanjit Samra |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Bolte |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tarik Haj-Khalil |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Gage Winde |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Brendan Doyle Wade |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nick Anderson |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Justin Chu |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Benjamin Pennant |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bing Hu |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Christina Hsu |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Dichek |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ananya Tegegn |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Andrew Jacobson |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Casey Kilborn |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Felipe Medeiros |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Hanah Olliges |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jessica Trinh |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Lien Chang |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Scott Hoang |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Stephanie Rogers |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tyler Sheehan |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Yifu Wang |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zach Caratao |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Courtney Yeager |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ward Handley |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Robert Larson |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Adrien Simkins |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Emil Caga-anan |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Madison Mackenzie |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Carter Beamish |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Varnum-Lowry |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Shida Xu |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Pico Premvuti |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Luke Macfarlan |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Marissa Reid |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jennifer Look |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Gizelle Gando |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Charlie Shaw-Feather |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Elaiza Luker |  |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Harrison Stankey |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Scott An |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daehyun Kim |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zachary Pankratz |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Navdeep Sandhu |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Mia Lee |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Simeng Zhu |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zachary Williams |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sam Hordeski |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Connor Kafka |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Anupam Gupta |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Zhu |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Arwa Sait |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nathan Isaman | [24 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Andrea Ostwald | [24 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Aaron Goldfogel | [24 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tadej Kosel | [24 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Arzouman | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vitor Vasconcelos | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Selina Lui | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zhenzhen Su | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Hannah Rotta | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Andrew Park | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jenny Garner | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Aditya Sharma | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Chris Nee | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Lee | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Daniel Matthew | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Eze Klarnet | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
James Kurniawan | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jason Borgida | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Karine Chen | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Michael Brady | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Riley Turk | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ryan Grimes | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Shumin Lin | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Truc Hoa | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Aaron Su | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Max McDonald | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Taehan Kook | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tommy Zhou | [38 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
BJ Arun | [40 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Brett Myers | [40 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Kelsey Gabel | [40 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Kibaek Jeong | [40 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ge Bao | [41 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Maius Wong | [41 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sicong Huang | [41 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nikita Filippov | [42 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sam Buxton | [42 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Alex Banh | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Cole Morgan | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Conor Reiland | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Helen Kuni | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Lanhao Wu | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nicholas Price | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nick Armstrong | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Nico Miguel | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Riley Harris | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Szymon Sarnowicz | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Zach Kirwan | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Kai Simpson | [43 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Carter Kraus | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Keegan McGrath | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ken Sekine | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Lee | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Gavin Cai | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Richard Jiang | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Adam Mokhalalati | [44 empty] | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
TJ Stark | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Mircea Cozmei | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tinnabhand Patana-anake | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sean Lin | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Matthew Lemelin | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Forrest Malcolm | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Rick Huang | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tom Pflibsen | [46 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Eric Wang | [46 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Alex Lange | [46 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
David Kim | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Ravi Patel | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Andrew Redd | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Emilynn Roehrich | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Areesa Trevino | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Chung Choi | [47 empty] | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bryson Bruno | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jason Yarrow | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sita Manne | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jaspreet Sidhu | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sai Ranganathan | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Griffin Klett | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Dylan Hoff | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sid Raman | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Deepanshu Gupta | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tushar Lakhanpal | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Firn Tieanklin | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Caelen Wang | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Joshua Brockschmidt | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Mike Kurnia | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Varith Hong | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vivian Hua | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Blake Fletcher | [50 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Orion Black-Brown | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Travis Clement | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Jacob Longhurst | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Grant Bringham | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Tao Jin | [52 empty] | #VALUE! | #VALUE! | #VALUE!
Yao Dou | [52 empty] | #VALUE! | #VALUE! | #VALUE!
Sheershak Agarwal | [52 empty] | #VALUE! | #VALUE! | #VALUE!
Alex Bernard | [53 empty] | #VALUE! | #VALUE!
Christopher Lynch | [53 empty] | #VALUE! | #VALUE!
Gabriella Sciuchetti | [53 empty] | #VALUE! | #VALUE!
Samden Sherpa | [53 empty] | #VALUE! | #VALUE!
Zachary Rotter | [53 empty] | #VALUE! | #VALUE!
Laura Smit | [53 empty] | #VALUE! | #VALUE!
Kirby Taylor | [53 empty] | #VALUE! | #VALUE!
Bohao Zhu | [53 empty] | #VALUE! | #VALUE!
Shaunak Pandit | [53 empty] | #VALUE! | #VALUE!
Mason Guiste | [53 empty] | #VALUE! | #VALUE!
Amol Sharma | [53 empty] | #VALUE! | #VALUE!
Rostyk Svitelskyi | [53 empty] | #VALUE! | #VALUE!

## sizing_mappings
size | points | estimated hours | comment
XS | 1 | 5 | a few hours
S | 2 | 10 | a few days
M | 3 | 15 | a week
L | 5 | 25 | a few weeks
XL | 8 | 40 | takes entire sprint (4 weeks)
XXL | N/A | - | Too big for 1 sprint
Estimated maximum workload is 10 hours/week (4 weeks per sprint = 40 hours per sprint maximum) |  | These assume a 40 hour work week
Estimated maximum hours per sprint
40
Expected time/story point commitment for research credits
hr/(wk*credit) | 3
Number credits | hr/wk | hr/quarter | expected story points per quarter
1 | 3 | 30 | 6
2 | 6 | 60 | 12
3 | 9 | 90 | 18
4 | 12 | 120 | 24
5 | 15 | 150 | 30
6 | 18 | 180 | 36

## status_mappings
status | value
in backlog | 0
in progress | 1
finished | 2
accepted | 3
stretch goal | 4
blocked | 5
descoped | 6